## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | FHTC |  |  | VCH/001622/2021-2022 | BP_2021_22_446 | 11/03/2022 |  | M/S BADAL CH SAHA | 14.11 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | FHTC |  |  | VCH/001693/2021-2022 | BP_2021_22_488 | 30/03/2022 |  | MS SSB CONSTRUCTION CO | 6.85 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | fhtc |  |  | VCH/000111/2022-2023 | BP-2022-23-22 | 13/04/2022 |  | ASHIM KUMAR CHAKRABORTY | 0.31 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of SALMARA PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000447/2021-2022 | 1437/CD | 10/03/2022 | 09/04/2022 | TAPAN CHANDA | 10.7 | 10.35 | 96.74 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at SALMARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000340/2022-2023 | 993/CD | 29/09/2022 | 29/10/2022 | SANKAR CHAKRABORTY | 80.14 | 34 | 42.43 | 1
6 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Quotation for new service connection at Salmara P/H No-I. Application No- 4003022299 |  |  | BILL/00025/2022-2023 | BP-112/22-23 | 19/12/2022 |  | WBSEDCL | 0.85 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | FHTC AT SALMARA |  |  | VCH/000784/2022-2023 | 285 | 30/09/2022 |  | TAPAN CHANDA | 83.08 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | FHTC AT SALMARA |  |  | VCH/000785/2022-2023 | 279 | 30/09/2022 |  | TAPAN CHANDA | 71.31 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | FHTC AT SALMARA P KHANDA (dumniguri) |  |  | VCH/000347/2022-2023 | 290 | 29/09/2022 |  | SIBAPADA SINGHA ROY | 2.87 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | FHTC AT SINGIMARI BHRTAGURI Z-II |  |  | VCH/000350/2022-2023 | 304 P | 30/09/2022 |  | MS DGB ENTERPRISE | 18 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | SINKING & FHTC |  |  | VCH/000875/2022-2023 | 314 | 30/09/2022 |  | MS SSB CONSTRUCTION CO | 9.33 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Providing FHTC Construction of B/Wall Switch room & New Laying of Pipe Line and other allied works at SALMARA PWSS under Cooch Behar Division, PHED PART - A | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000434/2021-2022 | 1529/CD | 15/03/2022 | 13/06/2022 | SANKAR CHAKRABORTY | 131.89 | 98.14 | 74.41 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | FHTC AT COB DIVN. PWSS |  |  | VCH/001335/2022-2023 | BP-240-22-23-P2 | 02/09/2022 |  | BRISTI CONSTRUCTION | 13.4 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Providing FHTC and other allied works at salmara and others PWSS |  |  | BILL/00680/2022-2023 | BP-707-2022-23 | 01/03/2023 |  | SANKAR CHAKRABORTY | 46.14 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Providing FHTC and other allied works at salmara and others PWSS |  |  | BILL/00680/2022-2023 | BP-707-2022-23 | 01/03/2023 |  | SANKAR CHAKRABORTY | 46.14 | 0 | 0 | 0
16 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvination of Salmara water supply scheme, TW no III in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000759/2022-2023 | 171/NMD-II | 19/01/2023 | 18/02/2023 | BLUE PINE | 11.39 | 10.71 | 94.04 | 80
17 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 785/CD | 07/12/2021 |  | Resource Division | 20.26 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2021-2022 | 1589/CD | 24/03/2022 |  | Resource Division | 5.5 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2021-2022 | 1103/CD | 27/01/2022 |  | Resource Division | 46.18 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2021-2022 | 1196/CD | 01/02/2022 |  | Resource Division | 0.82 | 0 | 0 | 0
21 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Hiring of inspection vehicle for office of the Assistant Engineer , Coochbehar Mechanical Sub- Division, I.C.W JJM works under Northern Mechanical Division -II, P.H.E. Dte. | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001969/2023-2024 | 01318/CMSD | 29/12/2023 | 27/02/2024 | DIPAK SARKAR | 0.69 | 0 | 0 | 100
22 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Salmara water supply scheme | SM/09820 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 1534/CD | 16/08/2024 |  | Resource Division | 17.23 | 0 | 0 | 0
Total | [13 empty] | 637.17 | 153.21 | 24.05