## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Shifting of pipeline with street stand post with guard wall for platform and other allied works for Satbhandari PWSS under Cooch Behar Sadar Sub-division, PHED | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000275/2020-2021 | 95/SD | 17/08/2020 | 27/08/2020 | SWAPAN KR.SARKAR | 2.64 | 2.65 | 100.15 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Sinking of Big Dia Tubewell at 3RD Site of SATBHANDARI PWSS under JAL JEEVAN MISSION | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000244/2022-2023 | 728/CD | 27/08/2022 | 11/10/2022 | UTTAM SAHA | 11.68 | 10.93 | 93.54 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 1182/CD | 01/02/2022 | 01/02/2022 | Resource Division | 2.42 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Providing FHTC & New UPVC/DI Pipe line with other allied works (PART ¿B) at SATBHANDARI PWSS under Cooch Behar Division, PHED | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000374/2021-2022 | 1277/CD | 09/02/2022 | 10/05/2022 | SHYAMAL NATH | 11.06 | 10.99 | 99.3 | 5
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of SATBHANDARI PWSS under Cooch Behar Division PHE Dte. | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000498/2021-2022 | 1446/CD | 10/03/2022 | 09/04/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 10.7 | 10.61 | 99.17 | 1
6 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation Satbhandari water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000063/2023-2024 | 1200/NMD-II | 23/06/2023 | 23/07/2023 | S P ENTERPRISE (KOLKATA) | 10.9 | 10.76 | 98.68 | 100
7 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS under RWS, Cooch Behar Sub-Division by Junior Engineer, RWS, Cooch Behar Sub-Division under Cooch Behar Division, PHE Dte. for 04 (Four) Months. (From Oct. 2023 to January, 2024). (WB-63A 7065) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER,JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000300/2023-2024 | 1103/CD | 30/09/2023 | 31/01/2024 | RAJAN SARKAR | 0.67 | 0.17 | 25 | 100
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
Total | [13 empty] | 19839.37 | 46.1 | 0.23