## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Shifting of pipeline with street stand post with guard wall for platform and other allied works for Satbhandari PWSS under Cooch Behar Sadar Sub-division, PHED | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000275/2020-2021 | 95/SD | 17/08/2020 | 27/08/2020 | SWAPAN KR.SARKAR | 2.64 | 2.65 | 100.15 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Sinking of Big Dia Tubewell at 3RD Site of SATBHANDARI PWSS under JAL JEEVAN MISSION | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000244/2022-2023 | 728/CD | 27/08/2022 | 11/10/2022 | UTTAM SAHA | 11.68 | 10.93 | 93.54 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 1182/CD | 01/02/2022 |  | Resource Division | 2.42 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Providing FHTC & New UPVC/DI Pipe line with other allied works (PART ¿B) at SATBHANDARI PWSS under Cooch Behar Division, PHED | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000374/2021-2022 | 1277/CD | 09/02/2022 | 10/05/2022 | SHYAMAL NATH | 11.06 | 8.16 | 73.71 | 5
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of SATBHANDARI PWSS under Cooch Behar Division PHE Dte. | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000498/2021-2022 | 1446/CD | 10/03/2022 | 09/04/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 10.7 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvination of Sathbhandari water supply scheme | SM/09821 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation Satbhandari water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000063/2023-2024 | 1200/NMD-II | 23/06/2023 | 23/07/2023 | S P ENTERPRISE (KOLKATA) | 10.9 | 5.11 | 46.85 | 100
Total | [13 empty] | 19838.7 | 26.84 | 0.14