## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | FHTC |  |  | VCH/001627/2021-2022 | BP_2021_22_451 | 11/03/2022 |  | SIBAPADA SINGHA ROY | 5.07 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | FHTC |  |  | VCH/001628/2021-2022 | BP_2021_22_452 | 16/03/2022 |  | TAPAN CHANDA | 4.13 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | FHTC |  |  | VCH/001624/2021-2022 | BP_2021_22_448 | 11/03/2022 |  | MS BIDYUT SARKAR | 4.93 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | FHTC |  |  | VCH/001625/2021-2022 | BP_2021_22_449 | 11/03/2022 |  | PARITOSH PANDIT | 5.01 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | FHTC |  |  | VCH/001626/2021-2022 | BP_2021_22_450 | 11/03/2022 |  | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.99 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | COST OF PIPE |  |  | VCH/001700/2021-2022 | BP_2021_22_415 | 04/03/2022 |  | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 5.87 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | New laying of UPVC/DI Pipe Line, Providing F.H.T.C. & Other allied works at Dhaluabari (Part-C) PWSS under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000362/2021-2022 | 1265/CD | 09/02/2022 | 10/05/2022 | SAMBHU BANIK | 73.92 | 73.78 | 99.82 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | New laying of UPVC/DI Pipe Line, Providing F.H.T.C. & Other allied works at Dhaluabari (Part-B) PWSS under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000366/2021-2022 | 1269/CD | 09/02/2022 | 10/04/2022 | RAJIB CHAKRABORTY | 53.67 | 53.36 | 99.42 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Providing 150 nos F.H.T.C. for Dhaluabari (Part-C) W.S.S. under Cooch Behar Sadar Sub- Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000110/2022-2023 | 206/SD | 27/06/2022 | 27/07/2022 | BISWAJIT GUHA | 4.82 | 4.82 | 100 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Providing 150 nos F.H.T.C. for Dhaluabari (Part-A) W.S.S. under Cooch Behar Sadar Sub- Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000107/2022-2023 | 200/SD | 27/06/2022 | 27/07/2022 | SARKAR CONSTRUCTION | 4.82 | 0 | 0 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | New Laying of UPVC/DI Pipe line, Providing F.H.T.C. & other allied works at Dhaluabari (Part-F-2) PWSS Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000080/2022-2023 | 289/CD | 31/05/2022 | 20/06/2022 | BIPASHA MAHANTA BANIK | 5.04 | 5.04 | 100 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | New Laying of UPVC/DI Pipe line, Providing F.H.T.C. & other allied works at Dhaluabari (Part-F-1) PWSS Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000079/2022-2023 | 288/CD | 31/05/2022 | 20/06/2022 | PRIYANKA MANDAL | 5.04 | 5.01 | 99.39 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | FUEL BILL |  |  | VCH/000351/2022-2023 | null | 04/08/2022 |  | R.C.BANIK & SONS | 0.74 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Providing FHTC and laying of pipeline and other misc. Work under Dhaluabari PWSS under Cooch behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000527/2021-2022 | 1575/CD | 23/03/2022 | 07/05/2022 | GOURANGA DATTA | 4.99 | 4.99 | 100 | 1
15 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Quotation for new service connection at Dhaluabari W/SS TW No III |  |  | BILL/00012/2022-2023 | BP-99/22-23 | 08/12/2022 |  | WBSEDCL | 1.06 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | New laying of UPVC/DI Pipe Line, Providing F.H.T.C. & Other allied works at Dhaluabari (Part-E) PWSS under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000364/2021-2022 | 1267/CD | 09/02/2022 | 10/05/2022 | CHAKRABORTY ENTERPRISE. | 29.84 | 29.39 | 98.48 | 1
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Providing FHTC & Addl. laying of Pipe line and other allied works at DHALUABARI PWSS under JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000236/2022-2023 | 722/CD | 27/08/2022 | 11/10/2022 | CHAKRABORTY ENTERPRISE. | 12.62 | 12.62 | 100 | 1
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Execution of different works related to DHALUABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000785/2022-2023 | 1861/CD | 14/03/2023 | 13/04/2023 | SWAPAN KR.SARKAR | 36.97 | 36.96 | 99.98 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Providing FHTC & Repairing of OHR B/Wall suplly Stairecase constn of Addl. Phouse at Dhaluabari PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000241/2022-2023 | 727/CD | 27/08/2022 | 11/10/2022 | SWAPAN KR.SARKAR | 35.48 | 35.42 | 99.85 | 1
20 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of DHALUABARI PWSS, TW no III in the district of Coochbehar under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000731/2022-2023 | 63/NMD-II | 09/01/2023 | 08/02/2023 | SUBODH KUMAR BANIK | 11.26 | 10.56 | 93.81 | 80
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Execution of different works related to DHALUABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000782/2022-2023 | 1698/CD | 13/02/2023 | 05/03/2023 | GOUTAM KUMAR DAS | 8.6 | 0 | 0 | 100
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of DHALUABARI PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000448/2021-2022 | 1438/CD | 10/03/2022 | 09/04/2022 | TAPAN CHANDA | 10.7 | 10.72 | 100.14 | 0
23 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | New laying of UPVC/DI Pipe Line, Providing F.H.T.C. & Other allied works at Dhaluabari (Part-F) PWSS under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000363/2021-2022 | 1266/CD | 09/02/2022 | 10/04/2022 | SUSHANTA SAHA | 37.17 | 31.28 | 84.15 | 0
24 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Providing FHTC Pump House & Boundary wall New UPVC/DI Pipe line with other allied works (PART ¿A) at DHALUABARI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000418/2021-2022 | 1516/CD | 15/03/2022 | 13/07/2022 | SWAPAN KR.SARKAR | 107.41 | 105.49 | 98.21 | 1
25 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Execution of different works related to DHALUABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000453/2022-2023 | 1429/CD/W | 29/12/2022 | 28/01/2023 | KARTICK CH SEAL | 3.11 | 3.11 | 100 | 100
26 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | New laying of UPVC/DI Pipe Line, Providing F.H.T.C. & Other allied works at Dhaluabari (Part-D) PWSS under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000365/2021-2022 | 1268/CD | 09/02/2022 | 26/03/2022 | SWAPAN SAHA | 45.41 | 45.09 | 99.29 | 1
27 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 791/CD | 07/12/2021 |  | Resource Division | 20.29 | 0 | 0 | 0
28 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2021-2022 | 1177/CD | 01/02/2022 |  | Resource Division | 1.65 | 0 | 0 | 0
29 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | EXECUTION OF DIFFERENT WORK AT TUPAMARI DEWANBAS PWSS |  |  | BILL/02048/2023-2024 | BP-1386 | 31/03/2024 |  | M/S DHAR ENTERPRISE | 25.71 | 0 | 0 | 0
30 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | Hiring of inspection vehicle for office of the Assistant Engineer , Coochbehar Mechanical Sub- Division, I.C.W JJM works under Northern Mechanical Division -II, P.H.E. Dte. | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001968/2023-2024 | 1012/CMSD | 31/10/2023 | 30/12/2023 | DIPAK SARKAR | 0.69 | 0 | 0 | 100
31 | COOCHBEHAR |  | Coochbehar Division | Augmentation of dhaluabari water supply scheme | SM/09822 | Augmentation | HIRING VEHICLE FOR AE/SD |  |  | BILL/00488/2024-2025 | null | 01/06/2024 |  | PARAUDDIN MIA | 0.55 | 0 | 0 | 0
Total | [13 empty] | 571.54 | 467.63 | 81.82