## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Providing functional house hold tap connection (unmetered) 135 nos. in NALANGIBARI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000319/2021-2022 | 329/MTB | 04/01/2022 | 19/01/2022 | PARITOSH PANDIT | 5.01 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Providing FHTC and Laying of Pipe line at NALANGIBARI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000411/2021-2022 | 1469/CD | 10/03/2022 | 09/04/2022 | PARITOSH PANDIT | 24.6 | 23.1 | 93.9 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Providing FHTC, Sinking of big dia tube well( 250 mm X 200 mm),Constuction of pump house, boundary wall,Repairing of reservior at head work site and laying of UPVC pipe line and other allied works at in-connection with augmentation NALANGIBARI PWSS under Cooch Behar Division, PHED.(Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000429/2021-2022 | 1525/CD | 15/03/2022 | 13/06/2022 | GHOSH AND SAHA CONSTRUCTION | 127.12 | 104.82 | 82.45 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Providing functional house hold tap connection within Nalangibari Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000130/2022-2023 | 132/MTB | 23/06/2022 | 08/07/2022 | NORTHE BENGAL CONST CO | 4.96 | 4.85 | 97.6 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Providing functional house hold tap connection within command area under Nalangibari Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000126/2022-2023 | 129/MTB | 23/06/2022 | 08/07/2022 | PARITOSH PANDIT | 4.82 | 4.81 | 99.81 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Supply of C.I Specials for NALANGIBARI PWSS under JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000246/2022-2023 | 739/CD | 27/08/2022 | 26/09/2022 | MS SSB CONSTRUCTION CO | 9.67 | 9.67 | 100 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Providing FHTC & other allied works at NALANGIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000281/2022-2023 | 888/CD | 22/09/2022 | 22/10/2022 | PARITOSH PANDIT | 9.98 | 9.13 | 91.47 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Providing functional house hold tap connection within command area of Nalangibari Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. (Part-F) Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000078/2022-2023 | 44/MTB | 02/05/2022 | 09/05/2022 | PARITOSH PANDIT | 4.96 | 4.93 | 99.54 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Laying of Additional boosting line for FHTC under BURABURI PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000067/2022-2023 | 264/CD | 24/05/2022 | 08/07/2022 | PARITOSH PANDIT | 11.73 | 0 | 0 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 1378/CD | 22/12/2022 | 22/12/2022 | Resource Division | 8.25 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | FHTC |  |  | VCH/001617/2021-2022 | BP_2021_22_441 | 11/03/2022 | 11/03/2022 | ORIENTAL CO OP LABOUR CONTRACT CONSTRUCTION SO | 8.82 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | FHTC |  |  | VCH/001769/2021-2022 | BP-2021_22_454 | 16/03/2022 | 16/03/2022 | TAPAN CHANDA | 1.26 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | PAYMENT TO RESOURCE DIV |  |  | VCH/001333/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 40 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Execution of different works related to NALANGIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000440/2022-2023 | 1417/CD | 29/12/2022 | 28/01/2023 | PINAKI SAHA | 9.57 | 6.71 | 70.14 | 1
15 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 1176/CD | 01/02/2022 | 01/02/2022 | Resource Division | 5.5 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 189/CD | 27/04/2023 | 27/04/2023 | Resource Division | 9.23 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | FHTC AT PWSS UNDER COB DIVN, PHED |  |  | VCH/000998/2022-2023 | 355 | 22/10/2022 | 22/10/2022 | MS SSB CONSTRUCTION CO | 3.15 | 0 | 0 | 0
18 | COOCHBEHAR |  | Northern Mechanical Division II | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT NALANGIBARI (AUG) W/SS TW IV |  |  | BILL/00015/2023-2024 | BP-2023-24-92 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
19 | COOCHBEHAR |  | Northern Mechanical Division II | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT NALANGIBARI (AUG) W/SS TW V |  |  | BILL/00016/2023-2024 | BP-2023-24-91 | 15/05/2023 | 15/05/2023 | WBSEDCL | 0.98 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Providing FHTC, Sinking of big dia tube well( 250 mm X 200 mm), Construction of pump house, boundary wall, Repairing of boundary wall at head work site and laying of UPVC pipe line and other allied works at in-connection with augmentation NALANGIBARI PWSS under Cooch Behar Division, PHED.(Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000430/2021-2022 | 1526/CD | 15/03/2022 | 13/06/2022 | GHOSH AND SAHA CONSTRUCTION | 166.74 | 92.68 | 55.59 | 70
21 | COOCHBEHAR |  | Northern Mechanical Division II | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NALANGIBARI TW no IV in the district of COOCHBEHAR under Northern Mechanical Division-II, PHE Dte ALIPURDUAR. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000806/2022-2023 | 398/NMD-II | 23/02/2023 | 25/03/2023 | ANUP BASU | 10.7 | 8.79 | 82.15 | 60
22 | COOCHBEHAR |  | Northern Mechanical Division II | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Nalangibari water supply scheme, TW no IV under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000174/2023-2024 | 1373/NMD-II | 12/07/2023 | 11/08/2023 | M/S ANJALI ENTERPRISE | 11 | 10.34 | 93.99 | 100
23 | COOCHBEHAR |  | Northern Mechanical Division II | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Supply & delivery of Submersible pump motor set and other Electro Mechanical Components at NALANGIBARI (AUG) PWSS and adjacent W/S Scheme in the district of Coochbehar under Northern Mechanical Division-II P.H.E Dte. |  | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000044/2024-2025 | 1935/CMSD | 13/06/2024 | 13/07/2024 | M/S SAJAHAN CHOWDHURY | 4.36 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Execution of different works related to NALANGIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000027/2023-2024 | 383/CD | 23/05/2023 | 18/01/2024 | MS SURAJIT MAJUMDER | 17.74 | 7.52 | 42.37 | 100
25 | COOCHBEHAR |  | Coochbehar Division | Augumentation of Nalangibari Water Supply scheme | SM/09823 | Augmentation | Execution of different works related to NALANGIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000771/2022-2023 | 1658/CD | 10/02/2023 | 01/02/2026 | KRISHNA GOPAL BASK | 28.46 | 23.74 | 83.44 | 70
Total | [13 empty] | 529.67 | 311.09 | 58.73