## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | fhtc |  |  | VCH/001596/2021-2022 | BP-2021-22-419 | 11/03/2022 |  | ASHIM KUMAR CHAKRABORTY | 4.32 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | FHTC |  |  | VCH/000031/2022-2023 | BP-22_23-38 | 13/04/2022 |  | KHOKAN DAS | 0.67 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Providing functional house hold tap connection within command area of PAYAMARI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. (Part-F). | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000051/2022-2023 | 46/MTB | 02/05/2022 | 17/05/2022 | UDAY CHAKI | 4.96 | 4.95 | 99.78 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Providing functional house hold tap connection within command area of PAYAMARI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. (Part-E). | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000052/2022-2023 | 40/MTB | 02/05/2022 | 17/05/2022 | UDAY CHAKI | 4.98 | 4.98 | 100 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Providing functional house hold tap connection (unmetered) 135 nos. in PAYAMARI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000546/2021-2022 | 463/MTB | 04/03/2022 | 19/03/2022 | COOCH BEHAR U/E CO-OP-LAB. CONT. & CONSTN. SO-LTD | 4.79 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Providing functional house hold tap connection within command area of Payamari Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme.Part-B | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000146/2022-2023 | 217/MTB | 27/07/2022 | 11/08/2022 | UDAY CHAKI | 4.82 | 4.82 | 100.01 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Providing functional house hold tap connection within command area of Payamari Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. (Part-A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000147/2022-2023 | 216/MTB | 26/07/2022 | 10/08/2022 | COOCH BEHAR U/E CO-OP-LAB. CONT. & CONSTN. SO-LTD | 4.8 | 4.8 | 99.89 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | FHTC PAYAMARI |  |  | VCH/000405/2022-2023 | BP-22-23-154 | 26/07/2022 |  | COOCHBEHAR ASSOCIATED UNEMPLOYED ENGINEERS COOP SOCY. LTD. | 4.77 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Providing functional house hold tap connection (unmetered) 125 nos. in PAYAMARI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E. Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000251/2020-2021 | 937/CD | 28/09/2020 | 12/11/2020 | AGNI UNEMP CO- OP LABOUR CONT & CONSTN. SOCY. LTD | 5.01 | 5.03 | 100.38 | 1
10 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of PAYAMARI water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar. |  |  | ORD/001041/2023-2024 | 2681/NMD-II | 11/09/2023 | 11/10/2023 | TAPAN BISWAS | 11.02 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Supply of C.I Specials for PAYAMARI PWSS under JAL JEEVAN MISSION. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000300/2022-2023 | 909/CD | 26/09/2022 | 26/10/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 9.68 | 9.56 | 98.77 | 1
12 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Electric Quotation Bill for NSC at PAYAMARI (REJU) |  |  | BILL/02235/2023-2024 | BP-2023-24-495 | 21/12/2023 |  | WBSEDCL | 3.88 | 0 | 0 | 0
13 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Electric Quotation Bill for NSC at PAYAMARI (REJU) |  |  | BILL/02235/2023-2024 | BP-2023-24-495 | 21/12/2023 |  | WBSEDCL | 3.88 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Providing FHTC Construction of B/Wall & New Laying of Pipe Line and other allied works at AUG. PAYAMARI PWSS under Cooch Behar Division, PHED PART - A | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000037/2022-2023 | 95/CD | 18/04/2022 | 17/07/2022 | DAS TRADING CO | 113.35 | 63 | 55.58 | 1
15 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of Payamari Water Supply Scheme | SM/09824 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 19970.23 | 97.14 | 0.49