## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | Providing FHTC & New laying UPVC/DI GI Pipe line construction of Sluice valve chamber & other allied works at NATABARI PWSS under Cooch Behar Division, PHED (PART ¿D) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000264/2021-2022 | 934/CD | 31/12/2021 | 30/04/2022 | SHREE RANI SATI ENTERPRISE | 156 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC |  |  | VCH/000047/2022-2023 | BP_22_23_20 | 13/04/2022 | 13/04/2022 | MATARA CONSTRUCTION CO. | 91.21 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | PAYMENT TO RESOUCE DIVN PHED |  |  | VCH/001332/2021-2022 | BP-2021-22-400 | 22/02/2022 | 22/02/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 30 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC |  |  | VCH/000063/2022-2023 | BP_22_23_48 | 13/04/2022 | 13/04/2022 | SHYAMAL NATH | 4.93 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC |  |  | VCH/001607/2021-2022 | BP_2021_22_431 | 10/03/2022 | 10/03/2022 | BIJOY ROY | 36.74 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC |  |  | VCH/000061/2022-2023 | BP_22_23_46 | 13/04/2022 | 13/04/2022 | DAS ENTERPRISE | 8.77 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC |  |  | VCH/000080/2022-2023 | BP_22_23_56 | 28/04/2022 | 28/04/2022 | SHREE RANI SATI ENTERPRISE | 9.58 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | fhtc |  |  | VCH/000116/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 0 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC AT NATABARI PART-A |  |  | VCH/000582/2022-2023 | 182 | 18/08/2022 | 18/08/2022 | SHREE RANI SATI ENTERPRISE | 25.95 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC NATABARI |  |  | VCH/000025/2022-2023 | BP-22_23-36 | 13/04/2022 | 13/04/2022 | SHREE RANI SATI ENTERPRISE | 113.55 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC |  |  | VCH/000144/2022-2023 | BP-22-23-74 | 27/05/2022 | 27/05/2022 | ORIENTAL CO OP LABOUR CONTRACT CONSTRUCTION SO | 7.94 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC |  |  | VCH/001759/2021-2022 | BP-2021_22_414 | 02/03/2022 | 02/03/2022 | ASHIM KUMAR CHAKRABORTY | 3.21 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC AT NATABARI |  |  | VCH/000649/2022-2023 | 215 | 25/08/2022 | 25/08/2022 | SHREE RANI SATI ENTERPRISE | 39.55 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC |  |  | VCH/000142/2022-2023 | BP-22-23-58 | 05/05/2022 | 05/05/2022 | MALAY KR.DEB | 8.77 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC |  |  | VCH/000069/2022-2023 | BP_22_23_54 | 28/04/2022 | 28/04/2022 | HIRAK CONSTRUCTION | 35.54 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000021/2021-2022 | 963/CD | 05/01/2022 | 05/01/2022 | Resource Division | 11 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000057/2021-2022 | 1200/CD | 01/02/2022 | 01/02/2022 | Resource Division | 1.65 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FUEL |  |  | VCH/000927/2022-2023 | 458 | 25/11/2022 | 25/11/2022 | ANJALI SERVICE CENTRE | 0.13 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FHTC AT SOULMARI PWS (NATABARI) |  |  | VCH/000548/2022-2023 | 331 P | 30/09/2022 | 30/09/2022 | CHAKRABORTY ENTERPRISE. | 0 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | EXECUTION OF DIFFERENT WORK AT BHOGDABRI PWSS |  |  | BILL/01991/2023-2024 | BP-1122-P2 | 02/03/2024 | 02/03/2024 | M/S MAA MANASA CONSTRUCTION CO. | 0 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | Providing FHTC & New laying UPVC/DI GI Pipe line construction of Sluice valve chamber & other allied works at NATABARI PWSS under Cooch Behar Division, PHED (PART ¿C) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000262/2021-2022 | 932/CD | 31/12/2021 | 30/04/2022 | SHREE RANI SATI ENTERPRISE | 159.16 | 0 | 0 | 87
22 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | Providing FHTC 3rd Site Pump House Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI/GI Pipe line and other allied works (PART ¿A) at NATABARI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000265/2021-2022 | 935/CD | 31/12/2021 | 15/03/2025 | SHREE RANI SATI ENTERPRISE | 199.28 | 0 | 0 | 90
23 | COOCHBEHAR |  | Coochbehar Division | Retrofitting works for providing functional household tap connection(FHTC) eithin the cpmmand area of Natabari Water Supply Scheme | SM/09831 | Retrofitting | FABRICATION AND INSTALLATION OF LAND POSSESSION SB AT EVERY LANDS OF DIFFERENT (NAGAR CHANGRABANDAAND MEGH NARAYANER KUTHI ) PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-C) | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000509/2024-2025 | 1794/CD | 30/09/2024 | 10/10/2024 | BIJOY ROY | 67.98 | 0 | 0 | 95
Total | [13 empty] | 1010.93 | 0 | 0