## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | fhtc dpr |  |  | VCH/001328/2021-2022 | BP-2021-22-363 | 17/02/2022 |  | SWAPAN KUMAR ROY | 2.83 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | fhtc |  |  | VCH/001329/2021-2022 | BP-2021-22-366 | 17/02/2022 |  | GOUTAM KUMAR DAS | 5.06 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | fhtc |  |  | VCH/001324/2021-2022 | BP-2021-22-358 | 08/02/2022 |  | GEETA CONSTRUCTION | 11.2 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | fhtc |  |  | VCH/001330/2021-2022 | BP-2021-22- 367 | 17/02/2022 |  | NABIN DEBNATH | 5.08 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | fhtc |  |  | VCH/001325/2021-2022 | BP-2021-22-359 | 08/02/2022 |  | MS SSB CONSTRUCTION CO | 4.91 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | fhtc |  |  | VCH/001326/2021-2022 | BP-2021-22-360 | 08/02/2022 |  | SHREE RANI SATI ENTERPRISE | 17.64 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | fhtc |  |  | VCH/001327/2021-2022 | BP-2021-22-361 | 08/02/2022 |  | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 2.12 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | FHTC |  |  | VCH/001668/2021-2022 | BP_2021_22_488 | 30/03/2022 |  | MS SSB CONSTRUCTION CO | 81.15 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | FHTC |  |  | VCH/000042/2022-2023 | BP_22_23_15 | 13/04/2022 |  | MS DD ENTERPRISE | 10.09 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | FHTC |  |  | VCH/000060/2022-2023 | BP_22_23_35 | 13/04/2022 |  | BISWAJIT GUHA | 4.94 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | FHTC |  |  | VCH/000079/2022-2023 | BP_22_23_56 | 28/04/2022 |  | SHREE RANI SATI ENTERPRISE | 3.63 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | FHTC |  |  | VCH/000236/2022-2023 | BP_97_22_23 | 20/06/2022 |  | GHOSH AND SAHA CONSTRUCTION | 1.19 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | Construction of 500 cum OHR Providing FHTC & New laying UPVC/DI GI Pipe line construction of Sluice valve chamber & other allied works at DEWANHAT PWSS under Cooch Behar Division, PHED (PART ¿A) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000245/2021-2022 | 894/CD | 24/12/2021 | 20/10/2022 | PALLAB BHAWAL | 239.96 | 191 | 79.59 | 1
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 962/CD | 05/01/2022 |  | Resource Division | 11 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000043/2021-2022 | 1179/CD | 01/02/2022 |  | Resource Division | 1.65 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 491/CD | 07/07/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 1956/CD | 24/03/2023 |  | Resource Division | 70.32 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 349/CD | 18/05/2023 |  | Resource Division | 6.24 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | Providing FHTC 3rd Site Pump House Boundary wall Sinking 250mm X 200mm Big dia Tubewell & New UPVC Pipe line with Rising main and other allied works (PART ¿B) at DEWANHAT PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000246/2021-2022 | 895/CD | 24/12/2021 | 23/04/2022 | PALLAB BHAWAL | 168.68 | 48.83 | 28.95 | 53
20 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | Providing FHTC & New laying UPVC/DI GI Pipe line construction of Sluice valve chamber & other allied works at DEWANHAT PWSS under Cooch Behar Division, PHED (PART ¿C) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000247/2021-2022 | 896/CD | 24/12/2021 | 23/04/2022 | SWAPAN KUMAR ROY | 172.79 | 155.05 | 89.73 | 80
21 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | quotation for new connection dewanhat tw 3 |  |  | BILL/01310/2023-2024 | BP-1039 | 13/02/2024 |  | WBSEDCL | 7.58 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | quotation for new connection dewanhat tw 4 |  |  | BILL/01309/2023-2024 | BP-1038 | 13/02/2024 |  | WBSEDCL | 4.94 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | Name of Work: Execution of different works related to DEWANHAT PWSS under JAL JEEVAN MISSION PART D | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000254/2023-2024 | 1021/CD | 22/09/2023 | 21/11/2023 | SIDHARTHA ROY | 47.65 | 0 | 0 | 100
24 | COOCHBEHAR |  | Coochbehar Division | Retrofitting cum rejuvenation of Dewanhat Piped Water Suply Scheme under Coochbehar Division PHE Dte. | SM/09832 | Retrofitting | Execution of different works at Dewanhat Sub District Water Testing Laboratory related to Dewanhat PWSS under JAL JEEVAN MISSION. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000163/2023-2024 | 940/CD | 04/09/2023 | 03/12/2023 | M/S A. B. ENTERPRISE | 79.59 | 59.33 | 74.54 | 47
Total | [13 empty] | 972.58 | 454.21 | 46.7