## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | FHTC |  |  | VCH/001646/2021-2022 | BP-2021_22_470 | 23/03/2022 |  | NABIN DEBNATH | 100 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | FHTC |  |  | VCH/000044/2022-2023 | BP_22_23_17 | 13/04/2022 |  | KHOKAN DAS | 13.32 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | FHTC |  |  | VCH/000078/2022-2023 | BP_22_23_56 | 28/04/2022 |  | SHREE RANI SATI ENTERPRISE | 8.83 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | ELETRICITY BILL |  |  | VCH/000196/2022-2023 | BP_85_22_23 | 10/06/2022 |  | WBSEDCL | 0.6 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | FHTC BALARAMPUR |  |  | VCH/000234/2022-2023 | BP-22_23-98 | 16/06/2022 |  | GHOSH AND SAHA CONSTRUCTION | 150.33 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | HIRING VECHILE |  |  | VCH/000403/2022-2023 | BP-22-23-138 | 14/07/2022 |  | SUDIP BASAK | 0.2 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Providing FHTC, New Laying of balance Pipe Line, New Construction Darin & Other allied works related to pipe line at BALARAMPUR Zone-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000202/2022-2023 | 677/CD | 23/08/2022 | 22/10/2022 | TAPAN CHANDA | 49.62 | 48.9 | 98.57 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Providing FHTC H W Site Pump House Sinking 250mm X 200mm Big dia Tubewell & New UPVC Pipe line with Rising main and other allied works (PART ¿B) at BALARAMPUR ZONE ¿ I I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000266/2021-2022 | 936/CD | 31/12/2021 | 29/06/2022 | TAPAN CHANDA | 166.46 | 162.8 | 97.8 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 1381/CD | 22/12/2022 |  | Resource Division | 61.6 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Providing FHTC & other allied works at BALARAMPUR ZII PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000369/2022-2023 | 1022/CD | 29/09/2022 | 29/10/2022 | TAPAN CHANDA | 10.03 | 10.01 | 99.81 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Construction of 550 cum OHR Providing FHTC & New UPVC Pipe line & other allied works (PART ¿A) at BALARAMPUR ZONE ¿ I I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000267/2021-2022 | 937/CD | 31/12/2021 | 27/10/2022 | TAPAN CHANDA | 238.65 | 225.98 | 94.69 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Providing FHTC & other allied works at BALARAMPUR ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000370/2022-2023 | 1023/CD | 29/09/2022 | 29/10/2022 | SIDHARTHA ROY | 10 | 10 | 100 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Supply and delivery of 200 mm dia UPVC pipe(CD) for Balarampur Zone-I H/W Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000519/2021-2022 | 1567/CD | 23/03/2022 | 07/04/2022 | GHOSH AND SAHA CONSTRUCTION | 2.98 | 2.98 | 100 | 1
14 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Providing FHTC 3rd Site Pump House Boundary wall Sinking 250mm X 200mm Big dia Tubewell & New UPVC Pipe line with Rising main and other allied works (PART ¿C) at BALARAMPUR ZONE ¿ I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000248/2021-2022 | 897/CD | 24/12/2021 | 23/04/2022 | GEETA CONSTRUCTION | 158.3 | 9.5 | 6 | 1
15 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Supply and delivery of UPVC pipe (CD) conforming to IS 12818:2010. (CIPET Certified) at 3rd site tubewell of Balarampur Zone-I under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000085/2022-2023 | 293/CD | 31/05/2022 | 20/06/2022 | GEETA CONSTRUCTION | 2.98 | 2.98 | 100 | 1
16 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Providing FHTC H W Site Pump House Sinking 250mm X 200mm Big dia Tubewell & New UPVC Pipe line with Rising main and other allied works (PART ¿B) at BALARAMPUR ZONE ¿ I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000249/2021-2022 | 898/CD | 24/12/2021 | 23/04/2022 | GHOSH AND SAHA CONSTRUCTION | 183.87 | 174.49 | 94.9 | 1
17 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Execution of different works related to BALARAMPUR Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000795/2022-2023 | 1871/CD | 14/03/2023 | 13/04/2023 | SAMBHU BANIK | 79.04 | 79 | 99.95 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Providing FHTC & Balance Laying of P/Line Rd culvert crossing & other allied works at BALARAMPUR ZONE - I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000417/2022-2023 | 1227/CD | 28/11/2022 | 27/01/2023 | SAMBHU BANIK | 45.1 | 43.37 | 96.16 | 1
19 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Execution of different works related to BALARAMPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000172/2023-2024 | 949/CD | 04/09/2023 | 03/12/2023 | GOUTAM KUMAR DAS | 9.12 | 0 | 0 | 78
20 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Execution of different works related to BALARAMPUR Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000791/2022-2023 | 1867/CD | 14/03/2023 | 13/04/2023 | TAPAN CHANDA | 97.76 | 96.32 | 98.53 | 100
21 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Execution of different works related to BALARAMPUR Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000036/2023-2024 | 373/CD | 23/05/2023 | 22/07/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 35.69 | 34.98 | 98.02 | 99
22 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000023/2021-2022 | 961/CD | 05/01/2022 |  | Resource Division | 21.97 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000059/2021-2022 | 1203/CD | 01/02/2022 |  | Resource Division | 2.75 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Supply and delivery of 200 mm dia UPVC pipe(CD) for Balarampur Zone-II 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000520/2021-2022 | 1568/CD | 23/03/2022 | 07/04/2022 | TAPAN CHANDA | 2.98 | 0 | 0 | 1
25 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Construction of 600 cum OHR Providing FHTC & New UPVC Pipe line & other allied works (PART ¿A) at BALARAMPUR ZONE ¿ I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000250/2021-2022 | 899/CD | 24/12/2021 | 20/10/2022 | MATARA CONSTRUCTION CO. | 237.48 | 142.43 | 59.98 | 15
26 | COOCHBEHAR |  | Coochbehar Division | Retrofitting Cum Rejuvenation of existing ground water baed Balarampur piped water supply scheme | SM/10006 | Retrofitting | Providing FHTC & other allied works at BALARAMPUR ZONE - II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000414/2022-2023 | 1225/CD | 28/11/2022 | 27/01/2023 | SEKHAR GHOSAL | 29.37 | 0 | 0 | 60
Total | [13 empty] | 1719 | 1043.74 | 60.72