## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at Different Location of BHOGMARA T/W I & II PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000453/2021-2022 | 1440/CD | 10/03/2022 | 09/04/2022 | MS DD ENTERPRISE | 21.4 | 19.52 | 91.2 | 1
2 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Soil investigation work for the proposed "Overhead reservoir" at Bhogmara PWSS under Mathabhanga Sub-Division, P.H.E. Dte | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000583/2021-2022 | 466/MTB | 04/03/2022 | 19/03/2022 | G. TECH INDIA | 0.57 | 0.51 | 89.05 | 0
3 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 185/CD | 27/04/2023 | 27/04/2023 | Resource Division | 10.62 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | quatation for new service connection bhogmara pwss tw no 1 |  |  | BILL/00714/2023-2024 | BP-562 | 11/10/2023 | 11/10/2023 | WBSEDCL | 2.15 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | quotation for new service connction at bhogmara pwss twno ii |  |  | BILL/00715/2023-2024 | BP-563 | 11/10/2023 | 11/10/2023 | WBSEDCL | 2.84 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | QUOTATION FOR SERVICE CONNTION BHOGMARA PWSS |  |  | BILL/00425/2023-2024 |  | 21/08/2023 | 21/08/2023 | WBSEDCL | 2.21 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Providing FHTC & Construction of pump house, Boundarry wall (2nd t/w site) and laying of Pipe line other allied works at BHOGMARA PWSS under JAL JEEVAN MISSION. (Part-C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000197/2022-2023 | 672/CD | 23/08/2022 | 22/10/2022 | SWAPAN KUMAR ROY | 91.64 | 91.09 | 99.4 | 8
8 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Execution of different works related to BHOGMARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000125/2023-2024 | 668/CD | 14/07/2023 | 11/12/2023 | SWAPAN KUMAR ROY | 98.59 | 98.56 | 99.97 | 64
9 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Bhogmara Water Supply Scheme TW No.- I and,II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001047/2023-2024 | 2698/NMD-II | 15/09/2023 | 15/10/2023 | DEY ENTERPRISE (MALDA) | 21.27 | 20.98 | 98.6 | 100
10 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Execution of different works related to BHOGMARA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000489/2023-2024 | 291/CD | 09/02/2024 | 09/04/2024 | SWAPAN KUMAR ROY | 44.97 | 43.54 | 96.82 | 40
11 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
12 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000075/2025-2026 | 752/CD | 17/05/2025 | 15/08/2025 | SHREE RANI SATI ENTERPRISE | 56.67 | 0 | 0 | 0
13 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Construction of OHR(250 Cum.) including rising main and laying of Distribution system at BHOGMARA PWSS Under Cooch Behar division P.H.E.Dte.(Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000040/2022-2023 | 98/CD | 18/04/2022 | 31/07/2025 | MS DGB ENTERPRISE | 134.91 | 115.37 | 85.51 | 100
14 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | Construction of Boundary wall, Pump house at Head Work site and laying of Pipe line and other allied works at BHOGMARA PWSS Under Cooch Behar division P.H.E.Dte.(Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000003/2022-2023 | 19/CD | 07/04/2022 | 22/03/2025 | SWAPAN KUMAR ROY | 80.93 | 70.9 | 87.61 | 49
15 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Bhogmara Piped Water Supply Scheme. | SM/10007 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000086/2025-2026 | 734/CD | 17/05/2025 | 15/08/2025 | M/S SURAJIT MAJUMDER | 33.76 | 0 | 0 | 30
Total | [13 empty] | 20391.82 | 460.46 | 2.26