## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | Providing FHTC & Construction of Boundary wall, Pump house at Head Work site and laying of Pipe line and other allied works at DUMNIGURI PWSS under JAL JEEVAN MISSION.(Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000198/2022-2023 | 673/CD | 23/08/2022 | 08/02/2025 | SHREE RANI SATI ENTERPRISE | 97.91 | 91.61 | 93.56 | 75
2 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | Providing FHTC & Construction of pump house, Boundary wall (2nd t/w site) and laying of Pipe line other allied works at DUMNIGURI PWSS under JAL JEEVAN MISSION. (Part-C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000201/2022-2023 | 676/CD | 23/08/2022 | 08/02/2025 | SHREE RANI SATI ENTERPRISE | 84.37 | 72.28 | 85.67 | 75
3 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | Providing FHTC laying of Pipe line other allied works at DUMNIGURI PWSS under JAL JEEVAN MISSION. (Part-X) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000203/2022-2023 | 678/CD | 23/08/2022 | 22/10/2022 | SHREE RANI SATI ENTERPRISE | 87.96 | 78.63 | 89.39 | 20
4 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | Construction of OHR(350 Cum.) including rising main and laying of Distribution system at DUMNIGURI PWSS Under Cooch Behar division P.H.E.Dte.(Part-Z) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000405/2022-2023 | 1169/CD | 10/11/2022 | 28/04/2025 | SHREE RANI SATI ENTERPRISE | 246.88 | 128.23 | 51.94 | 70
5 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | Soil investigation work for the proposed "Overhead reservoir" at DUMNIGURI PWSS under Mathabhanga Sub-Division P.H.E Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000581/2021-2022 | 464/MTB | 04/03/2022 | 19/03/2022 | G. TECH INDIA | 0.58 | 0.51 | 86.99 | 0
6 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | Laying of Pipe line and other allied works at DUMNIGURI PWSS under Cooch Behar Division, PHED. (Part-D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000004/2022-2023 | 20/CD | 04/04/2022 | 02/08/2022 | NABIN DEBNATH | 45.53 | 39.05 | 85.77 | 1
7 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at Different Location of DUMNIGURI T/W I & II PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000454/2021-2022 | 1441/CD | 10/03/2022 | 09/04/2022 | MS DD ENTERPRISE | 21.4 | 19.89 | 92.94 | 1
8 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 1373/CD | 22/12/2022 | 22/12/2022 | Resource Division | 85.27 | 0 | 0 | 0
9 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DUMNIGURU water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000009/2023-2024 | 842/NMD-II | 24/04/2023 | 24/05/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 21.73 | 21.53 | 99.11 | 100
10 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 186/CD | 27/04/2023 | 27/04/2023 | Resource Division | 13.17 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | HIRING DISEL BOLERO VEHICLE FOR MTB SUB DIVN.PHED. |  |  | BILL/00631/2022-2023 | BP-752-2022-23 | 06/03/2023 | 06/03/2023 | NABIN DEBNATH | 1.1 | 0 | 0 | 0
12 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | QUOTATION FOR NSC AT DUMNIGURI P/H NO-I |  |  | BILL/01679/2023-2024 | BP-2023-24-302 | 08/09/2023 | 08/09/2023 | WBSEDCL | 5.87 | 0 | 0 | 0
13 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | QUOTATION FOR NSC AT DUMNIGURI P/H NO-II |  |  | BILL/01680/2023-2024 | BP-2023-24-303 | 08/09/2023 | 08/09/2023 | WBSEDCL | 4.72 | 0 | 0 | 0
14 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Augmentation of Dumniguru Piped Water Supply Scheme. | SM/10008 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DAKSHIN BAJEJAMA KHASBAS Dumniguru & BHOGMARA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000585/2024-2025 | 2268/CD | 23/12/2024 | 19/10/2025 | SWAPAN KUMAR ROY | 45.76 | 0 | 0 | 60
Total | [13 empty] | 762.26 | 451.72 | 59.26