## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Hiring of Diesel Vehicle of Mahindra Scorpio Maxi cab for the Office use of Executive Engineer, Cooch Behar Division, PHE Dte. for 12 Months (October 2021 to September 2022) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000166/2021-2022 | 528/CD (1) | 30/09/2021 | 12/10/2021 | SWAPAN KR.SARKAR | 2.02 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Extension order for hiring of diesel vehicle (Bolero) under Executive Engineer, Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000552/2021-2022 | 93/CD | 29/06/2021 | 02/07/2021 | SWAPAN KR.SARKAR | 0.01 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Providing FHTC & New Laying of Pipe Line and other allied works at ANDARAN FULBARI ZONE-I PWSS under Cooch Behar Division, PHED PART - C | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000333/2021-2022 | 1234/CD | 09/02/2022 | 10/05/2022 | GOUTAM KUMAR DAS | 71.63 | 70.61 | 98.57 | 27
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Providing FHTC Construction P. House SSPOST New Laying of Pipe Line and other allied works at ANDARAN FULBARI ZONEI PWSS under Cooch Behar Division, PHED PART - B | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000327/2021-2022 | 1228/CD | 09/02/2022 | 10/05/2022 | BIJOY ROY | 85.75 | 59.86 | 69.81 | 74
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Providing FHTC & New Laying of Pipe Line and other allied works at ANDARAN FULBARI ZONE-II PWSS under Cooch Behar Division, PHED PART - D | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000326/2021-2022 | 1227/CD | 09/02/2022 | 10/05/2022 | BIJOY ROY | 31.15 | 29.68 | 95.27 | 1
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Providing FHTC & New Laying of Pipe Line and other allied works at ANDARAN FULBARI ZONE-I PWSS under Cooch Behar Division, PHED PART - E | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000378/2021-2022 | 1290/CD | 15/02/2022 | 25/01/2026 | ORIENTAL CO OP LABOUR CONTRACT CONSTRUCTION SO | 30.77 | 21.43 | 69.64 | 100
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Providing FHTC & New Laying of Pipe Line and other allied works at ANDARAN FULBARI ZONE-I PWSS under Cooch Behar Division, PHED PART - F | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000334/2021-2022 | 1235/CD | 09/02/2022 | 10/05/2022 | GOUTAM KUMAR DAS | 42.21 | 41.31 | 97.87 | 100
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Construction of 300 cum OHR Providing FHTC New Pipe line & other allied works (PART ¿A) at ANDARAN FULBARI ZONE-II PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000425/2021-2022 | 1475/CD | 10/03/2022 | 20/06/2025 | NABIN DEBNATH | 138.74 | 114.74 | 82.7 | 1
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Construction of 300 cum OHR Providing FHTC New Pipe line & other allied works (PART ¿A) at ANDARAN FULBARI ZONE-I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000426/2021-2022 | 1476/CD | 10/03/2022 | 18/04/2026 | SWAPAN KUMAR ROY | 159.86 | 137.87 | 86.25 | 100
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Augmentation of ANDARAN PHULBARI (Part-A) PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000095/2022-2023 | 303/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 100 | 1
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | New laying of HDPE pipe line, providing FHTC & other allied works at Andaran Fulbari Zone-II (Part-J) under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000266/2022-2023 | 89/TFG | 27/04/2022 | 27/05/2022 | SANJAY MANDAL | 4.65 | 3.51 | 75.4 | 1
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | New laying of HDPE pipe line, providing FHTC & other allied works at Andaran Fulbari Zone-II (Part-H) under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000267/2022-2023 | 87/TFG | 27/04/2022 | 08/09/2025 | SAMBHU BANIK | 4.83 | 4.23 | 87.54 | 100
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Extension work for Hiring of Diesel Vehicle of Bolero Maxi cab for the Office use of Assistant Engineer, Cooch Behar Sadar Sub-Division, PHE Dte. for 04 Months (October 2022 to January 2023) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000269/2022-2023 | 820/CD | 13/09/2022 | 13/01/2023 | PARAUDDIN MIAH | 0.67 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Providing FHTC ,Construction of Pump House ,Boundary Wall at Head Work Site & Laying of Rising Main & Other allied works at ANDARAN FULBARI ZONE- I PWSS PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000226/2022-2023 | 712/CD | 27/08/2022 | 09/11/2025 | SWAPAN KUMAR ROY | 35.45 | 23.12 | 65.22 | 87
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Providing FHTC and Laying of Pipe Line & Other allied work at ANDARAN FULBARI ZONE- II (Part- L) under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000227/2022-2023 | 713/CD | 27/08/2022 | 11/10/2022 | S.G ENTERPRISE | 12.46 | 12.36 | 99.24 | 99
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Providing FHTC and Laying of Pipe Line & Other allied work at ANDARAN FULBARI ZONE- II (Part- K) under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000228/2022-2023 | 714/CD | 27/08/2022 | 20/11/2023 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 14.83 | 11.49 | 77.46 | 1
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Extension of Newly constructed pipe line at ANDARAN FULBARI ZONE II W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000252/2022-2023 | 733/CD | 27/08/2022 | 26/09/2022 | BIJOY ROY | 9.66 | 6.4 | 66.22 | 1
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Hiring of Diesel Vehicle for the Office use of Executive Engineer, Cooch Behar Division, PHE Dte. for 04 Months (October 2022 to January 2023) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000396/2022-2023 | 935/CD | 27/09/2022 | 01/10/2022 | SWAPAN KR.SARKAR | 0.67 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Hiring of Diesel Vehicle for the Office use of Assistant Engineer, (H.Q) under office of the Executive Engineer, Cooch Behar Division, PHE Dte. for 04 Months (October 2022 to January 2023) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000397/2022-2023 | 939/CD | 27/09/2022 | 01/10/2022 | BHAGWATI BHUJEL | 0.67 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | New laying of HDPE pipe line, Providing FHTC & other allied works at Andaran Fulbari Zone-II (Part-G) under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000406/2022-2023 | 86/TFG | 27/04/2022 | 27/05/2022 | CHANDAN KIRTONIA | 2.81 | 2.4 | 85.53 | 1
21 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Repair of Xerox Machine along with supplying accessories as required of the office of Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000271/2022-2023 | 863/CD | 20/09/2022 | 23/09/2022 | ELECTRO SERVICES PVT.LTD | 0.28 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Execution of different works related to A.FULBARI Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000435/2022-2023 | 1411/CD | 29/12/2022 | 28/01/2023 | PRAPTI DUTTA | 9.57 | 9.57 | 100 | 0
23 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Hiring of Diesel Vehicle for the Office use of Assistant Engineer, Mathabhanga Sub-Division, PHE Dte. for 04 Months (October 2022 to January 2023) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000399/2022-2023 | 955/CD | 28/09/2022 | 28/01/2023 | NABIN DEBNATH | 0.67 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Supply of (One) Maxi Cab (Non air-condition) on hire basis including driver for Assistant Engineer, Survey Sub-Division-II, PHE Dte. Siliguri, PHE Dte. (with valid Taxi permit) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000284/2022-2023 | 606/CD | 10/08/2022 | 10/10/2022 | PARAKRAM BOSE | 0.29 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Supply of (One) Maxi Cap (Non air-condition) on hire basic including driver for Assistant Engineer, Jalpaiguri S.I. Sub-Division, PHE Dte.(with valid Taxi parmit) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000283/2022-2023 | 603/CD | 08/08/2022 | 08/10/2022 | SUKANTA BISWAS | 0.29 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | New laying of HDPE pipe line, Providing FHTC & other allied works at Andaran Fulbari Zone-II (Part-I) under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000428/2022-2023 | 88/TFG | 27/04/2022 | 27/05/2022 | GOUTAM KUMAR DAS | 4.69 | 2.84 | 60.45 | 1
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Execution of different works related to Aug. of ANDARAN FULBARI under JAL JEEVAN MISSION . | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000411/2022-2023 | 1222/CD | 28/11/2022 | 27/01/2023 | GOUTAM KUMAR DAS | 42.44 | 38 | 89.54 | 30
28 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Augmentation of ANDARAN PHULBARI (Part-B) PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000096/2022-2023 | 304/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.23 | 4.23 | 100 | 1
29 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Providing FHTC & New Laying of Pipe Line and other allied works at ANDARAN FULBARI ZONE-II PWSS under Cooch Behar Division, PHED PART - C | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000355/2021-2022 | 1260/CD | 09/02/2022 | 14/05/2025 | UTPAL CHAKRABORTY | 55.1 | 36.04 | 65.4 | 100
30 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Augmentation of ANDARAN PHULBARI (Part-C) PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000097/2022-2023 | 305/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 2.23 | 2.23 | 100 | 1
31 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Providing FHTC & New Laying of Pipe Line and other allied works at ANDARAN FULBARI ZONE-I PWSS under Cooch Behar Division, PHED PART - D | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000377/2021-2022 | 1289/CD | 15/02/2022 | 05/05/2024 | KHOKAN DAS | 39.06 | 28.47 | 72.88 | 100
32 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Construction P.House HWS & B/Wall & Laying of Rising main & delivery main New Pipe line & other allied works (PART ¿X) at ANDARAN FULBARI ZONE-II PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000380/2021-2022 | 1292/CD | 15/02/2022 | 16/05/2022 | NABIN DEBNATH | 22.62 | 21.27 | 94.05 | 1
33 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Construction P.House 2nd Site & B/Wall & Providing FHTC New Pipe line & other allied works (PART ¿B) at ANDARAN FULBARI ZONE-II PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000356/2021-2022 | 1261/CD | 09/02/2022 | 22/08/2025 | UTPAL CHAKRABORTY | 67.98 | 47.65 | 70.09 | 100
34 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at Different Location of ANDARAN FULBARI ZONE I & II PWSS under Cooch Behar Division PHE Dte | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000507/2021-2022 | 1455/CD | 10/03/2022 | 09/04/2022 | AUXILIARY TUBEWELL DRILLERS | 42.8 | 42.42 | 99.09 | 1
35 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 1342/CD | 19/12/2022 | 19/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
36 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | NABL |  |  | VCH/001647/2021-2022 | BP-2021_22_471 | 23/03/2022 | 23/03/2022 | QUALITY COOUNCIL OF INDIA NABL | 0.28 | 0 | 0 | 0
37 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | FHTC |  |  | VCH/001635/2021-2022 | BP_2021_22_461 | 16/03/2022 | 16/03/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 5.01 | 0 | 0 | 0
38 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | FHTC |  |  | VCH/001633/2021-2022 | BP_2021_22_458 | 16/03/2022 | 16/03/2022 | MS DD ENTERPRISE | 8.33 | 0 | 0 | 0
39 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | FUEL BILL |  |  | VCH/000343/2022-2023 |  | 03/08/2022 | 03/08/2022 | R.C.BANIK & SONS | 0.8 | 0 | 0 | 0
40 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | FHTC |  |  | VCH/000385/2022-2023 | BP-22-23-117 | 02/07/2022 | 02/07/2022 | GOUTAM KUMAR DAS | 0.04 | 0 | 0 | 0
41 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | FHTC |  |  | VCH/001632/2021-2022 | BP_2021_22_457 | 16/03/2022 | 16/03/2022 | KHOKAN DAS | 11.86 | 0 | 0 | 0
42 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | SOIL INVESTIGATION AT ANDARAN FULBARI |  |  | VCH/000194/2022-2023 | BP_102_22_23 | 21/06/2022 | 21/06/2022 | G MITRA & ASSOCIATES | 2.15 | 0 | 0 | 0
43 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Execution of different works related to A.FULBARI Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000525/2022-2023 | 1634/CD | 09/02/2023 | 11/03/2023 | MONORAMA ENTERPRISE | 9.57 | 9.57 | 100 | 100
44 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Execution of different works related to A. FULBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000752/2022-2023 | 1833/CD | 09/03/2023 | 08/04/2023 | GOUTAM KUMAR DAS | 75.14 | 73.89 | 98.34 | 100
45 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Execution of different works related to ANDARAN FULBARI PWSS under JAL JEEVAN MISSION PART X (P1) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000015/2023-2024 | 392/CD | 23/05/2023 | 04/09/2026 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 29.64 | 28.21 | 95.18 | 96
46 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Execution of different works related to ANDARAN FULBARI PWSS under JAL JEEVAN MISSION PART X (P2) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000016/2023-2024 | 393/CD | 23/05/2023 | 22/06/2023 | UTTAM SAHA | 29.64 | 28.31 | 95.49 | 100
47 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Execution of different works related to ANDARAN FULBARI PWSS under JAL JEEVAN MISSION PART Z (P1) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000019/2023-2024 | 389/CD | 23/05/2023 | 22/05/2025 | KANAILAL GOPE | 25.11 | 10.47 | 41.68 | 100
48 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000829/2022-2023 | 2049/CD | 31/03/2023 | 31/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 0
49 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Execution of different works related to A.FULBARI PWSS under JAL JEEVAN MISSION Z2 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000129/2023-2024 | 670/CD | 14/07/2023 | 12/09/2023 | NABIN DEBNATH | 23.5 | 0 | 0 | 0
50 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Execution of different works related to A.FULBARI PWSS under JAL JEEVAN MISSION Z1 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000131/2023-2024 | 672/CD | 14/07/2023 | 12/09/2023 | SWAPAN KUMAR ROY | 10.82 | 6.79 | 62.73 | 63
51 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Execution of different works related to A.FULBARI PWSS under JAL JEEVAN MISSION ZI | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000123/2023-2024 | 642/CD | 12/07/2023 | 09/12/2023 | GOUTAM KUMAR DAS | 39.17 | 17.23 | 43.99 | 100
52 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Andaran Fulbari water supply scheme, TW no II of Zone-I under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000802/2022-2023 | .378/NMD-II | 22/02/2023 | 24/03/2023 | KASHI NATH DEY | 11.4 | 11.3 | 99.07 | 100
53 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Andaran Fulbari water supply scheme, TW no II of Zone-II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000803/2022-2023 | 381/NMD-II | 22/02/2023 | 13/11/2024 | M/S PARITOSH BHOWMICK & CO. | 11.43 | 11.3 | 98.89 | 100
54 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Andaran Fulbari water supply scheme, TW no I(H/W Site) of Zone-I under Northern Mechanical Division-II, PHE | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000836/2022-2023 | 547/NMD-II | 16/03/2023 | 15/04/2023 | M/S MATRI CONSTRUCTION | 11.43 | 11.31 | 98.97 | 100
55 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Andaran Fulbari water supply scheme, TW no I (H/W Site) of Zone-II under Northern Mechanical Division. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000837/2022-2023 | 551/NMD-II | 16/03/2023 | 30/09/2024 | M/S UTPAL CHAKRABORTY & CO. | 11.42 | 10.91 | 95.52 | 100
56 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | EXC. OF DIFFERENT WORK AT ANGERKATA PARADUBI PWS |  |  | BILL/00554/2023-2024 | BP-183 | 01/06/2023 | 01/06/2023 | M/S SOBHA & CO. | 3.15 | 0 | 0 | 0
57 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Quotation for new service connection at andaranfulbari TW No I,Z-II |  |  | BILL/00453/2022-2023 | BP-144/22-23 | 23/02/2023 | 23/02/2023 | WBSEDCL | 0.85 | 0 | 0 | 0
58 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | EXECUTION OF DIFFERENT WORKS AT ANDARAN FULBARI PWSS |  |  | BILL/01087/2023-2024 | BP-634 | 16/10/2023 | 16/10/2023 | PARITOSH DATTA | 14 | 0 | 0 | 0
59 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Quotation for new service connection at andaranfulbari TW No I,z-i (H/W Site) |  |  | BILL/00452/2022-2023 | BP-147/22-23 | 23/02/2023 | 23/02/2023 | WBSEDCL | 0.85 | 0 | 0 | 0
60 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Quotation for new service connection at andaranfulbari TW No I, Z-II |  |  | BILL/00454/2022-2023 | BP-145/22-23 | 23/02/2023 | 23/02/2023 | WBSEDCL | 1.13 | 0 | 0 | 0
61 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | Quotation for new service connection at andaranfulbari TW No II, Z-II |  |  | BILL/00455/2022-2023 | BP-146/22-23 | 23/02/2023 | 23/02/2023 | WBSEDCL | 0.85 | 0 | 0 | 0
62 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF ANDARAN PHULBARI PIPED WATER SUPPLY SCHEME | SM/10049 | Augmentation | EXECUTION OF DIFFERENT WORK AT BARA MADHUSUDAN PWSS |  |  | BILL/02052/2023-2024 | BP-1123 | 02/03/2024 | 02/03/2024 | BRAJA GOPAL SAHA | 5.3 | 0 | 0 | 0
Total | [13 empty] | 1351.54 | 996.96 | 73.76