## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Extension of Hiring of Bolero (Diesel) No-WB/63A/0081 for the use of Assistant Engineer, Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000279/2020-2021 | 170/MTB | 28/09/2020 | 28/01/2021 | NABIN DEBNATH | 0.4 | 0.4 | 100 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Hiring of diesel vehicle of Bolero Maxi cap under the office of the Assistant Engineer, Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000278/2020-2021 | 332/MTB | 29/01/2021 | 04/02/2021 | NABIN DEBNATH | 0.29 | 0.29 | 100 | 100
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Hiring of Diesel Vehicle of Bolero Maxi cab for the Office use of Assistant Engineer, RWS Cooch Behar Sub-Division, PHE Dte. for 12 Months (October 2021 to September 2022) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000169/2021-2022 | 528/CD (4) | 30/09/2021 | 12/10/2021 | AJAD HOSSAIN | 2.02 | 0.18 | 8.81 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Providing FHTC, New Laying of HDPE Pipe Line & Other allied work related to pipe line at BOXIRHAT ZONE - II (Part- B) PWSS under Tufanganj Sub- Division, P.H.E Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000417/2021-2022 | 1514/CD | 15/03/2022 | 13/06/2022 | MS BIDYUT SARKAR | 228.08 | 228.08 | 100 | 1
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Providing FHTC Reconstruction of B/W PH 2nd site Footpath HWS related to P/Line BOXIRHAT ZONE ¿ II PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000017/2022-2023 | 33/CD | 07/04/2022 | 22/05/2022 | BIJOY ROY | 20.29 | 19.6 | 96.61 | 1
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Providing FHTC, New Laying of HDPE Pipe Line & Other allied work related to pipe line at BOXIRHAT ZONE - I (Part- A) PWSS under Tufanganj Sub- Division, P.H.E Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000416/2021-2022 | 1513/CD | 15/03/2022 | 13/06/2022 | MS BIDYUT SARKAR | 293.49 | 293.43 | 99.98 | 1
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000471/2021-2022 | 1159/CD | 31/01/2022 | 03/02/2022 | PRIYANKA MANDAL | 2.46 | 2.46 | 100 | 1
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Providing FHTC, 2(Two) Nos. Pump House, B/Wall, Footpath, Rising Main & Delivery line & other allied works related delivery line at BAKSIRHAT Zone-I & Zone-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000200/2022-2023 | 675/CD | 23/08/2022 | 22/10/2022 | NABIN DEBNATH | 58.02 | 53.12 | 91.56 | 1
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-B) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000211/2022-2023 | 534/CD | 19/07/2022 | 19/01/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Providing FHTC, New Laying of HDPE Pipe Line & Other allied work related to balance work of pipe line at BOXIRHAT ZONE ¿ I & II PWSS under Tufanganj SubDivision, P.H.E Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000121/2022-2023 | 442/CD | 29/06/2022 | 27/10/2022 | MS BIDYUT SARKAR | 321.62 | 321.28 | 99.9 | 1
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Providing FHTC & other allied works at BOXIRHAT ZII PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000373/2022-2023 | 1026/CD | 29/09/2022 | 29/10/2022 | BIJOY ROY | 9.98 | 9.98 | 100.02 | 1
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Providing FHTC & other allied works at BOXIRHAT ZONE ? I & II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000415/2022-2023 | 1220/CD | 28/11/2022 | 27/01/2023 | UTPAL CHAKRABORTY | 99.84 | 98.57 | 98.72 | 1
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-A) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000214/2022-2023 | 556/CD | 27/07/2022 | 27/01/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Augmentation of Baksirhat PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000087/2022-2023 | 295/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 100 | 1
15 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Supply, delivery, installation, commissioning of submersible pumping machinery including other related accessories of Boxirhat Water Supply Scheme TW No.-I (Replacement) under NMD-II,PHE.Dte,CoochBehar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000862/2021-2022 | 188/ NMD-II | 23/02/2022 | 25/03/2022 | MUSTAFI CONCERN | 2.55 | 2.55 | 100 | 0
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Providing FHTC & Construction of Latrine foothpath drain & Boundary Wall at HWS & 2nd Site of BOXIRHAT (ZONE-II) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000237/2022-2023 | 723/CD | 27/08/2022 | 11/10/2022 | BIJOY ROY | 12.17 | 12.13 | 99.74 | 1
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Providing FHTC & other allied works at BOXIRHAT ZII PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000374/2022-2023 | 1027/CD | 29/09/2022 | 29/10/2022 | NABIN DEBNATH | 10.05 | 9.91 | 98.59 | 1
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Providing FHTC, new rising main connection, earth filling & other allied works at Boxirhat Zone-II pwss under Tufanganj Sub-Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000277/2022-2023 | 210/TFG | 05/07/2022 | 04/08/2022 | BIJOY ROY | 4.03 | 3.96 | 98.1 | 1
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at Different Location of BOXIRHAT ZONE I & II PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000508/2021-2022 | 1456/CD | 10/03/2022 | 09/04/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 21.4 | 16.91 | 79.02 | 1
20 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Quotation for new service connection at Boxirhat PWSS,Z-II TW No-III ,Application no. 4003014792 |  |  | VCH/001455/2022-2023 |  | 18/11/2022 | 18/11/2022 | WBSEDCL | 1.06 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | FHTC |  |  | VCH/001614/2021-2022 | BP_2021_22_438 | 11/03/2022 | 11/03/2022 | DAS ENTERPRISE | 34.38 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | HIRING VEHICLE |  |  | VCH/000728/2022-2023 | 265 | 30/09/2022 | 30/09/2022 | SWAPAN KR.SARKAR | 1.41 | 0 | 0 | 0
23 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Quotation for new service connection at Boxirhat PWSS,Z-I TW No-III ,Application no. 4003014797 |  |  | VCH/001456/2022-2023 |  | 18/11/2022 | 18/11/2022 | WBSEDCL | 1.06 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | PIPE |  |  | VCH/001701/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 2.36 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | VEHICLE BILL |  |  | VCH/000802/2022-2023 | 296 | 30/09/2022 | 30/09/2022 | NIRANJAN KIRTANIA | 0.29 | 0 | 0 | 0
26 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Quotation for new service connection at BAKSIRHAT Z-II,T/W no. III, Application no. 4003014797 |  |  | VCH/001466/2022-2023 | BP-89/22-23 | 22/11/2022 | 22/11/2022 | WBSEDCL | 1.06 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | FUEL BILL |  |  | VCH/000345/2022-2023 |  | 04/08/2022 | 04/08/2022 | R.C.BANIK & SONS | 0.85 | 0 | 0 | 0
28 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Quotation for new service connection at BAKSIRHAT Z-I,T/W no. III, Application no. 4003014797 |  |  | VCH/001465/2022-2023 | BP-88/22-23 | 22/11/2022 | 22/11/2022 | WBSEDCL | 1.06 | 0 | 0 | 0
29 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Execution of different works related to BOXIRHAT PWSS under JAL JEEVAN MISSION PART M 2 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000176/2023-2024 | 953/CD | 04/09/2023 | 22/11/2025 | PARITOSH DATTA | 45.38 | 26.99 | 59.46 | 75
30 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Execution of different works related to BOXIRHAT PWSS under JAL JEEVAN MISSION PART M 1 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000175/2023-2024 | 952/CD | 04/09/2023 | 22/11/2025 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 45.38 | 32.6 | 71.84 | 99
31 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Execution of different works related to BOXIRHAT PWSS under JAL JEEVAN MISSION PART N | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000178/2023-2024 | 955/CD | 04/09/2023 | 24/08/2025 | GOPAL CH.GHOSH | 46.65 | 26.14 | 56.03 | 90
32 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Name of Work: Execution of different works related to BOXIRHAT PWSS under JAL JEEVAN MISSION PART O | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000262/2023-2024 | 1028/CD | 22/09/2023 | 21/11/2023 | KRISHNA GOPAL BASK | 42.64 | 25.97 | 60.89 | 70
33 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Name of Work: Execution of different works related to BOXIRHAT PWSS under JAL JEEVAN MISSION PART O | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000263/2023-2024 | 1030/CD | 22/09/2023 | 10/11/2025 | RED STAR UNEMPLOYED CO -OPARATIVE LABOUR CON.CONS. SOCY LTD. | 42.64 | 18.37 | 43.07 | 60
34 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Supply, installation, commissioning and trial operation ofelectro-mechanical components along with copper wound linevoltage corrector for Augmentation of BOXIRHAT AREA PWSS,ZONE-II TW no III inthe district of COOCHBEHAR under Northern MechanicalDivision-II, PHE Dte ALIPURDUAR. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 1, Northern Mechanical Division-II,PHE ,Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000730/2022-2023 | 60/NMD-II | 09/01/2023 | 01/11/2024 | SUDIP DUTTA | 10.74 | 10.61 | 98.8 | 100
35 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Execution of different works related to BOXIRHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000792/2022-2023 | 1868/CD | 14/03/2023 | 13/04/2023 | BIJOY ROY | 26.32 | 14.96 | 56.83 | 1
36 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Execution of different works related to BOXIRHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000750/2022-2023 | 1700/CD | 13/02/2023 | 15/03/2023 | MS BIDYUT SARKAR | 25.25 | 25.03 | 99.16 | 99
37 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-D) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000874/2022-2023 | 1980/CD | 27/03/2023 | 11/05/2023 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
38 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-F) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000877/2022-2023 | 2004/CD | 30/03/2023 | 14/05/2023 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
39 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-A) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000872/2022-2023 | 1896/CD | 16/03/2023 | 30/04/2023 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
40 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-E) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000875/2022-2023 | 1983/CD | 27/03/2023 | 11/05/2023 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
41 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-B) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000876/2022-2023 | 1916/CD | 22/03/2023 | 06/05/2023 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
42 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-C) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000873/2022-2023 | 1950/CD | 23/03/2023 | 07/05/2023 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
43 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BOXIRHAT AREA PWSS,ZONE-I TW no III in the district of COOCHBEHAR under Northern Mechanical Division-II, PHE Dte ALIPURDUAR. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000718/2022-2023 | 09/NMD-II | 02/01/2023 | 30/11/2024 | GEETA CONSTRUCTION | 10.75 | 10.28 | 95.62 | 100
44 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | xecution of different works related to BOXIRHAT PWSS under JAL JEEVAN MISSION PART N 1 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000177/2023-2024 | 954/CD | 04/09/2023 | 03/12/2023 | SAMBHU BANIK | 46.65 | 32.34 | 69.32 | 99
45 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Execution of different works related to BOXIRHATZ I&II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000366/2023-2024 | 1385/CD | 05/12/2023 | 03/02/2024 | NABIN DEBNATH | 8.62 | 4.67 | 54.24 | 90
46 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Execution of different works related to BOXIRHAT Z II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000332/2023-2024 | 1318/CD | 24/11/2023 | 23/03/2024 | BIJOY ROY | 15.07 | 14.15 | 93.93 | 95
47 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000398/2023-2024 | 1288/CD | 21/11/2023 | 05/01/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
48 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-B) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000399/2023-2024 | 1355/CD | 29/11/2023 | 13/01/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
49 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-C) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000400/2023-2024 | 1409/CD | 05/12/2023 | 19/01/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
50 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 208/CD | 27/04/2023 | 27/04/2023 | Resource Division | 49.95 | 0 | 0 | 0
51 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO BOXIRHAT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000571/2024-2025 | 2255/CD | 23/12/2024 | 21/02/2025 | MA MAHAMAYA UNP. CO-OP LABOUR CONT & CONT SOCITY LTD. | 14.75 | 0 | 0 | 50
52 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | FABRICATION AND INSTALLATION OF LAND POSSESSION SIGN BOARD AT EVERY LANDS OF DIFFERENT PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-A) |  |  | ORD/000622/2024-2025 | 2324/CD | 23/12/2024 | 21/02/2025 | LIMRA SOCIAL WELFARE SOCIETY | 44.49 | 0 | 0 | 0
53 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO BOXIRHAT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000517/2024-2025 | 2294/CD | 23/12/2024 | 21/06/2025 | UTTAM SAHA | 15.55 | 2.51 | 16.13 | 70
54 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within BAKSIRHAT area) SALBARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000604/2024-2025 | 2305/CD | 23/12/2024 | 19/10/2025 | AASHIRBAD ENTERPRISE | 17.54 | 0 | 0 | 70
55 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within BALABHUT area) BOXIRHAT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000628/2024-2025 | 2235/CD | 23/12/2024 | 21/02/2025 | RAJIB CHAKRABORTY | 6.96 | 0 | 0 | 25
56 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 1542/CD | 16/08/2024 | 16/08/2024 | Resource Division | 52.88 | 0 | 0 | 0
57 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME,TW No.- II and III OF Zone-I,TW NO-II OF Zone-II under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/000088/2025-2026 | 1230/NMD-II | 29/05/2025 | 28/06/2025 | ALPHA ENTERPRISE | 34.43 | 0 | 0 | 0
58 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000068/2025-2026 | 753/CD | 17/05/2025 | 15/08/2025 | ANIMESH DHAR CHOUDHURY | 53.67 | 0 | 0 | 0
59 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000078/2025-2026 | 798/CD | 17/05/2025 | 12/05/2026 | CHAKRABORTY ENTERPRISE | 72.16 | 0 | 0 | 30
60 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000094/2025-2026 | 735/CD | 17/05/2025 | 15/08/2025 | GHOSH AND SAHA CONSTRUCTION | 46.77 | 0 | 0 | 0
61 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000067/2025-2026 | 728/CD | 17/05/2025 | 15/02/2026 | M/S B PAUL AND COMPANY | 59.95 | 0 | 0 | 30
62 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000282/2025-2026 | 791/CD | 23/05/2025 | 17/02/2026 | UDAY CHAKI | 61.52 | 0 | 0 | 30
63 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000291/2025-2026 | 800/CD | 23/05/2025 | 21/08/2025 | MATARA CONSTRUCTION CO. | 34.83 | 0 | 0 | 0
64 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BAKSIRHAT PIPED WATER SUPPLY SCHEME | SM/10050 | Augmentation | Charges for new service connection at Aug of Baxirhat PWSS, P/H-IV under Coochbehar Dist. |  |  | BILL/00432/2025-2026 |  | 20/05/2025 | 20/05/2025 | WBSEDCL | 5.74 | 0 | 0 | 0
Total | [13 empty] | 2083.12 | 1331.18 | 63.9