## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Laying DI Pipe for Bridge crossing in node 147A 157A & 150 to 151A of MADHYA HUDUMDANGA PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000088/2021-2022 | 212/CD | 26/07/2021 | 24/10/2021 | DAS ENTERPRISE | 7.31 | 7.2 | 98.45 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Providing House connection for MADHYA HUDUMDANGA PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000351/2021-2022 | 1252/CD | 09/02/2022 | 11/03/2022 | DAS ENTERPRISE | 8.77 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Providing functional house hold tap connection (unmetered) 97 nos. in different School and AWC under different Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000446/2021-2022 | 451/MTB | 04/03/2022 | 19/03/2022 | UDAY CHAKI | 5.04 | 4.81 | 95.55 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Providing functional house hold tap connection within command area of Madhya Hudumdanga Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme.Part-B | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000145/2022-2023 | 220/MTB | 27/07/2022 | 11/08/2022 | UDAY CHAKI | 4.82 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Providing functional house hold tap connection within command area of Madhya Hudumdanga Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000144/2022-2023 | 219/MTB | 26/07/2022 | 10/08/2022 | DAS ENTERPRISE | 4.81 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Providing FHTC & laying of Pipe line and other allied works at Madhya Hudumdanga PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000196/2022-2023 | 666/CD | 23/08/2022 | 22/10/2022 | DAS ENTERPRISE | 23.84 | 15.33 | 64.33 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Providing FHTC and laying of UPVC Pipe line Madhyahudum Danga PWSS under JJM Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000286/2022-2023 | 971/CD | 29/09/2022 | 29/10/2022 | UDAY CHAKI | 4.56 | 4.56 | 100 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Providing FHTC & Laying of Pipe line Repairing of Boundary wall, Pumphouse & other allied works at MADHYA HUDUMDANGA PWSS Under Cooch Behar division P.H.E.Dte. (Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000404/2022-2023 | 1168/CD | 10/11/2022 | 01/06/2025 | M/S KAMAK ENGINEERS AND CO | 148.81 | 133.42 | 89.66 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Providing FHTC & Laying of Pipe line Construction of Boundary wall, Pumphouse Sinking Big T/well at 3RD site & other allied works at MADHYA HUDUMDANGA PWSS Under Cooch Behar division P.H.E.Dte. (Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000403/2022-2023 | 1167/CD | 10/11/2022 | 01/06/2025 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 148.26 | 95.61 | 64.49 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Laying 140 mm dia upve pipeline and 150 mm dia dI pipe line from head work Site to Baro bari under Madhaya Hudumdanga Water Supply scheme under JJM programmee under Mathabhanga Sub -Divn PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000354/2022-2023 | 1007/CD | 29/09/2022 | 29/10/2022 | UDAY CHAKI | 12.81 | 12.06 | 94.14 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | FHTC AT MADHYA HUDUMDANGA |  |  | VCH/000740/2022-2023 | 239 | 02/09/2022 | 02/09/2022 | DAS ENTERPRISE | 4.8 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | COST OF PIPE |  |  | VCH/001695/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 7.25 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | FHTC |  |  | VCH/001692/2021-2022 | BP_2021_22_508 | 31/03/2022 | 31/03/2022 | M/S BADAL CH SAHA | 4.78 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | FHTC |  |  | VCH/001691/2021-2022 | BP_2021_22_507 | 31/03/2022 | 31/03/2022 | M/S. MANDAL CONSTRUCTION | 17.97 | 0 | 0 | 0
15 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Madhya Hudumdanga water supply scheme, TW no. III under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000654/2023-2024 | 1940/NMD-II | 24/07/2023 | 23/08/2023 | SUDIP DUTTA | 10.63 | 10.52 | 98.96 | 100
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 201/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.25 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | FHTC AT PWSS |  |  | BILL/00660/2022-2023 | BP-583-22-23-P1 | 10/01/2023 | 10/01/2023 | GOPAL CH.GHOSH | 3 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | FHTC AT PWSS |  |  | BILL/00664/2022-2023 | BP-653-22-23-P | 23/01/2023 | 23/01/2023 | SAMBHU BANIK | 2.74 | 0 | 0 | 0
19 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT MADHYA HUDUMDANGA TW NO-III |  |  | BILL/00085/2023-2024 | BP-2023-24-81 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO MADHYA HUDUMDANGA HEMKUMARI ZONE-II & NIJTARAF PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000537/2024-2025 | 2221/CD | 23/12/2024 | 21/02/2025 | TORSHA CONSTRUCTION | 69.04 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing Functional House hold Tap Connection Within the Command Area of MADHYA HUDUMDANGA Piped Water Supply Scheme | SM/10141 | Augmentation | FABRICATION AND INSTALLATION OF LAND POSSESSION SB AT EVERY LANDS OF DIFFERENT (MADHYA HUDUMDANGA) PWSS WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, PHE Dte. UNDER JJM (PART-B) | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000507/2024-2025 | 1792/CD | 30/09/2024 | 10/10/2024 | REJAUL HAQUE | 20.49 | 4.46 | 21.75 | 85
Total | [13 empty] | 20316.32 | 287.97 | 1.42