## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing house hold tap connection of drinking water to the household of command area under BARO KAIMARI WATER SUPPLY SCHEME under Mathabhanga Sub-Division, P.H.E.Dte. Under JALSWAPNA PRAKALPA. |  |  | ORD/000065/2021-2022 | 112/MTB | 09/08/2021 | 24/08/2021 | SUBODH ROY & SONS | 5.05 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing FHTC Construction P. House Sinking Big Dia Tubewll New Laying of Pipe Line and other allied works at AUG. PAYAMARI PWSS under Cooch Behar Division, PHED PART - B | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000038/2022-2023 | 96/CD | 18/04/2022 | 16/08/2022 | M/S S.DAS AND ENTERPRISE | 118.61 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing FHTC & other allied works at BARO KAIMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000152/2022-2023 | 563/CD | 29/07/2022 | 27/09/2022 | SANJAY MANDAL | 20.71 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing FHTC & other allied works at BARO KAIMARI PWSS under JAL JEEVAN MISSION PART Z | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000153/2022-2023 | 564/CD | 29/07/2022 | 27/09/2022 | NABIN DEBNATH | 20.74 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing functional house hold tap connection (unmetered) 120 nos. in BARA KAIMARI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. |  |  | ORD/000176/2021-2022 | 178/MTB | 06/09/2021 | 21/09/2021 | SUBODH ROY & SONS | 5.06 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing FHTC, laying of Pipe line and other allied works at BARO KAIMARI PWSS under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000073/2022-2023 | 270/CD | 24/05/2022 | 08/07/2022 | SUBODH ROY & SONS | 16.54 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 1375/CD | 22/12/2022 | 22/12/2022 | Resource Division | 97.09 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | COST OF PIPE |  |  | VCH/001694/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 34.78 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | SUPPLY OF UPVC SINGIMARI BHETAGURI |  |  | VCH/000425/2022-2023 | BP-22-23-161 | 30/07/2022 | 30/07/2022 | SWAPAN KUMAR ROY | 2.95 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | FHTC BARA KAIMARI |  |  | VCH/000419/2022-2023 | BP-22-23-153 | 26/07/2022 | 26/07/2022 | NABIN DEBNATH | 103.88 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | FHTC BARA KAIMARI |  |  | VCH/000395/2022-2023 | BP-22-23-128 | 11/07/2022 | 11/07/2022 | M/S. NITYAGOPAL BANIK | 102.54 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Sinking of Big Dia Tubewell at Baro Kaimari PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000181/2022-2023 | 655/CD | 23/08/2022 | 22/10/2022 | MS DD ENTERPRISE | 11.68 | 0 | 0 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Laying of pipe line and other allied work related to pipe line at Bara Kaimari PWSS under Mathabhanga Sub-Division, PHE Dte. JJM Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000448/2022-2023 | 221/MTB | 26/07/2022 | 25/08/2022 | SUBODH ROY & SONS | 4.87 | 0 | 0 | 1
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 363/CD | 15/06/2022 | 15/06/2022 | Resource Division | 1.4 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 67/CD | 12/04/2022 | 12/04/2022 | Resource Division | 8.79 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | FHTC AT SOULMARI PWSS |  |  | VCH/000566/2022-2023 | 166 | 10/08/2022 | 10/08/2022 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 20.73 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | BARA SOULMARI |  |  | VCH/001068/2022-2023 | 167 | 10/08/2022 | 10/08/2022 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 0.13 | 0 | 0 | 0
18 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BARA KAIMARI (AUG) TW NO- III |  |  | BILL/00024/2023-2024 | BP-2023-24-13 | 27/04/2023 | 27/04/2023 | WBSEDCL | 1.34 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing functional house hold tap connection within command area under BARA KAIMARI Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000117/2022-2023 | 131/MTB | 23/06/2022 | 08/07/2022 | SUBODH ROY & SONS | 4.77 | 0 | 0 | 100
20 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Augumentation of BARA KAIMARI water supply scheme, TW no I of Zone-I under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001033/2023-2024 | 2665/NMD-II | 04/09/2023 | 04/10/2023 | M/S ANJALI ENTERPRISE | 10.71 | 0 | 0 | 100
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing FHTC, Repairing of Boundary wall, Pump house & Blower room, and laying of Pipe line and other allied works in-connection with augmentation of BARA KAIMARI PWSS under Cooch Behar Division, PHED.(Part-C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000035/2022-2023 | 92/CD | 18/04/2022 | 16/08/2022 | BRISTI CONSTRUCTION | 117.32 | 0 | 0 | 100
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation of BARA KAIMARI Piped Water Supply Scheme | SM/10142 | Augmentation | Providing functional house hold tap connection within command area of Mahishmuri Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme.Part-E | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000101/2022-2023 | 47/MTB | 02/05/2022 | 16/06/2022 | NABIN DEBNATH | 4.96 | 0 | 0 | 100
Total | [13 empty] | 714.65 | 0 | 0