## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Sinking of Big Dia Tubewell at 3RD Site of SITAI ZONE - I PWSS under JAL JEEVAN MISSION | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000245/2022-2023 | 729/CD | 27/08/2022 | 11/10/2022 | UTTAM SAHA | 11.68 | 11.56 | 98.98 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Soil investigation work for proposed OHR of Sitai Zone-I & II PWSS under Cooch Behar Division, PHE Dte. | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000553/2021-2022 | 496/SD | 25/01/2022 | 14/02/2022 | MOYTEC | 2.15 | 2.15 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | FHTC |  |  | VCH/001653/2021-2022 | BP-2021_22_498 | 31/03/2022 | 31/03/2022 | MS BIDYUT SARKAR | 80 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at SITAI Z- II PWSS under JAL JEEVAN MISSION PART D | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000394/2022-2023 | 1107/CD | 21/10/2022 | 20/11/2022 | DAFFODIL | 71.26 | 70.87 | 99.46 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at SITAI Z- II PWSS under JAL JEEVAN MISSION PART C | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000393/2022-2023 | 1106/CD | 21/10/2022 | 20/11/2022 | MESSRS A.B.G CONSTRUCTION | 68.34 | 36.46 | 53.35 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2021-2022 | 1360/CD | 24/02/2022 | 24/02/2022 | Resource Division | 10.98 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 492/CD | 07/07/2022 | 07/07/2022 | Resource Division | 30.8 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 1952/CD | 24/03/2023 | 24/03/2023 | Resource Division | 48.12 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 141/CD | 27/04/2023 | 27/04/2023 | Resource Division | 60.86 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT SITAI PWSS PH NO-III,Z-I |  |  | BILL/00075/2023-2024 | BP-2023-24-74 | 15/05/2023 | 15/05/2023 | WBSEDCL | 0.85 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | EXC. OF DIFF. WORK AT MAHARHAT BANDAR PWSS |  |  | BILL/00543/2023-2024 | BP-01 | 12/04/2023 | 12/04/2023 | GHOSH AND SAHA CONSTRUCTION | 160 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT SITAI PWSS PH NO-III,Z-II (AUG) |  |  | BILL/00078/2023-2024 | BP-2023-24-71 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.09 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | EXC. OF DIFF. WORKS AT SITALKUCHI PWSS |  |  | BILL/00550/2023-2024 | BP-04 | 12/04/2023 | 12/04/2023 | RAJAT ROY | 7.9 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI/GI Pipe line and other allied works (PART ¿B) at SITAI ZONE ¿ I I PWSS under Cooch Behar Division, PHED | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000466/2021-2022 | 1604/CD | 24/03/2022 | 22/07/2022 | MESSRS A.B.G CONSTRUCTION | 176.86 | 148.79 | 84.12 | 90
15 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sitai water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000870/2022-2023 | 680/NMD-II | 27/03/2023 | 26/04/2023 | RMD TRADING | 11.42 | 10.74 | 94.02 | 100
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Name of Work: Execution of different works related to Aug. of SITAI PWSS under JAL JEEVAN MISSION PART N | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000279/2023-2024 | 1047/CD | 22/09/2023 | 21/11/2023 | NORTH BENGAL CONSTRUCTION CO | 26.73 | 7.39 | 27.66 | 1
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Execution of different works related to Aug. of SITAI PWSS under JAL JEEVAN MISSION PART-Y | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000277/2023-2024 | 1045/CD | 22/09/2023 | 21/11/2023 | JAINCO TRADERS | 43.08 | 23.94 | 55.57 | 54
18 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Hiring of inspection vehicle for office of the Assistant Engineer , Coochbehar Mechanical Sub- Division, I.C.W JJM works under Northern Mechanical Division -II, P.H.E. Dte. | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001968/2023-2024 | 1012/CMSD | 31/10/2023 | 31/12/2023 | DIPAK SARKAR | 0.69 | 0 | 0 | 100
19 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Sitai water supply scheme, TW no. IV under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000675/2023-2024 | 2033/NMD-II | 26/07/2023 | 25/08/2023 | SUBHRANGSHU GUHARAJA | 11.42 | 11.28 | 98.83 | 100
20 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Name of Work: Execution of different works related Chamta & other mouzas at Aug. of SITAI PWSS under JAL JEEVAN MISSION PART X | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000276/2023-2024 | 1043/CD | 22/09/2023 | 21/11/2023 | MOTI INDUSTRIES | 67.22 | 65.76 | 97.82 | 100
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 1546/CD | 16/08/2024 | 16/08/2024 | Resource Division | 16.93 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 1538/CD | 16/08/2024 | 16/08/2024 | Resource Division | 64.06 | 0 | 0 | 0
23 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT SITAI TW VI. |  |  | BILL/01177/2024-2025 | BP-317/24-25 | 26/09/2024 | 26/09/2024 | WBSEDCL | 10.05 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | FUEL BILL |  |  | BILL/02057/2023-2024 | BP-1419 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 2.08 | 0 | 0 | 0
26 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION CHARGES AT SITAI TW NO. V |  |  | BILL/01178/2024-2025 | BP-324/24-25 | 03/10/2024 | 03/10/2024 | WBSEDCL | 7.67 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | HIRING VEHICLE |  |  | BILL/00560/2024-2025 | BP-204 | 31/07/2024 | 31/07/2024 | AJAD HOSSAIN | 0.53 | 0 | 0 | 0
28 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | PROVIDING FHTC AT KALARAYERKUTHI PWSS |  |  | BILL/02082/2023-2024 | BP-1239-P2 | 26/03/2024 | 26/03/2024 | LONGLAST PIPES (INDIA) PVT. LTD. | 2.09 | 0 | 0 | 0
29 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Construction of 450 cum OHR Providing FHTC & New UPVC Pipe line & other allied works (PART ¿A) at SITAI ZONE ¿ I I PWSS under Cooch Behar Division, PHED | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000420/2021-2022 | 1518/CD | 15/03/2022 | 29/09/2025 | S & P ENTERPRISE | 256.56 | 222.73 | 86.81 | 90
30 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Construction of 450 cum OHR Providing FHTC & New UPVC Pipe line & other allied works (PART ¿A) at SITAI ZONE ¿ I PWSS under Cooch Behar Division, PHED | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000559/2022-2023 | 1282/CD | 02/12/2022 | 01/05/2023 | PALLAB BHAWAL | 282.68 | 170.82 | 60.43 | 25
31 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI/GI Pipe line and other allied works (PART ¿B) at SITAI ZONE ¿ I PWSS under Cooch Behar Division, PHED | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000558/2022-2023 | 1281/CD | 02/12/2022 | 02/06/2025 | PALLAB BHAWAL | 220.47 | 169.72 | 76.98 | 75
32 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Aug of SITAI Water Supply Scheme TW No.- I, II of Zone-I under JJM under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000446/2024-2025 | 2517/NMD-II | 25/11/2024 | 24/05/2025 | B.B CONCERNED | 22.66 | 0 | 0 | 80
33 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Sitai piped water supply scheme. | SM/10147 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO SITAI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000611/2024-2025 | 2312/CD | 23/12/2024 | 20/08/2025 | RAHAMAN ENTERPRISE | 27.34 | 0 | 0 | 90
Total | [13 empty] | 1860.28 | 952.21 | 51.19