## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Providing FHTC construction SSPost with soak pit & New UPVC/DI/GI Pipe line and other allied works (PART ¿C) at CHILAKHANA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000325/2021-2022 | 1286/CD | 15/02/2022 | 16/05/2022 | KHOKAN DAS | 86.72 | 82.68 | 95.34 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Providing House connection for BAJEJAMA CHILAKHANA PWSS under Cooch Behar Division. PHE Dte | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000345/2021-2022 | 1246/CD | 09/02/2022 | 01/03/2022 | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 10.52 | 0 | 0 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Chilakhana Water Supply Scheme TW No.-IV (Kodomtala) under NMD-II,PHE Dte Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000817/2021-2022 | 198/NMD-II | 24/02/2022 | 26/03/2022 | HARA PROSAD DAS | 7.54 | 6 | 79.55 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Chilakhana Water Supply Scheme TW No.-III( Mondol Para ) under NMD-II,PHE Dte Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000819/2021-2022 | 200/NMD-II | 24/02/2022 | 26/03/2022 | DAWA DUKPA | 7.54 | 5.93 | 78.61 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Chilakhana Water Supply scheme T/W No.III (Mondol Para)under NMD-II,PHE.Dte,CoochBehar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000820/2021-2022 | 174/NMD-II | 22/02/2022 | 24/03/2022 | DIPA CHHETRI | 2.38 | 2.38 | 100 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Chilakhana 3rd Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000524/2021-2022 | 1572/CD | 23/03/2022 | 07/04/2022 | ASHIM KUMAR CHAKRABORTY | 2.95 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Supply and delivery of 200 mm dia UPVC pipe(CD) for Chilakhana 4th Site Tubewell under Cooch Behar Division , P.H.E Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000525/2021-2022 | 1573/CD | 23/03/2022 | 07/04/2022 | ASHIM KUMAR CHAKRABORTY | 2.95 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI/GI Pipe line and other allied works (PART ¿A) at CHILAKHANA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000464/2021-2022 | 1606/CD | 24/03/2022 | 22/07/2022 | ASHIM KUMAR CHAKRABORTY | 249.29 | 240.81 | 96.6 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC/DI/GI Pipe line and other allied works (PART ¿B) at CHILAKHANA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000465/2021-2022 | 1605/CD | 24/03/2022 | 22/07/2022 | ASHIM KUMAR CHAKRABORTY | 249.89 | 235.25 | 94.14 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Augmentation of CHILAKHANA PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000088/2022-2023 | 296/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.99 | 4.99 | 100 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Providing FHTC & other allied works at CHILAKHANA ZII PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000367/2022-2023 | 1020/CD | 29/09/2022 | 29/10/2022 | ASHIM KUMAR CHAKRABORTY | 9.98 | 9.55 | 95.71 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Providing FHTC & other allied works at CHILAKHANA ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000368/2022-2023 | 1021/CD | 29/09/2022 | 29/10/2022 | ASHIM KUMAR CHAKRABORTY | 9.98 | 0 | 0 | 1
13 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Supply, delivery & installation of 20 KVA, Servo Motor operated Copper wound line voltage stabilizer of Chilakhana Water Supply Scheme TW No.-IV (Near Kodomtala) under NMD-II, PHE. Dte, Cooch Behar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000805/2021-2022 | 172/NMD-II | 22/02/2022 | 24/03/2022 | M/S ANJALI ENTERPRISE | 2.39 | 2.39 | 100 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2021-2022 | 1364/CD | 24/02/2022 | 24/02/2022 | Resource Division | 10.99 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | FHTC UPLOADING CHARGES UNDER COB DIVN, PHED (chilakhana) |  |  | VCH/001020/2022-2023 | 323 | 29/09/2022 | 29/09/2022 | PRIYANKA MANDAL | 2.46 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | FHTC |  |  | VCH/001620/2021-2022 | BP_2021_22_444 | 11/03/2022 | 11/03/2022 | SANKAR BANIK | 26.17 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | FHTC AT RAMPUR Z-I PWSS (chilakhana) |  |  | VCH/001031/2022-2023 | 421 | 14/11/2022 | 14/11/2022 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 0.51 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Providing FHTC and Laying of Pipe line & other allied works related to AUG. of CHILAKHANA PWSS under JAL JEEVAN MISSION |  |  | VCH/000626/2022-2023 | 322 P | 30/09/2022 | 30/09/2022 | GOUTAM KUMAR DAS | 0.03 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | FHTC |  |  | VCH/001671/2021-2022 | BP_2021_22_489 | 30/03/2022 | 30/03/2022 | MS SSB CONSTRUCTION CO | 47.83 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | FHTC |  |  | VCH/001670/2021-2022 | BP_2021_22_502 | 31/03/2022 | 31/03/2022 | RAJIB CHAKRABORTY | 7.1 | 0 | 0 | 0
21 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Chilakhana water supply scheme Near Mandal Para , Application no. 4002874360 |  |  | VCH/002696/2021-2022 | BP-39/21-22 | 26/03/2022 | 26/03/2022 | WBSEDCL | 0.85 | 0 | 0 | 0
22 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Chilakhana W/s scheme near Kadamtala Chilakhana, Application no. 4002874361 |  |  | VCH/002695/2021-2022 | BP-38/21-22 | 26/03/2022 | 26/03/2022 | WBSEDCL | 0.85 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | PIPE |  |  | VCH/001705/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 1.71 | 0 | 0 | 0
24 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | COST OF PIPE |  |  | VCH/001696/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 9.59 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | FHTC |  |  | VCH/001615/2021-2022 | BP_2021_22_439 | 11/03/2022 | 11/03/2022 | SANKAR CHAKRABORTY | 8.82 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | FHTC AND OTHER ALLIED WORKS AT PWSS |  |  | BILL/00656/2022-2023 | BP-499-2022-23 | 15/12/2022 | 15/12/2022 | SANKAR CHAKRABORTY | 22.12 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 150/CD | 27/04/2023 | 27/04/2023 | Resource Division | 160.59 | 0 | 0 | 0
28 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | SUPPLY OF FUEL ASST ENGINEER TFG FOR THE PERIOD OCTOBER 2022 |  |  | BILL/00130/2023-2024 |  | 12/05/2023 | 12/05/2023 | SUCHITRO FUEL STATION | 0.21 | 0 | 0 | 0
29 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | supply of fuel januar and feb 2023 |  |  | BILL/00129/2023-2024 |  | 12/05/2023 | 12/05/2023 | SUCHITRO FUEL STATION | 0.41 | 0 | 0 | 0
30 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1541/CD | 16/08/2024 | 16/08/2024 | Resource Division | 184.8 | 0 | 0 | 0
31 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | HIRING VEHICLE FOR AE MTB |  |  | BILL/00477/2024-2025 | BP-209 | 31/07/2024 | 31/07/2024 | NARAYAN CHANDRA BANIK | 0.3 | 0 | 0 | 0
32 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Chilakhana piped water supply scheme. | SM/10148 | Augmentation | EXECUTION OF DIFFERENT WORK AT BARA MADHUSUDAN PWSS |  |  | BILL/02052/2023-2024 | BP-1123 | 02/03/2024 | 02/03/2024 | BRAJA GOPAL SAHA | 5.3 | 0 | 0 | 0
Total | [13 empty] | 1137.76 | 589.97 | 51.85