## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000551/2021-2022 | 861/CD | 20/12/2021 | 23/12/2021 | PRIYANKA MANDAL | 2.46 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Addl. Work in connection with Providing FHTC & Laying of Pipe line of GOSANIMARI ZONE ¿ I PWSS under JAL JEEVAN MISSION (PART ¿A) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000323/2022-2023 | 932/CD | 26/09/2022 | 25/11/2022 | MS BIDYUT SARKAR | 98.82 | 98.33 | 99.51 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Providing FHTC & other allied works at GOSANIMARI ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000388/2022-2023 | 1029/CD | 29/09/2022 | 29/10/2022 | MS BIDYUT SARKAR | 9.98 | 9.97 | 99.86 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Providing FHTC & other allied works at GOSANIMARI ZII PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000375/2022-2023 | 1028/CD | 29/09/2022 | 29/10/2022 | GEETA CONSTRUCTION | 9.99 | 9.99 | 99.98 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Providing FHTC & other allied works at GOSANIMARI ZONE - I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000413/2022-2023 | 1224/CD | 28/11/2022 | 27/01/2023 | MS BIDYUT SARKAR | 99.41 | 99.39 | 99.99 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 1382/CD | 22/12/2022 | 22/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | FHTC |  |  | VCH/001651/2021-2022 | BP-2021_22_474 | 25/03/2022 | 25/03/2022 | M/S. NITYAGOPAL BANIK | 90 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | FHTC |  |  | VCH/000050/2022-2023 | BP_22_23_24 | 13/04/2022 | 13/04/2022 | TAPAN CHANDA | 17.41 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | FHTC |  |  | VCH/000097/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 2.86 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | FHTC |  |  | VCH/000053/2022-2023 | BP_22_23_27 | 13/04/2022 | 13/04/2022 | SIBAPADA SINGHA ROY | 4.04 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | FHTC |  |  | VCH/000054/2022-2023 | BP_22_23_28 | 13/04/2022 | 13/04/2022 | RAJAT ROY | 3.23 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | FHTC |  |  | VCH/000068/2022-2023 | BP_22_23_53 | 28/04/2022 | 28/04/2022 | HIRAK CONSTRUCTION | 16.46 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | FHTC |  |  | VCH/000049/2022-2023 | BP_22_23_23 | 13/04/2022 | 13/04/2022 | BISWAJIT GUHA | 6 | 0 | 0 | 0
14 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Quotation for new service connection at Gosanimari TW-V |  |  | VCH/001404/2022-2023 | BP-78/22-23 | 18/10/2022 | 18/10/2022 | WBSEDCL | 1.15 | 0 | 0 | 0
15 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Quotation for new service connection at Gosanimari TW-VI |  |  | VCH/001405/2022-2023 | BP-79/22-23 | 18/10/2022 | 18/10/2022 | WBSEDCL | 1.15 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Providing FHTC & other allied works at GOSANIMARI ZONE - II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000410/2022-2023 | 1221/CD | 28/11/2022 | 27/01/2023 | TAPAN CHANDA | 84.2 | 84.17 | 99.97 | 1
17 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of GOSANIMARI PWSS, TW no .V in the district of Coochbehar under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000821/2022-2023 | 463/NMD-II | 01/03/2023 | 31/03/2023 | MUSTAFI CONCERN | 10.71 | 10.66 | 99.51 | 100
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soakpit Sinking 250mm X 200mm Big dia Tubewell & NewUPVC Pipe line and other allied works (PART ¿A) at GOSANIMARI ZONE ¿ I I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000460/2021-2022 | 1610/CD | 24/03/2022 | 22/07/2022 | TAPAN CHANDA | 258.1 | 249.64 | 96.72 | 1
19 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC Pipe line and other allied works (PART ¿B) at GOSANIMARI ZONE ¿ I I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000461/2021-2022 | 1609/CD | 24/03/2022 | 22/07/2022 | TAPAN CHANDA | 269.98 | 264.22 | 97.87 | 1
20 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of GOSANIMARI PWSS, TW no .VI in the district of Coochbehar under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000758/2022-2023 | 170/NMD-II | 19/01/2023 | 18/02/2023 | ALPHA ENTERPRISE | 10.74 | 10.69 | 99.59 | 100
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2021-2022 | 1361/CD | 24/02/2022 | 24/02/2022 | Resource Division | 10.98 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 493/CD | 07/07/2022 | 07/07/2022 | Resource Division | 36.96 | 0 | 0 | 0
23 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 166/CD | 27/04/2023 | 27/04/2023 | Resource Division | 78.16 | 0 | 0 | 0
24 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT GOSANIMARI TW NO VIII |  |  | BILL/00008/2023-2024 | BP-2023-24-7 | 20/04/2023 | 20/04/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
25 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT GOSANIMARI TW NO VII |  |  | BILL/00010/2023-2024 | BP-2023-24-6 | 20/04/2023 | 20/04/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | FHTC AT PWSS |  |  | BILL/00667/2022-2023 | BP-631-22-23-P | 23/01/2023 | 23/01/2023 | KARTICK CH SEAL | 0.06 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC Pipe line and other allied works (PART ¿B) at GOSANIMARI ZONE ¿ I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000467/2021-2022 | 1603/CD | 24/03/2022 | 22/07/2022 | MS BIDYUT SARKAR | 273.64 | 253.8 | 92.75 | 92
28 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Providing FHTC & Construction of Pump house at HW site & 2nd Site GOSANIMARI ZONE ¿ I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000240/2022-2023 | 726/CD | 27/08/2022 | 11/10/2022 | MS BIDYUT SARKAR | 33.21 | 28.99 | 87.29 | 70
29 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Goshanimari water supply scheme, TW no VII and VIII under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000655/2023-2024 | 1950/NMD-II | 24/07/2023 | 23/08/2023 | H.K DAS AND CO. | 23.4 | 23.38 | 99.95 | 100
30 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Providing FHTC 3rd Site Pump House Boundary Wall SSPost with soak pit Sinking 250mm X 200mm Big dia Tubewell & New UPVC Pipe line and other allied works (PART ¿A) at GOSANIMARI ZONE ¿ I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000468/2021-2022 | 1602/CD | 24/03/2022 | 08/07/2025 | MS BIDYUT SARKAR | 250.09 | 244.65 | 97.82 | 80
31 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Goshanimari water supply scheme, TW no I of Zone-I (Replacement) under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000872/2022-2023 | 688/NMD-II | 28/03/2023 | 27/04/2023 | DILIP MAHATO | 8.76 | 0 | 0 | 100
32 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Gosanimari piped water supply scheme. | SM/10150 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000269/2025-2026 | 745/CD | 17/05/2025 | 15/08/2025 | GHOSH AND SAHA CONSTRUCTION | 59.92 | 0 | 0 | 0
Total | [13 empty] | 1835.53 | 1387.88 | 75.61