## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | RESTORATION OF PIPE LINE AND OTHER ALLIED WORK RELATED TO FHTC UNDER JJM PROGRAMME FOR BANESWAR PWSS UNDER COOCH BEHAR DIVISION, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000472/2021-2022 | 720/SD | 18/03/2022 | 02/04/2022 | HIRAK CONSTRUCTION | 4.64 | 4.64 | 100 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Hiring of Diesel Vehicle of Bolero Maxi cab for the Office use of Assistant Engineer, Cooch Behar Sadar Sub-Division, PHE Dte. for 12 Months (October 2021 to September 2022) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000168/2021-2022 | 528/CD (3) | 30/09/2021 | 12/10/2021 | PARAUDDIN MIAH | 2.02 | 0.36 | 17.91 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | " Yard lighting arrangement at pump house No.-I under Baneswar Water supply scheme Under Northern Mechanical Division-II P.H.E Dte." | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000709/2021-2022 | 1120/NMD-II | 20/09/2021 | 20/10/2021 | THE BANERJEE CONCERN | 4.52 | 4.52 | 100 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | hiring desel vechile |  |  | VCH/000544/2022-2023 | BP-22_23-162 | 03/08/2022 | 03/08/2022 | NIRANJAN KIRTANIA | 0.75 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | FHTC |  |  | VCH/001654/2021-2022 | BP-2021_22_498 | 31/03/2022 | 31/03/2022 | MS BIDYUT SARKAR | 80 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | New laying of UPVC/DI Pipe Line, Providing FHTC & Other allied works at Baneswar Zone-I (Part-C) PWSS under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000441/2021-2022 | 1433/CD | 10/03/2022 | 09/05/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 47.34 | 44.55 | 94.11 | 95
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Providing FHTC, Street stand post along with soakpit, New laying of UPVC/DI Pipe Line & Other allied works at BANESWAR ZONE- II under Cooch Behar Division, P.H.E Dte. (PART-D) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000436/2021-2022 | 1428/CD | 10/03/2022 | 09/05/2022 | MS SURAJIT MAJUMDER | 23.55 | 22.98 | 97.6 | 100
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-C) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000212/2022-2023 | 542/CD | 22/07/2022 | 22/01/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-D) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000213/2022-2023 | 543/CD | 22/07/2022 | 22/01/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-E) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000215/2022-2023 | 569/CD | 01/08/2022 | 01/02/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-F) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000216/2022-2023 | 571/CD | 02/08/2022 | 02/02/2023 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Hiring of Diesel Vehicle of Maxi Cab for the Office use of Assistant Engineer, (H.Q) under office of the Executive Engineer, Cooch Behar Division, PHE Dte. for 02 Months (August 2022 to September 2022) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000268/2022-2023 | 517/CD | 14/07/2022 | 14/09/2022 | BHAGWATI BHUJEL | 0.34 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Execution of different works related to BANESWAR Z-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000769/2022-2023 | 1656/CD | 10/02/2023 | 11/04/2023 | GOPAL CH.GHOSH | 30.94 | 30.29 | 97.9 | 100
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Execution of different works related to BANESWAR Z ¿ I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000063/2023-2024 | 402/CD | 23/05/2023 | 22/06/2023 | UTTAM SAHA | 9.17 | 9.17 | 100 | 100
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at Different Location of BANESHWAR ZONE I , II & III PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000457/2021-2022 | 1444/CD | 10/03/2022 | 09/04/2022 | MS DD ENTERPRISE | 53.5 | 49.79 | 93.06 | 1
16 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BANESWAR ZONE-III TW no II in the district of COOCHBEHAR under Northern Mechanical Division-II, PHE Dte ALIPURDUAR | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000748/2022-2023 | 138/NMD-II | 17/01/2023 | 16/02/2023 | DEY ENTERPRISE (MALDA) | 10.75 | 10.66 | 99.22 | 100
17 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BANESWAR ZONE-III TW no I in the district of COOCHBEHAR under Northern Mechanical Division-II, PHE Dte ALIPURDUAR | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000834/2022-2023 | 543/NMD-II | 16/03/2023 | 15/04/2023 | THE BANERJEE CONCERN | 10.74 | 10.61 | 98.79 | 100
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2021-2022 | 1365/CD | 24/02/2022 | 24/02/2022 | Resource Division | 5.74 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 1953/CD | 24/03/2023 | 24/03/2023 | Resource Division | 90.19 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 136/CD | 27/04/2023 | 27/04/2023 | Resource Division | 14.89 | 0 | 0 | 0
21 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | New service connection for BANESWAR PWSS, ZONE-I,PH-I |  |  | BILL/02062/2023-2024 | BP-2023-24-434 | 05/12/2023 | 05/12/2023 | WBSEDCL | 1.81 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Providing FHTC and Laying of Pipe line & other allied works related to PWSS under JAL JEEVAN MISSION |  |  | VCH/000940/2022-2023 | 350 P | 29/10/2022 | 29/10/2022 | S & P ENTERPRISE | 0.07 | 0 | 0 | 0
23 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | QUOTATION FOR NSC AT BASENWAR PH NO III,Z-I |  |  | BILL/01017/2023-2024 | BP-2023-24-228 | 24/07/2023 | 24/07/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
24 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Quotation for new service connection at baneswar TW No- I |  |  | BILL/00037/2022-2023 | BP-126/22-23 | 13/01/2023 | 13/01/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
25 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | QUOTATION FOR NSC AT BANESWAR (AUG) PH NO-I,Z-II |  |  | BILL/01034/2023-2024 |  | 25/07/2023 | 25/07/2023 | WBSEDCL | 5.42 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Providing 150nos F.H.T.C. Connection in the command area at P. W.S.S. under Cooch Behar Sadar Sub-Division, PHE Dte. |  |  | VCH/000659/2022-2023 | 342 P | 25/10/2022 | 25/10/2022 | GOUTAM KUMAR DAS | 0.03 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | FHTC AT PWSS UNDER COB DIVN, PHED |  |  | VCH/001005/2022-2023 | 372 | 23/10/2022 | 23/10/2022 | MS SSB CONSTRUCTION CO | 2.3 | 0 | 0 | 0
28 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | QUOTATION FOR NSC AT BANESWAR AUG PH NO -I,Z-II |  |  | BILL/01822/2023-2024 | BP-2023-24-340 | 27/09/2023 | 27/09/2023 | WBSEDCL | 5.42 | 0 | 0 | 0
29 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Quotation for new service connection at baneswar TW No- II |  |  | BILL/00036/2022-2023 | BP-125/22-23 | 13/01/2023 | 13/01/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
30 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | QUOTATION FOR NSC AT BANESWAR AUG PH NO -III,Z-II |  |  | BILL/01824/2023-2024 | BP-2023-24-344 | 27/09/2023 | 27/09/2023 | WBSEDCL | 4.65 | 0 | 0 | 0
31 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Providing FHTC, Street stand post along with soakpit, New laying of UPVC/DI Pipe Line & Other allied works at BANESWAR ZONE- III under Cooch Behar Division, P.H.E Dte. (PART-D) | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000435/2021-2022 | 1436/CD | 10/03/2022 | 09/05/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 44.84 | 43.78 | 97.63 | 23
32 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Providing FHTC, Construction of sluice valve chamber and Street stand post along with soakpit , New laying of UPVC/DI Pipe Line & Other allied works at Baneswar Zone-II (Part-C) PWSS under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000437/2021-2022 | 1429/CD | 10/03/2022 | 09/05/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 43.28 | 41.87 | 96.73 | 26
33 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Providing FHTC, Street stand post along with soakpit , New laying of UPVC/DI Pipe Line & Other allied works at Baneswar Zone-II (Part-E) PWSS under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000438/2021-2022 | 1430/CD | 10/03/2022 | 09/05/2022 | GOPAL CH.GHOSH | 24.31 | 23.41 | 96.28 | 1
34 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Providing FHTC, Street stand post along with soakpit , New laying of UPVC/DI Pipe Line & Other allied works at Baneswar Zone-III (Part-C) PWSS under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000439/2021-2022 | 1431/CD | 10/03/2022 | 09/05/2022 | SIDHARTHA ROY | 84.21 | 82.96 | 98.51 | 100
35 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Execution of different works related to BANESWAR Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000794/2022-2023 | 1870/CD | 14/03/2023 | 13/04/2023 | MS DD ENTERPRISE | 25.55 | 24.25 | 94.93 | 50
36 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Execution of different works related to BANESHWAR Z-III PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000022/2023-2024 | 388/CD | 23/05/2023 | 20/10/2023 | KARTICK CH SEAL | 13.1 | 13.03 | 99.52 | 100
37 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Temporary Water Supply arrangement at Baneswar PWSS under JJM in the District of Cooch Behar under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000846/2022-2023 | 1764/A/CD | 01/03/2023 | 01/05/2023 | GEETA CONSTRUCTION | 0.96 | 0.96 | 100 | 1
38 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Baneswar Water Supply Scheme TW No.- III of zone-II and III under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/001231/2023-2024 | 2967/NMD-II | 21/11/2023 | 21/12/2023 | M/S A.D. ENTERPRISE | 21.16 | 19.25 | 90.98 | 80
39 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Laying of raising main & delivery line connection , Constructions of Head works site Pump & Boundary walland Other allied works at Baneswar Zone-III PWSS under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000443/2021-2022 | 1435/CD | 10/03/2022 | 09/05/2022 | KARTICK CH SEAL | 30.83 | 28 | 90.82 | 70
40 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Execution of different works related to Baneswar Z-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000319/2023-2024 | 1301/CD | 24/11/2023 | 23/01/2024 | GOPAL CH.GHOSH | 9.52 | 6.85 | 71.96 | 71
41 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Baneswar water supply scheme, TW no I and II of Zone-II and TW III of Zone-I under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000040/2023-2024 | 1008/NMD-II | 16/05/2023 | 15/06/2023 | CHOWDHURY AND BASU ENTERPRISE | 32.8 | 30.9 | 94.2 | 100
42 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Execution of different works related to BANESHWAR Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000416/2023-2024 | 1387/CD | 05/12/2023 | 03/02/2024 | DAS AND COMPANY | 9.95 | 9.84 | 98.86 | 100
43 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | New laying of UPVC/DI Pipe Line, Providing FHTC & Other allied works at Baneswar Zone-I (Part-B) PWSS under Cooch Behar Division, P.H.E Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000440/2021-2022 | 1432/CD | 10/03/2022 | 10/12/2024 | HIRAK CONSTRUCTION | 90.09 | 78.75 | 87.42 | 100
44 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Providing FHTC, Constructions 3.6 m x 3.0 m switch room & Boundary wall, Street stand post along with soakpit, New laying of UPVC/DI Pipe Line & Other allied works at Baneswar Zone-III PWSS under Cooch Behar Division, P.H.E Dte. (Part-B) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000427/2021-2022 | 1523/CD | 15/03/2022 | 10/09/2025 | MALAY KR.DEB | 126.66 | 122.94 | 97.06 | 85
45 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Execution of different works related to BANESWAR Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000793/2022-2023 | 1869/CD | 14/03/2023 | 10/05/2025 | PARITOSH KR.CHOUDHARY | 20.97 | 12.98 | 61.89 | 95
46 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | EXECUTION OF DIFFERENT WORKS (within BANESWAR area) RELATED TO Baraibari PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000656/2024-2025 | 85/CD | 17/01/2025 | 18/03/2025 | ASHIM KUMAR CHAKRABORTY | 70.33 | 0 | 0 | 0
47 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Constructions of 250 Cum OHR as per Departmental Design & drawing, Providing F.H.T.C New laying of UPVC/DI Pipe Line & other allied work at BANESWAR Zone-II PWSS under Cooch Behar Division , P.H.E Dte. (PART-A) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000422/2021-2022 | 1520/CD | 15/03/2022 | 09/07/2025 | PALLAB BHAWAL | 200.61 | 179.38 | 89.42 | 1
48 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Repairing of 250 Cum OHR as per Departmental Design & drawing, Providing F.H.T.C New laying of UPVC/DI Pipe Line & other allied work at BANESWAR Zone-I PWSS under Cooch Behar Division , P.H.E Dte. (PART-A) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000423/2021-2022 | 1521/CD | 15/03/2022 | 07/07/2025 | PALLAB BHAWAL | 179.72 | 175.16 | 97.46 | 74
49 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Constructions of 250 Cum OHR as per Departmental Design & drawing, Providing F.H.T.C New laying of UPVC/DI Pipe Line & other allied work at BANESWAR Zone-III PWSS under Cooch Behar Division , P.H.E Dte. (PART-A) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000424/2021-2022 | 1522/CD | 15/03/2022 | 03/07/2025 | PALLAB BHAWAL | 185.37 | 171.28 | 92.4 | 1
50 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | Execution of different works related to BANESWAR Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000786/2022-2023 | 1862/CD | 14/03/2023 | 30/04/2025 | KRISHNA GOPAL BASK | 38 | 34.85 | 91.7 | 98
51 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF BANESWAR PIPED WATER SUPPLY SCHEME | SM/10152 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO Baneswar PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000601/2024-2025 | 2302/CD | 23/12/2024 | 22/04/2025 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 9.32 | 0 | 0 | 98
Total | [13 empty] | 1677.37 | 1288 | 76.79