## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing FHTC and Laying of Pipe line at BARO DHAPERCHATRA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000403/2021-2022 | 1461/CD | 10/03/2022 | 09/04/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 46.13 | 39.89 | 86.48 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing functional house hold tap connection (unmetered) 135 nos. in BARA DHAPERCHATRA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. (Part-C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000452/2021-2022 | 462/MTB | 04/03/2022 | 19/03/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 4.98 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing functional house hold tap connection 145 nos. in BARO DHAPERCHATRA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000044/2022-2023 | 15/MTB | 11/04/2022 | 26/04/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 5.03 | 4.96 | 98.54 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing FHTC & Laying of DI pipeline and other allied works under JJM Programme for Chekierchhara PWSS under Mathabhanga Sub-Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000133/2022-2023 | 38/MTB | 02/05/2022 | 09/05/2022 | NABIN DEBNATH | 4.66 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Supply of C.I Specials for BARO DHAPERCHATRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000248/2022-2023 | 737/CD | 27/08/2022 | 26/09/2022 | MS SSB CONSTRUCTION CO | 9.64 | 9.64 | 100 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing House connection for CHHOTO GADAIKHORA PWSS under Cooch Behar Division. PHE Dte. P 2 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000349/2021-2022 | 1250/CD | 09/02/2022 | 11/03/2022 | ASHIM KUMAR CHAKRABORTY | 14.03 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing FHTC, laying of Pipe line and other allied works at BARO GADAIKHORA PWSS under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000072/2022-2023 | 269/CD | 24/05/2022 | 23/07/2022 | BIJOY ROY | 39.76 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing House connection for CHHOTO GADAIKHORA PWSS under Cooch Behar Division. PHE Dte. P 1 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000330/2021-2022 | 1231/CD | 09/02/2022 | 11/03/2022 | TAPAN CHANDA | 17.55 | 0 | 0 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing 150nos functional house hold tap connection within command area of Chhoto Godaikhora Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte.(Part-D) Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000056/2022-2023 | 49/MTB | 02/05/2022 | 09/05/2022 | MS DD ENTERPRISE | 4.84 | 0 | 0 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing FHTC & other allied works at BARO DHAPERCHATRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000356/2022-2023 | 1009/CD | 29/09/2022 | 29/10/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 9.97 | 9.41 | 94.3 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing FHTC, Repairing of reservoir and Boundary Wall at H/W site and laying new Pipe line and other allied works at Augmentation BARO DHAPERCHATRA PWSS under Cooch Behar Division, PHED.(Part-C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000071/2022-2023 | 268/CD | 24/05/2022 | 23/07/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 48.13 | 44.7 | 92.87 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing FHTC, Construction of pump house, Boundary wall (3rd T/W site) & laying of Pipe line and other allied works at Augmentation of BARO DHAPERCHATRA PWSS under Cooch Behar Division, PHED. (Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000076/2022-2023 | 273/CD | 24/05/2022 | 23/07/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 70.05 | 66.41 | 94.8 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Providing functional house hold tap connection within command area of Chhoto Godaikhora Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte.(Part-C) Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000055/2022-2023 | 48/MTB | 02/05/2022 | 09/05/2022 | ARUN KUMAR KARMAKAR | 4.84 | 0 | 0 | 1
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of BARO DHAPERCHATRA PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000064/2022-2023 | 261/CD | 24/05/2022 | 08/07/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 12 | 11.98 | 99.9 | 1
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 62/CD | 12/04/2022 | 12/04/2022 | Resource Division | 9.88 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 1368/CD | 22/12/2022 | 22/12/2022 | Resource Division | 31.44 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | FHTC |  |  | VCH/001650/2021-2022 | BP-2021_22_470 | 23/03/2022 | 23/03/2022 | NABIN DEBNATH | 22.9 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | FHTC |  |  | VCH/001655/2021-2022 | BP-2021_22_498 | 31/03/2022 | 31/03/2022 | MS BIDYUT SARKAR | 3.3 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | FHTC AT AMTHENGA |  |  | VCH/000738/2022-2023 | 233 | 03/09/2022 | 03/09/2022 | KAJAL KUMAR DE | 0.82 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | COST OF PIPE |  |  | VCH/001698/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 3.8 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Execution of different works related to CHHOTO GADAI KHORA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000726/2022-2023 | 1653/CD | 10/02/2023 | 11/04/2023 | ASHIM KUMAR CHAKRABORTY | 21.56 | 0 | 0 | 1
22 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARADHAPERCHATRA TW no III in the district of COOCHBEHAR under Northern Mechanical Division-II, PHE Dte ALIPURDUAR. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000844/2022-2023 | 590/NMD-II | 18/03/2023 | 17/04/2023 | RIPON DAS | 10.74 | 10.62 | 98.86 | 100
23 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | Execution of different works related to BARA DHAPERCHATRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000725/2022-2023 | 1654 | 10/02/2023 | 11/04/2023 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 23.41 | 10.41 | 44.47 | 100
24 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BARA DHEPCHATRA W/SS TW NO-III |  |  | BILL/00542/2022-2023 | BP-171/22-23 | 29/03/2023 | 29/03/2023 | WBSEDCL | 1.25 | 0 | 0 | 0
25 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | FUEL BILL |  |  | BILL/02055/2023-2024 | BP-1410 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 0.99 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection (FJTC) within command area of Baro Dhaperchatra Piped water supply Scheme. | SM/10158 | Augmentation | hiring of vehicle for ee/cd |  |  | BILL/00595/2024-2025 | BP-230 | 01/08/2024 | 01/08/2024 | SWAPAN KR.SARKAR | 0.45 | 0 | 0 | 0
Total | [13 empty] | 477.86 | 208.02 | 43.53