## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | FHTC |  |  | VCH/001605/2021-2022 | BP_2021_22_429 | 10/03/2022 |  | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 5.02 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | FHTC |  |  | VCH/001669/2021-2022 | BP_2021_22_488 | 30/03/2022 |  | MS SSB CONSTRUCTION CO | 50 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | FHTC |  |  | VCH/001664/2021-2022 | BP_2021_22_484 | 30/03/2022 |  | DIGENDRA CH DEY & SONS | 14.11 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | FHTC |  |  | VCH/001665/2021-2022 | BP_2021_22_487 | 30/03/2022 |  | MS BIDYUT SARKAR | 8.77 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | FHTC |  |  | VCH/000043/2022-2023 | BP_22_23_16 | 13/04/2022 |  | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 4.4 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | FHTC |  |  | VCH/000001/2002-2003 | BP-2022-23-22 | 13/04/2022 |  | ASHIM KUMAR CHAKRABORTY | 0.68 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | FHTC |  |  | VCH/000065/2022-2023 | BP_22_23_51 | 28/04/2022 |  | INDRAJIT MITRA | 6.01 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Construction of pump house, Boundary wall at 2ND site and laying of Pipe line and other allied works at in-connection with augmentation of NAGAR CHANGRABANDHA (Zone-II) PWSS under Cooch Behar Division, PHED. (Part-C) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000008/2022-2023 | 24/CD | 07/04/2022 | 05/08/2022 | BISWAJIT GUHA | 48.23 | 28 | 58.05 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 1372/CD | 22/12/2022 |  | Resource Division | 29.41 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of N.CHANGRABANDHA Z-II PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000066/2022-2023 | 263/CD | 24/05/2022 | 08/07/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 12 | 11.84 | 98.69 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 99/CD | 26/04/2023 |  | Resource Division | 191.2 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | FHTC & OTHER ALLIED WORKS AT PWSS |  |  | VCH/001035/2022-2023 | 426 | 30/11/2022 |  | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 1.61 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Providing FHTC, Repairing of reservoir and laying new Pipe line and other allied works at in-connection with augmentation NAGAR CHANGRABANDHA (ZONE-I) PWSS under Cooch Behar Division, PHED.(Part-A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000023/2022-2023 | 39/CD | 07/04/2022 | 22/05/2022 | RELIANCE UN EMPLOYED ENGINEERS CO OP SOC LTD | 83.5 | 53.74 | 64.36 | 1
14 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT NAGARCHANGRABANDHA TW NO-III |  |  | BILL/00084/2023-2024 | BP-2023-24-80 | 15/05/2023 |  | WBSEDCL | 1.01 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Soil investigation work for the proposed "Overhead reservoir" at Changrabandha (Zone-II) PWSS under Mathabhanga Sub-Division, P.H.E Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000582/2021-2022 | 465/MTB | 04/03/2022 | 19/03/2022 | G. TECH INDIA | 0.58 | 0.57 | 97.79 | 0
16 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | QUOTATION FOR NSC AT NAGAR CHANGRABANDHA TW NO IV |  |  | BILL/01730/2023-2024 | BP-2023-24-313 | 27/09/2023 |  | WBSEDCL | 5.56 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Execution of different works related to NAGAR CHANGRA BHANDHA (ZONE-II) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000547/2022-2023 | 1681/CD | 13/02/2023 | 13/07/2023 | SHIBA ENTERPRISE | 99.06 | 16.23 | 16.38 | 33
18 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augumentation of Nagar Changrabanda Water Supply Scheme TW No.- I AND II OF ZONE-II under NMD-II,PHE.Dte,APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000044/2023-2024 | 1050/NMD-II | 25/05/2023 | 24/06/2023 | DILIP MAHATO | 23.3 | 0 | 0 | 50
19 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Supply & delivery of Submersible pump motor set and other Electro Mechanical Componenets at JAMALDAHA (REJU) PWSS and adjacent W/S Scheme in the district of Coochbehar under Northern Mechanical Division-II P.H.E Dte. |  | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000043/2024-2025 | 1934/CMSD | 13/06/2024 | 13/07/2024 | ALPHA ENTERPRISE | 4.55 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Execution of different works related to NAGAR CHANGRABANDHA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000041/2024-2025 | 1149/CD | 14/06/2024 | 13/08/2024 | UDAY CHAKI | 7.74 | 0 | 0 | 60
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 1543/CD | 16/08/2024 |  | Resource Division | 22.65 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for providing functional household tap connection within command area of NAGAR CHANGRABANDA Piped Water Supply Scheme | SM/10159 | Augmentation | Construction of pump house, Boundary wall at Head work site and laying of Pipe line and other allied works at inconnection with augmentation of NAGAR CHANGRABANDHA (Zone-II) PWSS under Cooch Behar Division, PHED. (Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000009/2022-2023 | 25/CD | 07/04/2022 | 05/08/2022 | SHIBA ENTERPRISE | 93.03 | 49.09 | 52.77 | 50
Total | [13 empty] | 712.42 | 159.46 | 22.38