## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | Providing house connection of drinking water to the house hold of command area under RAMPUR W.S.S. of Tufanganj Sub-Division, PHED under Jal Swapna Programme. (Part-B) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000388/2021-2022 | 331/TFG | 27/01/2022 | 11/02/2022 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 4.39 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | Providing FHTC Pump House SSPost & New Pipe line and other allied works at CHHAT RAMPUR DWITIYA KHANDA PWSS under Cooch Behar Division, PHED (PART ¿ C) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000014/2022-2023 | 30/CD | 07/04/2022 | 05/08/2022 | BIJAN KR.ROY | 12.76 | 12.38 | 97 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | Providing FHTC laying of Pipe line other allied works at CHHAT RAMPUR DWITIYA KHANDA PWSS under JAL JEEVAN MISSION. (Part-A) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000206/2022-2023 | 683/CD | 23/08/2022 | 22/10/2022 | TAPASH KUMAR BHOWMICK | 90.35 | 54.06 | 59.83 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Augmentation of CHHAT RAMPUR DWITIYA KHANDA PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000089/2022-2023 | 297/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 100 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | FHTC |  |  | VCH/000077/2022-2023 | BP_22_23_56 | 28/04/2022 | 28/04/2022 | SHREE RANI SATI ENTERPRISE | 4.39 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | FHTC |  |  | VCH/001649/2021-2022 | BP-2021_22_473 | 23/03/2022 | 23/03/2022 | MS BIDYUT SARKAR | 14.04 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | FHTC |  |  | VCH/001657/2021-2022 | BP_2021_22_476 | 25/03/2022 | 25/03/2022 | GOUTAM KUMAR DAS | 10.52 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | FHTC |  |  | VCH/001658/2021-2022 | BP_2021_22_477 | 25/03/2022 | 25/03/2022 | RELIANCE UN EMPLOYED ENGINEERS CO OP SOC LTD | 5 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | FHTC |  |  | VCH/000108/2022-2023 | BP-2022-23-22 | 13/04/2022 | 13/04/2022 | ASHIM KUMAR CHAKRABORTY | 0.44 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | Constructions of 250 Cum OHR as per Departmental Design & drawing , Providing F.H.T.C ,New laying DI Pipe Line & other allied work at CHHAT RAMPUR PWSS under JAL JEEVAN MISSION (PART ¿D) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000217/2022-2023 | 706/CD | 27/08/2022 | 23/02/2023 | GOUTAM KUMAR DAS | 88.74 | 36.36 | 40.97 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | FHTC AT RAMPUR PWSS |  |  | BILL/00603/2022-2023 | BP-480-22-23-P1 | 13/12/2022 | 13/12/2022 | TAPAN CHANDA | 3.96 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | Name of Work: Execution of different works related to CHHAT RAMPUR PWSS under JAL JEEVAN MISSION PART B | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000265/2023-2024 | 1035/CD | 22/09/2023 | 21/11/2023 | UNIQUE ENGINEERS CO OP SOCIETY LTD | 38.6 | 37.96 | 98.35 | 100
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | Name of Work: Execution of different works related to CHHAT RAMPUR PWSS under JAL JEEVAN MISSION PART A | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000268/2023-2024 | 1034/cd | 22/09/2023 | 21/12/2023 | UTTAM SAHA | 30.88 | 30.47 | 98.69 | 10
14 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | Charges for new service connection at Chat rampur dwitiya khanda PWSS, P/H-III. |  |  | BILL/00747/2024-2025 | BP-204/24-25 | 15/07/2024 | 15/07/2024 | WBSEDCL | 5.35 | 0 | 0 | 0
15 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | Charges for new service connection at Chat rampur ditwiya khanda PWSS, P/H-II |  |  | BILL/00746/2024-2025 | BP-205/24-25 | 15/07/2024 | 15/07/2024 | WBSEDCL | 5.54 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000007/2025-2026 | 600/CD | 28/04/2025 | 25/10/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 60
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | Providing FHTC Pump House SSPost & New Pipe line and other allied works at CHHAT RAMPUR DWITIYA KHANDA PWSS under Cooch Behar Division, PHED (PART ¿ B) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000039/2022-2023 | 97/CD | 18/04/2022 | 05/03/2024 | GHOSH AND SAHA CONSTRUCTION | 133.55 | 112.37 | 84.14 | 100
18 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of ChatRampur Dwitiyakhanda water supply scheme, TW no III and IV under Northern Mechanical Division-II, PHE Dte. APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000727/2023-2024 | 2325/NMD-II | 01/08/2023 | 15/01/2025 | DEY ENTERPRISE (MALDA) | 23.24 | 19.53 | 84.06 | 100
19 | COOCHBEHAR |  | Coochbehar Division | Augmentation of CHAT RAMPUR DWITIYA KHANDA Piped Water Supply Scheme | SM/10161 | Augmentation | EXECUTION OF DIFFERENT WORKS (ithin CHAT RAMPUR DWITIYA KHANDA area) RELATED TO NAKKATIGACHH PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000669/2024-2025 | 98/CD | 17/01/2025 | 18/03/2025 | SHRI ANNAPURNA DISTRIBUTORS | 14.67 | 1.44 | 9.81 | 100
Total | [13 empty] | 588.22 | 309.56 | 52.63