## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | Providing functional house hold tap connection (unmetered) 135 nos. in Upen chowki KuchlibariPiped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. (Part-C) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000445/2021-2022 | 450/MTB | 04/03/2022 | 19/03/2022 | SANJAY MANDAL | 4.98 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | Shifting of Pipe line incl River Crossing with suppurting RSJ pile at Kangratoli immigr. Rd. at PURBA FULKADABRI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000408/2021-2022 | 1466/CD | 10/03/2022 | 09/04/2022 | MANABENDRA DE | 35.47 | 24.1 | 67.96 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | Providing FHTC, Construction of pump house, Boundary wall at additional T/W site and laying of Pipe line and other allied works at in-connection with augmentation of PURBA FULKAR DABRI PWSS under Cooch Behar Division, PHED. (Part-B) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000006/2022-2023 | 22/CD | 07/04/2022 | 05/08/2022 | NABIN DEBNATH | 82.64 | 57.59 | 69.69 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | Providing FHTC, Repairing of Boundary wall, Pump house & Blower room, and laying of Pipe line and other allied works at in-connection with augmentation of PURBA FULKARDABRI PWSS under Cooch Behar Division, PHED.(Part-A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000007/2022-2023 | 23/CD | 07/04/2022 | 05/08/2022 | MANABENDRA DE | 85.75 | 75.75 | 88.34 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of PURBA FULKADABRI PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000065/2022-2023 | 262/CD | 24/05/2022 | 08/07/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 12 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | Providing FHTC and Laying of pipe line and other allied work at PURBA FULKARDABRI PWSS under JAL JEEVAN MISSION.(Part-E) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000335/2022-2023 | 984/CD | 29/09/2022 | 28/11/2022 | ASHIT KUMAR SINGHA | 60.18 | 43.43 | 72.17 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | Providing FHTC, Repairing of reservoir and laying new Pipe line and other allied works at in-connection with augmentation PURBA FULKAR DABRI PWSS under Cooch Behar Division, PHED.(Part-C) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000005/2022-2023 | 21/CD | 07/04/2022 | 05/08/2022 | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 66.67 | 57.76 | 86.64 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | Providing FHTC and Laying of pipe line and other allied work at PURBA FULKARDABRI PWSS under JAL JEEVAN MISSION (Part-D) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000329/2022-2023 | 978/CD | 29/09/2022 | 16/05/2025 | MANABENDRA DE | 76.88 | 72.42 | 94.2 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 1370/CD | 22/12/2022 | 22/12/2022 | Resource Division | 29.75 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | COST OF PIPE |  |  | VCH/001699/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 1.11 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | FHTC |  |  | VCH/001690/2021-2022 | BP_2021_22_506 | 31/03/2022 | 31/03/2022 | SHIBA ENTERPRISE | 28.89 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Purba Fulkardabri water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar |  |  | ORD/000849/2023-2024 | 2429/NMD-II | 10/08/2023 | 09/09/2023 | M/S RATAN KUMAR DASGUPTA & CO. | 11.01 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 106/CD | 26/04/2023 | 26/04/2023 | Resource Division | 29.6 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | HIRING VEHICLE |  |  | BILL/00480/2024-2025 | BP-212 | 31/07/2024 | 31/07/2024 | BHAGWATI BHUJEL | 0.66 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | HIRING VEHICLE |  |  | BILL/00489/2024-2025 | BP-224 | 01/08/2024 | 01/08/2024 | ANIMESH DHAR CHOUDHURY | 0.36 | 0 | 0 | 0
16 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of PURBA FULKARDABRI Piped water supply schemes. | SM/10162 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT PURBA FULKARDABRI (AUG) TW I. |  |  | BILL/02166/2024-2025 | BP-471/24-25 | 17/03/2025 | 17/03/2025 | WBSEDCL | 6.05 | 0 | 0 | 0
Total | [13 empty] | 531.99 | 331.06 | 62.23