## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Providing functional house hold tap connection (unmetered) 135 nos. in Nijtaraf Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000444/2021-2022 | 449/MTB | 04/03/2022 | 19/03/2022 | PARITOSH PANDIT | 4.98 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Providing functional house hold tap connection (unmetered) 145 nos. in NIZTARAF Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000041/2022-2023 | 12/MTB | 11/04/2022 | 26/04/2022 | PARITOSH PANDIT | 5.04 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of NIZTARAF PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000062/2022-2023 | 259/CD | 24/05/2022 | 08/07/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 12 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 1371/CD | 22/12/2022 | 22/12/2022 | Resource Division | 70.31 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | FHTC |  |  | VCH/001652/2021-2022 | BP-2021_22_474 | 25/03/2022 | 25/03/2022 | M/S. NITYAGOPAL BANIK | 16.95 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | FHTC |  |  | VCH/001674/2021-2022 | BP_2021_22_489 | 30/03/2022 | 30/03/2022 | MS SSB CONSTRUCTION CO | 3.05 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | FHTC |  |  | VCH/000081/2022-2023 | BP_22_23_56 | 28/04/2022 | 28/04/2022 | SHREE RANI SATI ENTERPRISE | 4.98 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | FUEL BILL |  |  | VCH/000348/2022-2023 |  | 04/08/2022 | 04/08/2022 | R.C.BANIK & SONS | 0.89 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Providing FHTC, Repairing of Pump house, boundary wall and laying new Pipe line and other allied works at inconnection with augmentation of NIJTARAF PWSS under Cooch Behar Division, PHED.(Part-C) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000011/2022-2023 | 27/CD | 07/04/2022 | 05/08/2022 | ABHIJIT KUMAR DAS | 71.44 | 0 | 0 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Providing FHTC, laying new Pipe line & other allied works at in-connection with augmentation of NIJTARAF PWSS under Cooch Behar Division, PHED.(Part-B) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000012/2022-2023 | 28/CD | 07/04/2022 | 05/08/2022 | PARITOSH PANDIT | 62.98 | 0 | 0 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Supply of C.I Specials for NIJTARAF PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000293/2022-2023 | 894/CD | 22/09/2022 | 22/10/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 9.62 | 0 | 0 | 1
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Execution of different works related to NIZTARAF PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000743/2022-2023 | 1665/CD | 10/02/2023 | 11/04/2023 | UDAY CHAKI | 29.3 | 0 | 0 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Execution of different works related to NIZTARAF PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000450/2022-2023 | 1426/CD | 29/12/2022 | 28/01/2023 | MS SURAJIT MAJUMDER | 7.47 | 0 | 0 | 1
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 1473/CD | 16/01/2023 | 16/01/2023 | Resource Division | 15.9 | 0 | 0 | 0
15 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT NIJTARAF PWSS TW NO -I |  |  | BILL/01436/2023-2024 | BP-2023-24-274 | 18/08/2023 | 18/08/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
16 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT NIJTARAF TW NO- VIII |  |  | BILL/00023/2023-2024 |  | 11/04/2023 | 11/04/2023 | WBSEDCL | 1.51 | 0 | 0 | 0
17 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT NIJTARAF PWSS TW NO -II |  |  | BILL/01438/2023-2024 | BP-2023-24-283 | 21/08/2023 | 21/08/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | PREPARATION OF DPR FOR PWSS UNDER COB DIVN, PHED |  |  | BILL/00684/2022-2023 | BP-734-2022-23 | 06/03/2023 | 06/03/2023 | RADIANT | 3.02 | 0 | 0 | 0
19 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT NIJTARAF TW NO -VIII |  |  | BILL/00095/2023-2024 | BP-2023-24-29 | 28/04/2023 | 28/04/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | FHTC AT PWSS UNDER MTB SUB-DIVN., PHED |  |  | BILL/00685/2022-2023 | BP-744-2022-23 | 06/03/2023 | 06/03/2023 | TISTA LABOUR CO-OP CONT AND CONST SOCIETY LTD | 4.81 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Providing FHTC, Repairing of reservoir and laying new Pipe line and other allied works at in-connection with augmentation NIJTARAF PWSS under Cooch Behar Division, PHED.(Part-D) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000010/2022-2023 | 26/CD | 07/04/2022 | 05/08/2022 | TISTA LABOUR CO-OP CONT AND CONST SOCIETY LTD | 46.52 | 0 | 0 | 1
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Providing FHTC, Construction of pump house, Boundary wall and laying of Pipe line and other allied works at inconnection with augmentation of NIJTARAF PWSS under Cooch Behar Division, PHED. (Part-A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000013/2022-2023 | 29/CD | 07/04/2022 | 05/08/2022 | ASHIM KUMAR CHAKRABORTY | 94.96 | 0 | 0 | 80
23 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of NIJTARAF Piped water supply schemes | SM/10163 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Nijtaraf PWSS, TW no III in the district of CoochBehar under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000052/2023-2024 | 1118/NMD-II | 07/06/2023 | 02/02/2025 | M/S P.P ELECTRICALS | 11.38 | 0 | 0 | 100
Total | [13 empty] | 480.28 | 0 | 0