## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | FHTC |  |  | VCH/001672/2021-2022 | BP_2021_22_489 | 30/03/2022 |  | MS SSB CONSTRUCTION CO | 34.93 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Providing FHTC including Construction of pump house, Boundary wall at 3rd tube well site and laying of UPVC pipe line and other allied works in-connection with augmentation of SALMARA PRATHAM KHANDA PWSS under Cooch Behar Division, PHED.(Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000036/2022-2023 | 94/CD | 18/04/2022 | 16/08/2022 | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 112.32 | 78.66 | 70.04 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Providing functional house hold tap connection 135 nos. in Salmara Pratham Khanda Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000549/2021-2022 | 460/MTB. | 04/03/2022 | 17/07/2022 | ASHIM KUMAR CHAKRABORTY | 4.98 | 4.96 | 99.52 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Providing functional house hold tap connection within command area of Salmara Pratham Khanda Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000156/2022-2023 | 124/MTB | 23/06/2022 | 08/07/2022 | SIBAPADA SINGHA ROY | 4.78 | 1.91 | 39.95 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Providing FHTC and Extn. of Laying of Pipe line at SALMARA PRATHAM KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000225/2022-2023 | 703/CD | 27/08/2022 | 11/10/2022 | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 66.05 | 61.27 | 92.76 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Supply of C.I Specials for SALMARA PRATHAM KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000299/2022-2023 | 900/CD | 22/09/2022 | 22/10/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 9.64 | 9.64 | 100 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Providing functional house hold tap connection within command area of Chakiarchhara Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000081/2022-2023 | 43/MTB | 02/05/2022 | 17/05/2022 | PINAKI SAHA | 4.96 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 1374/CD | 22/12/2022 |  | Resource Division | 47.33 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Providing FHTC, repairing of OHR, and laying of Pipe line including other allied works in-connection with Aug. of SALMARA PRATHAMKHANDA PWSS under Cooch Behar Division, PHED.(Part-B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000328/2022-2023 | 977/CD | 29/09/2022 | 28/11/2022 | M/S. MANDAL CONSTRUCTION | 79.76 | 44.27 | 55.5 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 187/CD | 27/04/2023 |  | Resource Division | 26.04 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | HIRING DISEL BOLERO VEHICLE FOR MTB SUB DIVN.PHED. |  |  | BILL/00631/2022-2023 | BP-752-2022-23 | 06/03/2023 |  | NABIN DEBNATH | 1.1 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT SALMARA PRAHAM KHANDA (AUG) TW NO -III |  |  | BILL/00093/2023-2024 | BP-2023-24-86 | 15/05/2023 |  | WBSEDCL | 1 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Providing FHTC, laying of new Pipe line and repairing of boundarry wall and pump house (H/w & 2nd T/w site) and other allied works in-connection with augmentation of SALMARA PRATHAM KHANDA PWSS under Cooch Behar Division, PHED.(Part-C) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000024/2022-2023 | 40/CD | 07/04/2022 | 22/05/2022 | M/S NARAYAN KR. GHOSH | 70.44 | 61.39 | 87.14 | 90
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Providing FHTC & other allied works at SALMARA PRATHAM KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000306/2022-2023 | 915/CD | 26/09/2022 | 26/10/2022 | SIBAPADA SINGHA ROY | 9.98 | 5.15 | 51.59 | 28
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Sinking of Big Dia Tubewell at Salmara Pratham Khanda PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000182/2022-2023 | 656/CD | 23/08/2022 | 22/10/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 11.68 | 0 | 0 | 100
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | FUEL BILL |  |  | BILL/02059/2023-2024 | BP-1414 | 31/03/2024 |  | R.C BANIK BANIK & SONS | 2.06 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
18 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of SALMARA PRATHAM KHANDA Piped water supply schemes. | SM/10164 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentaion of SALMARA PRATHAM KHANDA water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000701/2023-2024 | 2206/NMD-II | 28/07/2023 | 27/08/2023 | SOUMEN ELECTRIC | 10.89 | 0 | 0 | 70
Total | [13 empty] | 553.63 | 267.24 | 48.27