## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of NAGARERBARI ZONE I & II PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000456/2021-2022 | 1443/CD | 10/03/2022 | 09/04/2022 | MS DD ENTERPRISE | 21.4 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Laying of Pipe line at controllerhat under NAGARERBARI Zone-I PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000402/2021-2022 | 1460/CD | 10/03/2022 | 09/04/2022 | KARTICK CH SEAL | 6.25 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Laying of pipe line at Controllerhat under Nagarerbari Zone-I PWSS under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000390/2022-2023 | 77/SD | 13/05/2022 | 12/06/2022 | KARTICK CH SEAL | 4.93 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Providing FHTC & other allied works at NAGARERBARI Z-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000189/2022-2023 | 663/CD | 23/08/2022 | 22/10/2022 | DIGENDRA CH DEY & SONS | 11.48 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Providing FHTC & other allied works at NAGARERBARI ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000363/2022-2023 | 1016/CD | 29/09/2022 | 29/10/2022 | DIGENDRA CH DEY & SONS | 10.01 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Providing House connection for NAGARERBARI PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000303/2022-2023 | 912/CD | 26/09/2022 | 26/10/2022 | KARTICK CH SEAL | 9.71 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Providing FHTC Laying Of Pipe Line And Construction Of Boundary Wall And Pump House at 3rd Site of NAGARERBARI (ZONE-I) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000199/2022-2023 | 674/CD | 23/08/2022 | 22/10/2022 | GOUTAM KUMAR DAS | 67.9 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2021-2022 | 1591/CD | 24/03/2022 | 24/03/2022 | Resource Division | 5.49 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 487/CD | 07/07/2022 | 07/07/2022 | Resource Division | 36.96 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT NAGARERBARI (REJU) Z-I,PH NO-I |  |  | BILL/00144/2023-2024 | BP-2023-24-132 | 23/05/2023 | 23/05/2023 | WBSEDCL | 1 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT NAGARERBARI (REJU) Z-I,PH NO-II |  |  | BILL/00145/2023-2024 | BP-2023-24-131 | 23/05/2023 | 23/05/2023 | WBSEDCL | 1 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | CONST OF OHR AT RAKHALMARI PWS |  |  | BILL/01039/2023-2024 | BP-483 | 18/09/2023 | 18/09/2023 | S & P ENTERPRISE | 38.41 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Execution of different works (Within the area of LAWCHAPRA) related to NAGARERBARI PWSS under JAL JEEVAN MISSION PART D. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000531/2023-2024 | 326/CD | 09/02/2024 | 09/04/2024 | BIJOY ROY | 33.9 | 0 | 0 | 90
14 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Providing FHTC Laying Of Pipe Line And Construction Of Boundary Wall And Pump House at 3rd Site of NAGARERBARI (ZONE-II) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000204/2022-2023 | 679/CD | 23/08/2022 | 22/10/2022 | RED STAR UNEMPLOYED CO -OPARATIVE LABOUR CON.CONS.S LTD. | 67.1 | 0 | 0 | 100
15 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvination of Nagarerbari water supply scheme, TW no I of Zone-I and TW no I of Zone-II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000033/2023-2024 | 960/NMD-II | 12/05/2023 | 11/06/2023 | SUBODH KUMAR BANIK | 24.92 | 0 | 0 | 100
16 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Execution of different works related to NAHARHAT BANDAR & adjacent of NAGARERBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000513/2023-2024 | 311/CD | 09/02/2024 | 03/02/2025 | GHOSH AND SAHA CONSTRUCTION | 55.81 | 0 | 0 | 30
17 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 1544/CD | 16/08/2024 | 16/08/2024 | Resource Division | 3.1 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Execution of different works related to RAKHALMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000080/2024-2025 | 1188/CD | 18/06/2024 | 11/09/2025 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 32.46 | 0 | 0 | 60
19 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | Execution of different works related to NAGARERBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000595/2023-2024 | 635/CD | 11/03/2024 | 04/07/2025 | GLOCAL FARMS PRIVATE LIMITED | 74.64 | 0 | 0 | 90
20 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000094/2025-2026 | 735/CD | 17/05/2025 | 15/08/2025 | GHOSH AND SAHA CONSTRUCTION | 46.77 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of NAGARERBARI Piped Water Supply Scheme | SM/10219 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000328/2025-2026 | 712/CD | 17/05/2025 | 14/09/2025 | M/S MAHAVIR ENTERPRISE | 7.79 | 0 | 0 | 60
Total | [13 empty] | 561.02 | 0 | 0