## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | Providing F.H.T.C. Connection in the command area at JHAUKUTHI W.S.S. under Tufanganj Sub-Division, PHE Dte. (Part-A) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000459/2021-2022 | 416/TFG | 17/03/2022 | 01/04/2022 | KHOKAN DAS | 4.9 | 4.9 | 100 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | Supply of Sluice valve & C.I Specials as per requisite IS Specification for Augmentation of JHAUKUTHI PWSS under Cooch Behar Division, P.H.E. Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000090/2022-2023 | 298/CD | 31/05/2022 | 15/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.99 | 4.99 | 100 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | Jhawkuthi W/S scheme Near Jhawkuthi B.O.P . Application No. 4002874348 |  |  | VCH/002694/2021-2022 | BP-37/21-22 | 26/03/2022 | 26/03/2022 | WBSEDCL | 0.85 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | Providing FHTC & other allied works at JHAUKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000235/2022-2023 | 719/CD | 27/08/2022 | 11/10/2022 | KHOKAN DAS | 14.27 | 14.27 | 100 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | Providing FHTC, New laying of UPVC/DI Pipe Line & Other allied works at JHAUKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000218/2022-2023 | 707/CD | 27/08/2022 | 11/10/2022 | MATARA CONSTRUCTION CO. | 95.94 | 93.98 | 97.96 | 1
6 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | Supply, delivery,of standby Automatically controlled diaphragm type chlorinator for accurate dosing of chlorine solution at Jhaukuthi Water Supply Scheme ,in the dist of COOCHBEHAR under NMD-II, PHE. Dte Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000788/2022-2023 | 260/NMD-II | 15/02/2023 | 02/03/2023 | ALOK GUHA | 1.8 | 1.8 | 100 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | QUOTATION FOR NSC AT JHAUKUTHI (AUG) Z-I |  |  | BILL/01044/2023-2024 | BP-2023-24-240 | 27/07/2023 | 27/07/2023 | WBSEDCL | 2.75 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | Supply, delivery and fitting fixing of Photovoltiac solar pump controller and other allied work at Jaukuthi water supply scheme, TW No. I in the dist. of Coochbehar under NMD-II, P.H.E Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000661/2022-2023 | 0564/CMSD | 29/07/2022 | 28/08/2022 | DIAMOND ELECTRICAL WORKS | 1.99 | 0 | 0 | 100
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | Execution of different works related to JHAUKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000165/2023-2024 | 942/CD | 04/09/2023 | 03/12/2023 | M/S PRADIP KUMAR PAL | 46.43 | 45.67 | 98.37 | 100
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | Providing FHTC Construction of 250 cum OHR Construction of Pump House & Sinking of Tubewell at JHAUKUTHI PWSS under JAL JEEVAN MISSION (PART ¿A) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000221/2022-2023 | 710/CD | 27/08/2022 | 23/02/2023 | M/S PRADIP KUMAR PAL | 97.76 | 97.53 | 99.76 | 100
11 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Augmentation of JHAUKUTHI water supply scheme, TW no I OF ZONE-I under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000723/2023-2024 | 2235/NMD-II | 28/07/2023 | 27/08/2023 | PRAGATI CONSTRUCTION COMPANY | 9.31 | 9.23 | 99.15 | 100
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | HIRING VEHICLE FO AE/SD |  |  | BILL/01463/2023-2024 | BP-831 | 12/01/2024 | 12/01/2024 | ANIMESH DHAR CHOUDHURY | 0.62 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | FUEL BILL |  |  | BILL/02078/2023-2024 | BP-1418 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 1.87 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | FUEL BILL |  |  | BILL/02029/2023-2024 |  | 01/03/2024 | 01/03/2024 | A.O BSNL | 1.87 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | EXECUTION OF DIFFERENT WORKS (within PHULBARI PART A & BHERBHERI MANABARI area) RELATED TO TAKOAMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000666/2024-2025 | 95/CD | 17/01/2025 | 12/01/2026 | ORIENTAL CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 38.98 | 0 | 0 | 70
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of JHAUKUTHI Piped Water Supply Scheme | SM/10220 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within RAMPUR & JHAUKUTHI ) area BARA KAIMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000597/2024-2025 | 2298/CD | 23/12/2024 | 18/12/2025 | SAMBHU BANIK | 24 | 0 | 0 | 100
Total | [13 empty] | 348.34 | 272.37 | 78.19