## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 1376/CD | 22/12/2022 | 22/12/2022 | Resource Division | 140.76 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | PIPE |  |  | VCH/001702/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 34.38 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | Joining P/line incl Road Crossing withdrawing relaying & other allied works Providing House connection at ANDARAN NIZTARAF PWSS under Cooch Behar Division. PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000062/2021-2022 | 266/CD | 06/08/2021 | 05/10/2021 | DAS ENTERPRISE | 42.23 | 3.76 | 8.9 | 100
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of ANDARAN NIZTARAF PWSS under Cooch Behar Division PHE Dte | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000063/2022-2023 | 260/CD | 24/05/2022 | 08/07/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 12 | 11.83 | 98.61 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 104/CD | 26/04/2023 | 26/04/2023 | Resource Division | 150.8 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | FHTC At PWSS |  |  | BILL/00658/2022-2023 | BP-568-2022-23 | 31/12/2022 | 31/12/2022 | SANKAR BANIK | 4.33 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT ANDARAN NIJTARAF TW NO- VIII |  |  | BILL/00022/2023-2024 |  | 11/04/2023 | 11/04/2023 | WBSEDCL | 1.65 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | FHTC AT PWSS |  |  | BILL/00657/2022-2023 | BP-473-22-23-P | 13/12/2022 | 13/12/2022 | BIJOY ROY | 2.74 | 0 | 0 | 0
9 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT ANDARAN NIJTARAF TW NO -VIII |  |  | BILL/00094/2023-2024 | BP-2023-24-28 | 28/04/2023 | 28/04/2023 | WBSEDCL | 1.16 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | Providing FHTC & Laying of Pipe line Repairing of Boundary wall, Pumphouse & other allied works at ANDARAN NIZTARAF PWSS Under Cooch Behar division P.H.E.Dte. (Part-B) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000402/2022-2023 | 1166/CD | 10/11/2022 | 09/05/2023 | DAS ENTERPRISE | 108.75 | 90.61 | 83.32 | 89
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | Providing FHTC & Laying of Pipe line Construction of Boundary wall, Pumphouse at 3RD site & other allied works at ANDARAN NIZTARAF PWSS Under Cooch Behar division P.H.E.Dte. (Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000401/2022-2023 | 1165/CD | 10/11/2022 | 09/05/2023 | MS SSB CONSTRUCTION CO | 202.97 | 168.73 | 83.13 | 1
12 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | Supply & delivery of different Electrical & Electronics spare parts of PLC based Automatic Panel for attending breakdown maintenance at Andaran Nijtaraf PWSS & adjacent w/s scheme in the district of Coochbehar under Northern Mechanical Division-II P.H.E Dte. |  | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/002288/2023-2024 | 1633/CMSD | 12/03/2024 | 22/03/2024 | M/S SAJAHAN CHOWDHURY | 0.96 | 0 | 0 | 0
13 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Andaran Nijtaraf water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte. APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000809/2022-2023 | 421/NMD-II | 27/02/2023 | 29/03/2023 | SUNLIT | 11.63 | 10.95 | 94.16 | 100
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation works for Providing Functional House Hold Tap Connection ( FHTC) within Commandarea of ANDARAN NIJTARAF Piped water supply schemes. | SM/10221 | Augmentation | Execution of different works related to ANDARAN NIZTARAF PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000024/2023-2024 | 386/CD | 23/05/2023 | 23/07/2025 | DAS ENTERPRISE | 95.16 | 53.4 | 56.12 | 70
Total | [13 empty] | 809.51 | 339.28 | 41.91