## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Constn. of S/Valve chamber / stand post bamboo filling, Earth filling etc. at Lauchapra Zone-I Water Supply Scheme. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000392/2022-2023 | 212/TFG | 05/07/2022 | 04/08/2022 | BIJOY ROY | 3.4 | 3.38 | 99.31 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of LAWCHAPRA ZONE I & II PWSS under Cooch Behar Division PHE Dte | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000503/2021-2022 | 1451/CD | 10/03/2022 | 09/04/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 21.4 | 20.59 | 96.18 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Execution of different works related to LAWCHAPRA Z-2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000445/2022-2023 | 1422/CD | 29/12/2022 | 28/01/2023 | GOUTAM KUMAR DAS | 9.98 | 9.41 | 94.3 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2021-2022 | 1595/CD | 24/03/2022 | 24/03/2022 | Resource Division | 5.49 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 486/CD | 07/07/2022 | 07/07/2022 | Resource Division | 36.94 | 0 | 0 | 0
6 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT LAUCHAPRA PWSS REJU TW NO IV |  |  | BILL/00011/2023-2024 | BP-2023-24-8 | 20/04/2023 | 20/04/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Quotation for new service connection at Lauchapra TG Z-I. Application No- 4003022273 |  |  | BILL/00024/2022-2023 | BP-113/22-23 | 19/12/2022 | 19/12/2022 | WBSEDCL | 0.85 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | UPLOAD CHARGES (MOBILE APPS) |  |  | BILL/00548/2023-2024 | BP-16,29,31-37 | 17/04/2023 | 17/04/2023 | BIPASHA MAHANTA BANIK | 8.86 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at LAWCHAPRA ZONE I W.S.S under Cooch Behar Division P.H.E.Dte | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000069/2022-2023 | 266/CD | 24/05/2022 | 23/07/2022 | NANDALAL SARKAR | 66.81 | 41.29 | 61.8 | 90
10 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Providing FHTC and Laying of Pipe line & Construction of B/Wall 3RD Site of LAUCHAPRA ZONE ¿ I I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000186/2022-2023 | 660/CD | 23/08/2022 | 22/10/2022 | MS BIDYUT SARKAR | 97.11 | 89.79 | 92.46 | 30
11 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Execution of different works related to LAWCHAPRA Z-I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000030/2023-2024 | 380/CD | 23/05/2023 | 22/07/2023 | SUBHAJIT DUTTA | 21.19 | 11 | 51.88 | 43
12 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Execution of different works related to LAWCHAPRA PWSS under JAL JEEVAN MISSION PART B | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000505/2023-2024 | 301/CD | 09/02/2024 | 09/04/2024 | MA MAHAMAYA UNP. CO-OP LABOUR CONT & CONT SOCITY LTD. | 30.53 | 30.27 | 99.12 | 95
13 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Execution of different works related to LAWCHAPRA PWSS under JAL JEEVAN MISSION Z2 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000033/2024-2025 | 1142/CD | 14/06/2024 | 13/08/2024 | MS BIDYUT SARKAR | 92.53 | 0 | 0 | 90
14 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Lawchapra water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000885/2022-2023 | 721/NMD-II | 30/03/2023 | 29/04/2023 | M/S J.K ENGINEERING CO. | 10.81 | 10.79 | 99.78 | 100
15 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvination of Lawchapra water supply scheme, TW no IV under Northern Mechanical Division-II, PHE Dte. APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000663/2023-2024 | 1986/NMD-II | 25/07/2023 | 24/08/2023 | M/S PARITOSH BHOWMICK & CO. | 10.85 | 10.75 | 99 | 100
16 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
17 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Execution of different works related to LAWCHAPRA PWSS under JAL JEEVAN MISSION PART C | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000512/2023-2024 | 310/CD | 09/02/2024 | 07/08/2024 | SENGUPTA ENTERPRISE | 36.89 | 36.41 | 98.69 | 75
18 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within LAUCHAPRA & KOCHABARI area) LAOCHAPRA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000603/2024-2025 | 2304/CD | 23/12/2024 | 22/04/2025 | BIJOY ROY | 52.06 | 0 | 0 | 90
19 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000040/2025-2026 | 676/CD | 14/05/2025 | 10/11/2025 | M/S J C ENTERPRISE | 67.52 | 0 | 0 | 70
20 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000069/2025-2026 | 645/CD | 05/05/2025 | 01/11/2025 | BIJOY ROY | 69.05 | 0 | 0 | 70
21 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000328/2025-2026 | 712/CD | 17/05/2025 | 14/09/2025 | M/S MAHAVIR ENTERPRISE | 7.79 | 0 | 0 | 60
22 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LAUCHAPRA Piped Water Supply Scheme | SM/10231 | Augmentation | Execution of different works related to LAWCHAPRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000056/2024-2025 | 1335/CD | 24/07/2024 | 20/04/2025 | SAMBHU BANIK | 58.32 | 52.38 | 89.82 | 85
Total | [13 empty] | 20498.74 | 316.04 | 1.54