## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KALAPANI Water Supply Scheme | SM/10359 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of Kalpani PWSS under Cooch Behar Division PHE Dte | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000027/2022-2023 | 43/CD | 07/04/2022 | 22/05/2022 | SWAPAN KUMAR ROY | 12.01 | 11.98 | 99.79 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KALAPANI Water Supply Scheme | SM/10359 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at KALAPANI W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000532/2021-2022 | 1632/CD | 29/03/2022 | 28/03/2025 | SIDHARTHA ROY | 35.55 | 20.28 | 57.06 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KALAPANI Water Supply Scheme | SM/10359 | Augmentation | fhtc at pwss |  |  | VCH/000352/2022-2023 | 341 p | 25/10/2022 | 25/10/2022 | NARAYAN CHANDRA BANIK | 0 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KALAPANI Water Supply Scheme | SM/10359 | Augmentation | FHTC |  |  | VCH/001648/2021-2022 | BP-2021_22_472 | 23/03/2022 | 23/03/2022 | SANKAR BANIK | 4.93 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of KALAPANI Water Supply Scheme | SM/10359 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Kalapani PWSS, TW no III in the district of CoochBehar under Northern Mechanical Division-II,PHE Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000734/2022-2023 | 73/NMD-II | 09/01/2023 | 08/02/2023 | B.B CONCERNED | 11.29 | 11.22 | 99.32 | 100
6 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of KALAPANI Water Supply Scheme | SM/10359 | Augmentation | Quotation for new service connection at Kalapani W/SS TW No-III |  |  | BILL/00248/2022-2023 | BP-137/22-23 | 31/01/2023 | 31/01/2023 | WBSEDCL | 0.92 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KALAPANI Water Supply Scheme | SM/10359 | Augmentation | supply of fuel for AE/TFG |  |  | BILL/01083/2024-2025 | BP-220 | 31/07/2024 | 31/07/2024 | ANJALI SERVICE CENTRE | 1.53 | 0 | 0 | 0
Total | [13 empty] | 66.22 | 43.48 | 65.66