## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KUMIRGHAT Water Supply Scheme | SM/10360 | Augmentation | FHTC |  |  | VCH/001683/2021-2022 | BP_2021_22_501 | 31/03/2022 | 31/03/2022 | ANIMESH DHAR CHOUDHURY | 36.93 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KUMIRGHAT Water Supply Scheme | SM/10360 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of KUMIRGHAT PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000499/2021-2022 | 1447/CD | 10/03/2022 | 09/04/2022 | AUXILIARY TUBEWELL DRILLERS | 10.7 | 0 | 0 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of KUMIRGHAT Water Supply Scheme | SM/10360 | Augmentation | QUOTATION FOR NSC AT KUMIRGHAT PH NO -III |  |  | BILL/02193/2023-2024 | BP-2023-24-459 | 07/12/2023 | 07/12/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of KUMIRGHAT Water Supply Scheme | SM/10360 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Kumirghat water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000743/2023-2024 | 2296/NMD-II | 31/07/2023 | 30/08/2023 | THE BANERJEE CONCERN | 11.08 | 0 | 0 | 100
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KUMIRGHAT Water Supply Scheme | SM/10360 | Augmentation | Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under KUMIRGHAT Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. (Part-C) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000633/2024-2025 | 2057/CD | 19/12/2024 | 19/10/2025 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
Total | [13 empty] | 60.74 | 0 | 0