## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BOGDABARI KESAIBARI Water Supply Scheme | SM/10361 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of Bhogdabri Kesiabari PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000028/2022-2023 | 44/CD | 07/04/2022 | 22/05/2022 | MS BIDYUT SARKAR | 12.13 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BOGDABARI KESAIBARI Water Supply Scheme | SM/10361 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at BHOGDABRI KESIABARI W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000538/2021-2022 | 1638/CD | 29/03/2022 | 28/05/2022 | MS BIDYUT SARKAR | 37.54 | 0 | 0 | 99
3 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of BOGDABARI KESAIBARI Water Supply Scheme | SM/10361 | Augmentation | INFRASTRUCTURE DEV COST FOR EFFECTING 01 NOS PHE VIDE APP NO 4003137835 AT BOGDABARI KESHRIBARI |  |  | BILL/01037/2023-2024 | BP-2023-24-246 | 27/07/2023 | 27/07/2023 | WBSEDCL | 3.94 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of BOGDABARI KESAIBARI Water Supply Scheme | SM/10361 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BOGDABARI KESAIBARI TW NO-III |  |  | BILL/00159/2023-2024 | BP-2023-24-136 | 24/05/2023 | 24/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BOGDABARI KESAIBARI Water Supply Scheme | SM/10361 | Augmentation | HIRING OF VEHICLE FOR AE/SADAR |  |  | BILL/00561/2024-2025 | BP-216 | 31/07/2024 | 31/07/2024 | PARAUDDIN MIA | 0.18 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BOGDABARI KESAIBARI Water Supply Scheme | SM/10361 | Augmentation | Execution of different works (WITHIN HARINCHAOWRA & BOGDABARI KESAIBARI AREA) related to JIRANPUR PWSS under JAL JEEVAN MISSION P B | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000679/2024-2025 | 1184/CD | 18/06/2024 | 13/06/2025 | MALAY KR.DEB | 66.85 | 0 | 0 | 35
7 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BOGDABARI KESAIBARI Water Supply Scheme | SM/10361 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000810/2023-2024 | 601/CD | 11/03/2024 | 07/09/2024 | SUBHAS CHANDRA ROY | 5.57 | 0 | 0 | 100
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BOGDABARI KESAIBARI Water Supply Scheme | SM/10361 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000100/2025-2026 | 729/CD | 17/05/2025 | 15/08/2025 | MS BIDYUT SARKAR | 23.91 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BOGDABARI KESAIBARI Water Supply Scheme | SM/10361 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000271/2025-2026 | 743/CD | 17/05/2025 | 15/08/2025 | M/S BADAL CH SAHA | 96.84 | 0 | 0 | 0
Total | [13 empty] | 248.02 | 0 | 0