## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KHAPAIDANGA Water Supply Scheme | SM/10363 | Augmentation | Providing FHTC, Replacing of damaged UPVC pipe line, Culvert crossing damaged due to road Construction & other some allied works related to pipe line at Khapaidanga PWSS under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000054/2022-2023 | 80/SD | 13/05/2022 | 12/06/2022 | BIJOY ROY | 4.08 | 4.08 | 100 | 1
2 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of KHAPAIDANGA Water Supply Scheme | SM/10363 | Augmentation | Supply, delivery of Electro mechanical components at Khapaidanga Water Supply Scheme , in the dist of COOCHBEHAR under NMD-II, PHE. Dte, Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000015/2022-2023 | 601/NMD-II | 05/05/2022 | 04/06/2022 | CINZANO | 8.27 | 8.27 | 100 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KHAPAIDANGA Water Supply Scheme | SM/10363 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at KHAPAIDANGA W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000534/2021-2022 | 1634/CD | 29/03/2022 | 28/05/2022 | BIJOY ROY | 39 | 25.58 | 65.58 | 1
4 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of KHAPAIDANGA Water Supply Scheme | SM/10363 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT KHAPAIDANGA TW NO-III |  |  | BILL/00168/2023-2024 | BP-2023-24-102 | 18/05/2023 |  | WBSEDCL | 1.05 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KHAPAIDANGA Water Supply Scheme | SM/10363 | Augmentation | Providing House Connection of drinking water to the house hold of command Area under KHAPAIDANGA PWSS under Cooch Behar Division, PHED PART - D | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000051/2020-2021 | 1104/CD | 16/10/2020 | 14/01/2021 | BIJOY ROY | 12.17 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KHAPAIDANGA Water Supply Scheme | SM/10363 | Augmentation | Execution of different works related to KHAPAIDANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000329/2023-2024 | 1312/CD | 24/11/2023 | 23/01/2024 | MS DD ENTERPRISE | 9.06 | 4.53 | 49.98 | 100
7 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of KHAPAIDANGA Water Supply Scheme | SM/10363 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Khapaidanga water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000739/2023-2024 | 2269/NMD-II | 31/07/2023 | 30/08/2023 | UTTAM PAUL | 11.07 | 0 | 0 | 60
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of KHAPAIDANGA Water Supply Scheme | SM/10363 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
Total | [13 empty] | 140.41 | 42.45 | 30.24