## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of DEOCHARAI Water Supply Scheme | SM/10364 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at DEOCHARAI W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000542/2021-2022 | 1642/CD | 29/03/2022 | 28/05/2022 | M/S. NITYAGOPAL BANIK | 41.3 | 0 | 0 | 1
2 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of DEOCHARAI Water Supply Scheme | SM/10364 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvination of DEOCHARAI water supply scheme, TW no I under JJM under NMD-II, PHE Dte. APD. |  |  | ORD/000800/2023-2024 | 2382/NMD-II | 09/08/2023 | 08/09/2023 | RAJEEV RANJAN OJHA | 10.87 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of DEOCHARAI Water Supply Scheme | SM/10364 | Augmentation | EXECUTION OF DIFFERENT WORKS AT KLARAYERKUTHI PWSS |  |  | BILL/00684/2023-2024 | BP-356 | 26/07/2023 | 26/07/2023 | GOUTAM KUMAR DAS | 4.81 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of DEOCHARAI Water Supply Scheme | SM/10364 | Augmentation | FUEL BILL |  |  | BILL/02051/2023-2024 | BP-1413 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 1.52 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of DEOCHARAI Water Supply Scheme | SM/10364 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of DEOCHARAI Water Supply Scheme | SM/10364 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of DEOCHARAI PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000509/2021-2022 | 1457/CD | 10/03/2022 | 04/03/2025 | AUXILIARY TUBEWELL DRILLERS | 10.7 | 0 | 0 | 100
Total | [13 empty] | 124.91 | 0 | 0