## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BHANDIJALAS Water Supply Scheme | SM/10365 | Augmentation | Providing F.H.T.C. Earth work filling work of various location at HWS of Bhandijalas PWSS. under Tufanganj Sub-Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000209/2022-2023 | 205/TFG | 05/07/2022 | 04/08/2022 | GOUTAM KUMAR DAS | 4.7 | 1.6 | 34.14 | 1
2 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of BHANDIJALAS Water Supply Scheme | SM/10365 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BHANDIJALAS TW NO I |  |  | BILL/00544/2022-2023 | BP-170/22-23 | 29/03/2023 |  | WBSEDCL | 1.06 | 0 | 0 | 0
3 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of BHANDIJALAS Water Supply Scheme | SM/10365 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvination of BHANDIJALAS water supply scheme, TW no I under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000013/2023-2024 | 874/NMD-II | 28/04/2023 | 28/05/2023 | BEE GEE CONSTRUCTION | 10.86 | 10.19 | 93.82 | 85
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BHANDIJALAS Water Supply Scheme | SM/10365 | Augmentation | Providing F.H.T.C. Connection of Footh path drain & other allied works related to pipe line at HWS of Bhandijalas PWSS. under Tufanganj Sub-Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000207/2022-2023 | 207/TFG | 05/07/2022 | 04/08/2022 | GOUTAM KUMAR DAS | 4.17 | 0.08 | 1.87 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BHANDIJALAS Water Supply Scheme | SM/10365 | Augmentation | Execution of different works related to A. FULBARI AREA at BHANDIJALAS PWSS under JAL JEEVAN MISSION PART K | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000326/2023-2024 | 1309/CD | 24/11/2023 | 23/01/2024 | UTTAM SAHA | 4.52 | 0 | 0 | 100
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BHANDIJALAS Water Supply Scheme | SM/10365 | Augmentation | Providing F.H.T.C. Earth filling, new construction of Footh path & other allied works related to pipe line at 2nd & 3rd site of Bhandijalas PWSS. under Tufanganj Sub-Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000208/2022-2023 | 206/TFG | 05/07/2022 | 04/08/2022 | GOUTAM KUMAR DAS | 4.67 | 2.01 | 43.09 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BHANDIJALAS Water Supply Scheme | SM/10365 | Augmentation | Execution of different works related to A. FULBARI AREA at BHANDIJALAS PWSS under JAL JEEVAN MISSION PART L | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000327/2023-2024 | 1310/CD | 24/11/2023 | 23/01/2024 | GOUTAM KUMAR DAS | 4.65 | 0 | 0 | 100
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BHANDIJALAS Water Supply Scheme | SM/10365 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at BHANDIJALAS W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000529/2021-2022 | 1629/CD | 29/03/2022 | 28/05/2022 | GOUTAM KUMAR DAS | 49.5 | 36.57 | 73.88 | 100
Total | [13 empty] | 84.14 | 50.46 | 59.97