## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of CHHAGALBER Water Supply Scheme | SM/10366 | Augmentation | Providing House connection for CHHAGALBER PWSS under Cooch Behar Division. PHE Dte | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000258/2022-2023 | 748/CD | 29/08/2022 | 13/10/2022 | NARAYAN CHANDRA BANIK | 9.96 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of CHHAGALBER Water Supply Scheme | SM/10366 | Augmentation | Providing FHTC & other allied works at CHAGALBER PWSS under JAL JEEVAN MISSIO | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000358/2022-2023 | 1011/CD | 29/09/2022 | 29/10/2022 | NARAYAN CHANDRA BANIK | 9.97 | 0 | 0 | 95
3 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of CHHAGALBER Water Supply Scheme | SM/10366 | Augmentation | Quotation for new service connection at Chhagalber TW No III |  |  | BILL/00451/2022-2023 | BP-143/22-23 | 23/02/2023 | 23/02/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of CHHAGALBER Water Supply Scheme | SM/10366 | Augmentation | Execution of different works related to CHHAGALBER PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000048/2023-2024 | 409/CD | 23/05/2023 | 20/10/2023 | NARAYAN CHANDRA BANIK | 60.18 | 0 | 0 | 99
5 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of CHHAGALBER Water Supply Scheme | SM/10366 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVINATION of CHHAGALBER PWSS, TW no .III in the district of Coochbehar under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000824/2022-2023 | 468/NMD-II | 01/03/2023 | 31/03/2023 | MASSK ENGINEERING WORKS | 11.24 | 0 | 0 | 100
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of CHHAGALBER Water Supply Scheme | SM/10366 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000275/2025-2026 | 739/CD | 17/05/2025 | 12/05/2026 | DAS ENTERPRISE | 37.76 | 0 | 0 | 70
Total | [13 empty] | 130.16 | 0 | 0