## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PUTIMARI PHULESWARI Water Supply Scheme | SM/10367 | Augmentation | FHTC |  |  | VCH/001667/2021-2022 | BP_2021_22_486 | 30/03/2022 |  | SIDHARTHA ROY | 10.52 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PUTIMARI PHULESWARI Water Supply Scheme | SM/10367 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of Putimari Fuleswari PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000029/2022-2023 | 45/CD | 07/04/2022 | 22/05/2022 | GHOSH AND SAHA CONSTRUCTION | 12.13 | 8.87 | 73.15 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PUTIMARI PHULESWARI Water Supply Scheme | SM/10367 | Augmentation | FHTC AT PUPTIMARI PHULESWARI PWSS |  |  | VCH/001043/2022-2023 | 435 | 30/11/2022 |  | GHOSH AND SAHA CONSTRUCTION | 31.03 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of PUTIMARI PHULESWARI Water Supply Scheme | SM/10367 | Augmentation | Quotation for new service connection at Putimari fuleswari TW No-III |  |  | BILL/00011/2022-2023 | BP-100/22-23 | 08/12/2022 |  | WBSEDCL | 0.85 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of PUTIMARI PHULESWARI Water Supply Scheme | SM/10367 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Putimari Fuleswari water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000845/2022-2023 | 602/NMD-II | 20/03/2023 | 19/04/2023 | SANJIB SAHA | 11.02 | 7.42 | 67.3 | 100
Total | [13 empty] | 65.56 | 16.29 | 24.85