## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of Panisala PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000030/2022-2023 | 46/CD | 07/04/2022 | 22/05/2022 | MATARA CONSTRUCTION CO. | 12.13 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | FHTC |  |  | VCH/000084/2022-2023 | BP_22_23_55 | 28/04/2022 | 28/04/2022 | SHYAMAL NATH | 1.85 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | PIPE |  |  | VCH/001704/2021-2022 | BP_2021_22_415 | 04/03/2022 | 04/03/2022 | EXECUTIVE ENGINEER RESOURCES DIVISION P.H.E.DTE. | 1.97 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | fhtc |  |  | VCH/001595/2021-2022 | BP-2021-22-417 | 11/03/2022 | 11/03/2022 | ASHIM KUMAR CHAKRABORTY | 4.99 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | FHTC |  |  | VCH/000039/2022-2023 | BP_22_23_13 | 13/04/2022 | 13/04/2022 | MATARA CONSTRUCTION CO. | 11.32 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of SSPOST at PANISALA W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000530/2021-2022 | 1630/CD | 29/03/2022 | 28/05/2022 | GOUTAM KUMAR DAS | 10.8 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | Providing FHTC & other allied works at PANISALA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000222/2022-2023 | 711/CD | 27/08/2022 | 11/10/2022 | GOUTAM KUMAR DAS | 17.51 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | Providing FHTC Rising main of Pipe line at PANISALA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000352/2022-2023 | 1005/ CD | 29/09/2022 | 29/10/2022 | GOUTAM KUMAR DAS | 38.82 | 0 | 0 | 81
9 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Panisala PWSS, TW no III in the district of CoochBehar under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000842/2022-2023 | 578/NMD-II | 17/03/2023 | 16/04/2023 | M/S BHOWMIK & CO. | 11.32 | 0 | 0 | 80
10 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | Supply, delivery,of standby Automatically controlled diaphragm type chlorinator for accurate dosing of chlorine solution at Panisala Water Supply Scheme ,in the dist of CoochBehar under NMD-II,PHE.Dte Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000797/2022-2023 | 277/NMD-II | 16/02/2023 | 03/03/2023 | SOUMEN ELECTRIC | 1.8 | 0 | 0 | 100
11 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT PANISALA PWSS TW NO III |  |  | BILL/00531/2022-2023 | BP-154/22-23 | 17/03/2023 | 17/03/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PANISALA Water Supply Scheme | SM/10368 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at PANISALA W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000528/2021-2022 | 1628/CD | 29/03/2022 | 28/05/2022 | GOUTAM KUMAR DAS | 56.15 | 0 | 0 | 1
Total | [13 empty] | 169.67 | 0 | 0