## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of MARICHBARI Water Supply Scheme | SM/10369 | Augmentation | Sinking of 250mm x 200 mm Big dia. Tube well with UPVC Pipes & Strainer at 3rd Site of MARICHBARI PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000500/2021-2022 | 1448/CD | 10/03/2022 | 09/04/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 10.7 | 0 | 0 | 100
2 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of MARICHBARI Water Supply Scheme | SM/10369 | Augmentation | QUOTATION FOR NSC AT MARICHBARI PH NO III |  |  | BILL/01018/2023-2024 | BP-2023-24-225 | 24/07/2023 | 24/07/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of MARICHBARI Water Supply Scheme | SM/10369 | Augmentation | Providing FHTC Works, Laying of pipe line Constructions of 3rd site Pump House, Boundary Wall at MARICHBARI W.S.S under Cooch Behar Division P.H.E.Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000539/2021-2022 | 1639/CD | 29/03/2022 | 28/05/2022 | MATARA CONSTRUCTION CO. | 55.7 | 0 | 0 | 100
4 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of MARICHBARI Water Supply Scheme | SM/10369 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Marichbari water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000679/2023-2024 | 2027/NMD-II | 26/07/2023 | 01/04/2024 | SARKAR ELECTRIC | 11.08 | 0 | 0 | 100
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of MARICHBARI Water Supply Scheme | SM/10369 | Augmentation | FHTC AT KUCHLIBARI ZONR -I |  |  | BILL/01210/2023-2024 | BP-724-P2 | 08/11/2023 | 08/11/2023 | M/S PALIT ENTERPRISE | 15 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of MARICHBARI Water Supply Scheme | SM/10369 | Augmentation | FUEL BILL |  |  | BILL/02054/2023-2024 | BP-1408 | 31/03/2024 | 31/03/2024 | R.C BANIK BANIK & SONS | 1.78 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of MARICHBARI Water Supply Scheme | SM/10369 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of MARICHBARI Water Supply Scheme | SM/10369 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within MARICHBARI, KHATERBARI & BALASI area) BHANGAMORE PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000651/2024-2025 | 2330/CD | 23/12/2024 | 21/02/2025 | SUPRITI ENTERPRISE | 89.52 | 0 | 0 | 0
Total | [13 empty] | 240.54 | 0 | 0