## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PAKHIHAGA Water Supply Scheme | SM/10707 | Augmentation | Laying of Pipe Line & other allied work related to F.H.T.C. under JJM Programme for PAKHIHAGA PWSS under Cooch Behar Division. PHE Dte. PART A |  |  | ORD/000014/2021-2022 | 138/CD | 06/07/2021 | 04/10/2021 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 22.12 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PAKHIHAGA Water Supply Scheme | SM/10707 | Augmentation | Pipe Line in the Command area incl. Providing House connection at PAKHIHAGA PWSS under Cooch Behar Division. PHE Dte. PART - B |  |  | ORD/000126/2021-2022 | 301/CD | 13/08/2021 | 27/09/2021 | SWAPAN SAHA | 29.52 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PAKHIHAGA Water Supply Scheme | SM/10707 | Augmentation | Providing functional house hold tap connection within command area under PAKHIHAGA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000122/2022-2023 | 125/MTB | 23/06/2022 | 20/11/2022 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 4.78 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PAKHIHAGA Water Supply Scheme | SM/10707 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at PAKHIHAGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000341/2022-2023 | 994/CD | 29/09/2022 | 29/10/2022 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 18.38 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PAKHIHAGA Water Supply Scheme | SM/10707 | Augmentation | Providing FHTC Laying of Pipe line incl rising main at 3rd Site at REJ. of PAKHIHAGA PWSS under JAL JEEVAN MISSION (PART ¿B) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000183/2022-2023 | 657/CD | 23/08/2022 | 22/10/2022 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 40.78 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PAKHIHAGA Water Supply Scheme | SM/10707 | Augmentation | Sinking of Big Dia Tubewell at 4TH Site of PAKHIHAGA HAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000193/2022-2023 | 668/CD | 23/08/2022 | 22/10/2022 | MS DD ENTERPRISE | 11.68 | 0 | 0 | 1
7 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of PAKHIHAGA Water Supply Scheme | SM/10707 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Pakhihaga water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000761/2022-2023 | 184/NMD-II | 19/01/2023 | 18/02/2023 | M/S ANJALI ENTERPRISE | 11.07 | 0 | 0 | 90
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of PAKHIHAGA Water Supply Scheme | SM/10707 | Augmentation | FHTC AND OTHER ALLIED WORKS AT PWSS |  |  | BILL/00655/2022-2023 | BP-514-22-23-P | 16/12/2022 | 16/12/2022 | MS SSB CONSTRUCTION CO | 0.87 | 0 | 0 | 0
9 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of PAKHIHAGA Water Supply Scheme | SM/10707 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT PAKHIHAGA PH NO-II |  |  | BILL/00538/2022-2023 | BP-157/22-23 | 17/03/2023 | 17/03/2023 | WBSEDCL | 0.7 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of PAKHIHAGA Water Supply Scheme | SM/10707 | Augmentation | Supply & delivery of Submersible pump motor set and other Electro Mechanical Componenets at PAKHIHAGA (REJU) PWSS and adjacent W/S Scheme in the district of Coochbehar under Northern Mechanical Division-II P.H.E Dte. |  | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000040/2024-2025 | 1932/CMSD | 13/06/2024 | 01/04/2025 | B.B CONCERNED | 4.54 | 0 | 0 | 100
Total | [13 empty] | 144.45 | 0 | 0