## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of UTTAR FULKARDABRI Water Supply Scheme | SM/10708 | Augmentation | Providing FHTC and Laying of Pipe line at UTTAR FULKADABRI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000405/2021-2022 | 1463/CD | 10/03/2022 | 09/04/2022 | SHIBA ENTERPRISE | 37.85 | 31.63 | 83.57 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of UTTAR FULKARDABRI Water Supply Scheme | SM/10708 | Augmentation | Shifting of Pipe line due to construction of Bridge over the Saniajan at Bagdogra & approach Rd at UTTAR FULKADABRI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000406/2021-2022 | 1464/CD | 10/03/2022 | 09/04/2022 | SHIBA ENTERPRISE | 31.28 | 21.26 | 67.96 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of UTTAR FULKARDABRI Water Supply Scheme | SM/10708 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Uttar Fulkardabri water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar |  |  | ORD/001140/2023-2024 | 2875/NMD-II | 17/10/2023 | 16/11/2023 | INDRANI ENTERPRISE | 11.08 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of UTTAR FULKARDABRI Water Supply Scheme | SM/10708 | Augmentation | Execution of different works related to UTTAR FULKADABRI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000772/2022-2023 | 1659/CD | 10/02/2023 | 11/04/2023 | PARITOSH PANDIT | 85.21 | 69.14 | 81.14 | 67
Total | [13 empty] | 165.42 | 122.03 | 73.77