## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | Providing FHTC and Laying of Pipe line at JAMALDAH PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000412/2021-2022 | 1470/CD | 10/03/2022 | 09/04/2022 | MS SURAJIT MAJUMDER | 28.88 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | Providing FHTC and Laying of pipe line, Const. Of Pump house , B/Wall at 4th T/W site and other allied work of JAMALDAH HAT PWSS under JAL JEEVAN MISSION (PART ¿A) | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000331/2022-2023 | 980/CD | 29/09/2022 | 28/11/2022 | MS SURAJIT MAJUMDER | 61.14 | 58.7 | 96.01 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | Providing FHTC & other allied works at JAMALDAH PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000282/2022-2023 | 889/CD | 22/09/2022 | 22/10/2022 | MS SURAJIT MAJUMDER | 9.98 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | Laying of Additional boosting line for FHTC under BURABURI PWSS under Cooch Behar Division PHE Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000067/2022-2023 | 264/CD | 24/05/2022 | 08/07/2022 | PARITOSH PANDIT | 11.73 | 11.46 | 97.62 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | Sinking of Big Dia Tubewell at 4TH Site of JAMALDAH HAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000194/2022-2023 | 669/CD | 23/08/2022 | 22/10/2022 | MS DD ENTERPRISE | 11.68 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | Sinking of Big Dia Tubewell at 4TH Site of JAMALDAH HAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000409/2022-2023 | 669/CD. | 24/08/2022 | 23/10/2022 | MS DD ENTERPRISE | 11.68 | 11.68 | 100.01 | 1
7 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of JAMALDAHA water supply scheme, TW no IV under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000858/2022-2023 | 654/NMD-II | 24/03/2023 | 23/04/2023 | MITRA ENTERPRISE | 10.73 | 10.6 | 98.78 | 80
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | Execution of different works related to JAMALDAH PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000132/2023-2024 | 728/CD | 26/07/2023 | 24/09/2023 | MS SURAJIT MAJUMDER | 11.78 | 11.78 | 99.98 | 100
9 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | Execution of different works related to JAMALDAH HAT (Bhogramguri Adj. Area) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000028/2023-2024 | 382/CD | 23/05/2023 | 22/07/2023 | NORTH BENGAL CONSTRUCTION CO | 14.78 | 3.97 | 26.86 | 61
10 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT JAMALDAHAT (AUG) PH NO-IV |  |  | BILL/00539/2022-2023 | BP-158/22-23 | 17/03/2023 | 17/03/2023 | WBSEDCL | 0.72 | 0 | 0 | 0
11 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | Supply & delivery of Submersible pump motor set and other Electro Mechanical Componenets at JAMALDAHA (REJU) PWSS and adjacent W/S Scheme in the district of Coochbehar under Northern Mechanical Division-II P.H.E Dte. |  | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000043/2024-2025 | 1934/CMSD | 13/06/2024 | 27/03/2025 | ALPHA ENTERPRISE | 4.55 | 0 | 0 | 70
12 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | supply of ci special at jamaldahat pwss |  |  | BILL/02041/2023-2024 |  | 01/03/2024 | 01/03/2024 | A.O BSNL | 9.66 | 0 | 0 | 0
13 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of JAMALDAH HAT Water Supply Scheme | SM/10709 | Augmentation | SUPPLY OF CI SPECIAL AT JAMALDAHAT PWSS |  |  | BILL/01999/2023-2024 |  | 30/03/2024 | 30/03/2024 | PALLAB BHAWAL | 9.66 | 0 | 0 | 0
Total | [13 empty] | 196.98 | 108.19 | 54.92