## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | Providing FHTC and Laying of Pipe line at RAMTHENGA PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000414/2021-2022 | 1472/CD | 10/03/2022 | 09/04/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 31.89 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 1367/CD | 22/12/2022 | 22/12/2022 | Resource Division | 67.41 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | FHTC RAMTHENGA |  |  | VCH/000408/2022-2023 | BP-22-23-144 | 26/07/2022 | 26/07/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.96 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | hiring vechile |  |  | VCH/000668/2022-2023 | BP-22-23-227 | 29/08/2022 | 29/08/2022 | AJAD HOSSAIN | 0.2 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | hiring vechicle |  |  | VCH/000667/2022-2023 | BP-22-23-226 | 29/08/2022 | 29/08/2022 | PARAUDDIN MIAH | 0.62 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 183/CD | 27/04/2023 | 27/04/2023 | Resource Division | 29.74 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT RAMTHENGA (REJU) TW NO-III |  |  | BILL/00088/2023-2024 | BP-2023-24-93 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | Sinking of Big Dia Tubewell at 3RD Site of RAMTHENGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000192/2022-2023 | 667/CD | 23/08/2022 | 22/10/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 11.68 | 0 | 0 | 100
9 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | Providing FHTC & Construction of Boundary wall, Pumphouse at 3rd site and laying of Pipe line and other allied works at Rej. of RAMTHENGA PWSS under JAL JEEVAN MISSION (Part-A) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000195/2022-2023 | 670/CD | 23/08/2022 | 22/10/2022 | KAJAL KUMAR DE | 65.92 | 0 | 0 | 38
10 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO RAMTHANGA PANIGRAM BARAIBARI PWSS UNDER JAL JEEVAN MISSION. MTB |  |  | ORD/000539/2024-2025 | 2223/CD | 23/12/2024 | 21/02/2025 | SHREE RANI SATI ENTERPRISE | 41.72 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO RAMTHANGA GHOKSADANGA SALMARA PRATHAM KHANDA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000528/2024-2025 | 2212/CD | 23/12/2024 | 21/02/2025 | SUBHAS CHANDRA ROY | 60.24 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of RAMTHANGA Water Supply Scheme | SM/10710 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvination Of Ramthenga water supply scheme, TW no III of under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000798/2023-2024 | 2372/NMD-II | 08/08/2023 | 07/09/2023 | SANJIB SAHA | 10.66 | 0 | 0 | 100
Total | [13 empty] | 326.1 | 0 | 0