## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of CHUNGERKHATA KHAGRIBARI Water Supply Scheme | SM/10711 | Augmentation | Providing FHTC and Laying of Pipe line at CHONGERKHATA KHAGRIBARI PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000413/2021-2022 | 1471/CD | 10/03/2022 | 09/04/2022 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 30.24 | 15.54 | 51.39 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of CHUNGERKHATA KHAGRIBARI Water Supply Scheme | SM/10711 | Augmentation | ELECTRICITY PAYMENT CHONGER KATHA KHAGRIBARI PWSS |  |  | BILL/00555/2023-2024 | BP-192 | 05/06/2023 |  | WBSEDCL | 4.66 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of CHUNGERKHATA KHAGRIBARI Water Supply Scheme | SM/10711 | Augmentation | Execution of different works related to CHONGERKHATA KHAGRIBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000549/2022-2023 | 1683/CD | 13/02/2023 | 13/07/2023 | BIJOY ROY | 92.22 | 42.59 | 46.18 | 95
Total | [13 empty] | 127.12 | 58.13 | 45.73