## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of BHANGA MORE Water Supply Scheme | SM/10712 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT BHANGAMORE (REJU) PWSS PH NO-II |  |  | BILL/00083/2023-2024 | BP-2023-24-78 | 15/05/2023 |  | WBSEDCL | 1.18 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of BHANGA MORE Water Supply Scheme | SM/10712 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvination of BHANGA MORE water supply scheme, TW no I under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000105/2023-2024 | 1317/NMD-II | 11/07/2023 | 10/08/2023 | M/S A.D. ENTERPRISE | 10.5 | 4.37 | 41.59 | 40
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BHANGA MORE Water Supply Scheme | SM/10712 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of BHANGA MORE Water Supply Scheme | SM/10712 | Augmentation | Execution of different works related to BHANGAMORE PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000548/2022-2023 | 1682/CD | 13/02/2023 | 13/07/2023 | NABIN DEBNATH | 93.36 | 31.59 | 33.84 | 95
Total | [13 empty] | 19894.33 | 35.96 | 0.18