## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of LOTAPOTA Water Supply Scheme | SM/10713 | Augmentation | Supply, delivery,of standby Automatically controlled diaphragm type chlorinator for accurate dosing of chlorine solution at Lotapota Water Supply Scheme ,in the dist of Coochbehar under NMD-II,PHE.Dte Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000006/2023-2024 | 782/NMD-II | 06/04/2023 | 21/04/2023 | SUNLIT | 1.8 | 1.8 | 100 | 100
2 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of LOTAPOTA Water Supply Scheme | SM/10713 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONECTION AT LOTAPOTA (REJU) PWSS TW NO. III. |  |  | BILL/00194/2024-2025 | BP-49/24-25 | 29/04/2024 | 29/04/2024 | WBSEDCL | 7.16 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LOTAPOTA Water Supply Scheme | SM/10713 | Augmentation | Execution of different works related to LOTAPOTA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000025/2023-2024 | 385/CD | 23/05/2023 | 24/04/2025 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 71.59 | 23.06 | 32.21 | 32
4 | COOCHBEHAR |  | Northern Mechanical Division II | Rejuvenation of LOTAPOTA Water Supply Scheme | SM/10713 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Rejuvenation of Lotapota water supply scheme, TW no III under Northern Mechanical Division-II, PHE Dte.Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000671/2023-2024 | 2052/NMD-II | 26/07/2023 | 01/04/2025 | SUDIP DUTTA | 11.06 | 6.17 | 55.75 | 80
5 | COOCHBEHAR |  | Coochbehar Division | Rejuvenation of LOTAPOTA Water Supply Scheme | SM/10713 | Augmentation | Restoration of Pipe line broken due to storm & Providing FHTC & other allied works at LOTAPOTA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000346/2022-2023 | 999/CD | 29/09/2022 | 30/08/2025 | MATARA CONSTRUCTION CO. | 3.24 | 0 | 0 | 90
Total | [13 empty] | 94.85 | 31.03 | 32.71