## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Resource | Engagement of Implementation Support Angency (ISA) for implementation of Community mobilization and capacity building activities under Jal Jeevan Mission (JJM) support Activities at Coochbehar District. | SM/11270 | Support-IEC | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Coochbehar District. |  | Junior Engineer | ORD/000527/2022-2023 | 4687/RS | 17/08/2022 | 17/08/2023 | DAKSHIN RANGALIBAZNA WELFARE ASSOCIATION | 174.4 | 174.26 | 99.92 | 100
2 | COOCHBEHAR |  | Coochbehar Division | Engagement of Implementation Support Angency (ISA) for implementation of Community mobilization and capacity building activities under Jal Jeevan Mission (JJM) support Activities at Coochbehar District. | SM/11270 | Support-IEC | Providing necessary furniture¿s etc. for Water testing LAB/ DPMU/ ISA setup under Cooch Behar Division in connection with implementation of Jal Jeevan Mission in West Bengal. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000426/2022-2023 | 1086/CD | 18/10/2022 | 02/11/2022 | JAINCO TRADERS | 9.91 | 9.91 | 100 | 0
Total | [13 empty] | 184.31 | 184.17 | 99.92