## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Hiring of Diesel Vehicle of Bolero for the Office use of Office use of Assistant Engineer, (H.Q) under office of the Executive Engineer, Cooch Behar Division, PHE Dte. for 12 Months (October 2021 to September 2022) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000167/2021-2022 | 528/CD (2) | 30/09/2021 | 12/10/2021 | NIRANJAN KIRTANIA | 2.02 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing FHTC & Laying of Pipe line and other allied works at RAMPUR ZONE ¿ I PWSS under Cooch Behar Division, PHED (PART ¿B) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000175/2022-2023 | 647/CD | 22/08/2022 | 06/10/2022 | HARIDAS GHOSH | 101.52 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing FHTC & Laying of Pipe line and other allied works at RAMPUR ZONE ¿ I I PWSS under Cooch Behar Division, PHED (PART ¿B) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000176/2022-2023 | 648/CD | 22/08/2022 | 06/10/2022 | GOUTAM KUMAR DAS | 101.17 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing F.H.T.C. Connection in the command area at RAMPUR ZONE-I W.S.S. under Tufanganj Sub-Division, PHE Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000142/2022-2023 | 209/TFG | 05/07/2022 | 04/08/2022 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 4.01 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing FHTC & other allied works at RAMPUR ZI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000377/2022-2023 | 1031/CD | 29/09/2022 | 29/10/2022 | GOUTAM KUMAR DAS | 10.02 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | New laying of Pipe Line, Providing F.H.T.C. & Other allied works at (Part-C9) RAMPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000347/2022-2023 | 1000/CD | 29/09/2022 | 28/11/2022 | PRAPTI DUTTA | 12.28 | 0 | 0 | 1
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing FHTC & other allied works at RAMPUR ZII PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000376/2022-2023 | 1030/CD | 29/09/2022 | 29/10/2022 | GOUTAM KUMAR DAS | 9.98 | 0 | 0 | 1
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing FHTC & Laying of Pipe line and other allied works at RAMPUR ZONE ¿ I PWSS under Cooch Behar Division, PHED (PART ¿D) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000174/2022-2023 | 646/CD | 22/08/2022 | 06/10/2022 | UTPAL CHAKRABORTY | 60.32 | 0 | 0 | 1
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing FHTC & Laying of Pipe line and other allied works at RAMPUR ZONE ¿ I PWSS under Cooch Behar Division, PHED (PART ¿C) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000177/2022-2023 | 649/CD | 22/08/2022 | 06/10/2022 | GOUTAM KUMAR DAS | 101.11 | 0 | 0 | 1
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing FHTC Construction of 450 cum OHR and Laying of Pipe line Construction of Pump House & B/Wall Sinking of Tubewell at 3rd Site of RAMPUR ZONE ¿ I PWSS under JAL JEEVAN MISSION (PART ¿A) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000179/2022-2023 | 651/CD | 22/08/2022 | 18/02/2023 | TAPAN CHANDA | 298.11 | 0 | 0 | 1
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing FHTC Construction of 450 cum OHR and Laying of Pipe line Construction of Pump House & B/Wall Sinking of Tubewell at 3rd Site of RAMPUR ZONE ¿ I I PWSS under JAL JEEVAN MISSION (PART ¿A) | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000178/2022-2023 | 650/CD | 22/08/2022 | 18/02/2023 | TAPAN CHANDA | 298.81 | 0 | 0 | 21
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing FHTC & other allied works at RAMPUR ZONE ? I & II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000422/2022-2023 | 1280/CD | 02/12/2022 | 31/01/2023 | AKANSHA COMMERCIAL PVT LTD | 89.88 | 0 | 0 | 1
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing FHTC Bridge Culvert Crossing of Pipe line at RAMPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000350/2022-2023 | 1003/CD | 29/09/2022 | 29/10/2022 | PARITOSH DUTTA | 29.99 | 0 | 0 | 1
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Providing FHTC Rising main of Pipe line at RAMPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000353/2022-2023 | 1006/CD | 29/09/2022 | 29/10/2022 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 28.99 | 0 | 0 | 1
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | FHTC RAMPUR (CHHAT) PWSS |  |  | VCH/001001/2022-2023 | 359 | 23/10/2022 | 23/10/2022 | GHOSH AND SAHA CONSTRUCTION | 0.9 | 0 | 0 | 0
16 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Charges for load enhancement at rampur pwss. P/H-III |  |  | BILL/02055/2023-2024 | BP-2023-24-428 | 05/12/2023 | 05/12/2023 | WBSEDCL | 0.79 | 0 | 0 | 0
17 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Quotation for new service connection at Rampur TW No VI |  |  | BILL/00450/2022-2023 | BP-141/22-23 | 23/02/2023 | 23/02/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | PURCHASE OF FUEL UNDER COB DIVN. PHED |  |  | VCH/001019/2022-2023 | 333 | 17/10/2022 | 17/10/2022 | SUCHITRO FUEL STATION | 0.3 | 0 | 0 | 0
19 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Quotation for new service connection at rampur TW No VIII |  |  | BILL/00449/2022-2023 | BP-142/22-23 | 23/02/2023 | 23/02/2023 | WBSEDCL | 1.01 | 0 | 0 | 0
20 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Charges for Load enhancement at Rampur PWSS, P/H-I |  |  | BILL/02053/2023-2024 | BP-2023-24-426 | 05/12/2023 | 05/12/2023 | WBSEDCL | 0.91 | 0 | 0 | 0
21 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Balance portion Pipe line, Rising & Delivery line & other allied work related to pipe line at RAMPUR ZONE I & II WSS under Tufanganj Sub- Division, Cooch Behar Divn., P.H.E Dte. Under JJM Programme. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000018/2023-2024 | 369/CD | 23/05/2023 | 20/10/2023 | TAPAN CHANDA | 72.87 | 0 | 0 | 98
22 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Execution of different works related to RAMPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000412/2023-2024 | 1315/CD | 24/11/2023 | 23/01/2024 | GOUTAM KUMAR DAS | 4.32 | 0 | 0 | 90
23 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO RAMPUR PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000547/2024-2025 | 2232/CD | 23/12/2024 | 21/02/2025 | AMBITIOUS ENTERPRISE | 97.03 | 0 | 0 | 0
24 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Rampur water supply scheme, TW no VII and VIII under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000886/2022-2023 | 726/NMD-II | 30/03/2023 | 29/04/2023 | GEETA CONSTRUCTION | 21.71 | 0 | 0 | 100
25 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | PROVIDING FHTC AT JIRANPUR PWSS |  |  | BILL/02045/2023-2024 | BP-1227-P2 | 22/03/2024 | 22/03/2024 | MALAY KR.DEB | 2 | 0 | 0 | 0
26 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | EXECUTION OF DIFFERENT WORK AT NIZTARAF PWSS |  |  | BILL/01993/2023-2024 | BP-1350-P2 | 30/03/2024 | 30/03/2024 | TORSHA CONSTRUCTION | 0 | 0 | 0 | 0
27 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
28 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | Execution of different works related to RAMPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000372/2023-2024 | 1357/CD | 05/12/2023 | 24/11/2025 | KARTICK CH SEAL | 95.75 | 0 | 0 | 75
29 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within RAMPUR & JHAUKUTHI ) area BARA KAIMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000597/2024-2025 | 2298/CD | 23/12/2024 | 18/12/2025 | SAMBHU BANIK | 24 | 0 | 0 | 100
30 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within RAMPUR area) NAJIRAN DEUTIKHATA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000606/2024-2025 | 2307/CD | 23/12/2024 | 21/02/2025 | UTPAL CHAKRABORTY | 76.27 | 0 | 0 | 0
31 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED (WITHIN AUG. RAMPUR AREA) TO Tufanganj 2 PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000008/2025-2026 | 601/CD | 28/04/2025 | 25/10/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 60
32 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000001/2025-2026 | 707/CD | 17/05/2025 | 15/08/2025 | M/S MAA MANASA CONSTRUCTION CO. | 24.21 | 0 | 0 | 0
33 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000007/2025-2026 | 600/CD | 28/04/2025 | 25/10/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 60
34 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000073/2025-2026 | 788/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 75.53 | 0 | 0 | 0
35 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000080/2025-2026 | 784/CD | 23/05/2025 | 21/08/2025 | GOUTAM KUMAR DAS | 92.33 | 0 | 0 | 0
36 | COOCHBEHAR |  | Coochbehar Division | Augmentation of RAMPUR Piped Water Supply Scheme | SM/11272 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000255/2025-2026 | 765/CD | 17/05/2025 | 13/11/2025 | BIJOY ROY | 40.21 | 0 | 0 | 100
Total | [13 empty] | 2028.69 | 0 | 0