## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 159/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.33 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | New service connection at Naharhat bandar pwss |  |  | BILL/02147/2023-2024 | BP-2023-24-480 | 12/12/2023 | 12/12/2023 | WBSEDCL | 13.46 | 0 | 0 | 0
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | New service connection at Naharhat bandar pwss |  |  | BILL/02148/2023-2024 | BP-2023-24-481 | 12/12/2023 | 12/12/2023 | WBSEDCL | 8.89 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (with NAHARHAT BANDAR area)NIGAMNAGAR PWSS UNDER JAL JEEVAN MISSION. P1 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000600/2024-2025 | 2301/CD | 23/12/2024 | 21/02/2025 | TAPAN CHANDA | 52.08 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGUMENTATION Of Naharhat Bandar Water Supply Scheme TW No.-I under Jal Jeevan Mission under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000440/2023-2024 | 1708/NMD-II | 18/07/2023 | 17/08/2023 | PRAGATI CONSTRUCTION COMPANY | 9.29 | 0 | 0 | 100
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-I, Augmentation of Naharhat Bandar Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000525/2023-2024 | 362/CD | 22/02/2024 | 22/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-II, Augmentation of Naharhat Bandar Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000526/2023-2024 | 363/CD | 22/02/2024 | 22/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-I, Augmentation of Naharhat Bandar Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000528/2023-2024 | 364/CD | 22/02/2024 | 22/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-I, Augmentation of Naharhat Bandar Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000536/2023-2024 | 374/CD | 27/02/2024 | 27/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | Execution of different works related to NAHARHAT BANDAR & adjacent of NAGARERBARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000513/2023-2024 | 311/CD | 09/02/2024 | 03/02/2025 | GHOSH AND SAHA CONSTRUCTION | 55.81 | 0 | 0 | 30
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-II, Augmentation of Naharhat Bandar Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000530/2023-2024 | 365/CD | 22/02/2024 | 22/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mathabhanga-II, Augmentation of Naharhat Bandar Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000538/2023-2024 | 375/CD | 27/02/2024 | 27/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0 | 0 | 100
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | EXECUTION OF DIFFERENT WORKS (within NAHARHAT BANDAR area) RELATED TO BARA PHALIMARI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000667/2024-2025 | 96/CD | 17/01/2025 | 18/03/2025 | KAJAL KUMAR DE | 20.43 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000280/2025-2026 | 787/CD | 23/05/2025 | 21/08/2025 | CONSTRUCTION DEVELOPMENT PROJECT | 79.37 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF NAHARHAT BANDAR PIPED WATER SUPPLY SCHEME | SM/11486 | Augmentation | Execution of different works related to NAHARHATBANDAR PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 977/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000457/2022-2023 | 1508/CD | 19/01/2023 | 20/07/2025 | GHOSH AND SAHA CONSTRUCTION | 407.26 | 0 | 0 | 30
Total | [13 empty] | 668.83 | 0 | 0