## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Providing functional house hold tap connection (unmetered) 135 nos. in GHOKSADANGA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000494/2021-2022 | 459/MTB | 04/03/2022 | 19/03/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.98 | 4.96 | 99.49 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Providing functional house hold tap connection within command area under GHOKSADANGA Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000113/2022-2023 | 130/MTB | 23/06/2022 | 08/07/2022 | MODERN UN EMP CO OP LAB CONT AND CONST SOCIETY LTD | 4.8 | 4.8 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 180/CD | 27/04/2023 |  | Resource Division | 43.99 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GHOKSADANGA water supply scheme, TW no III,IV AND V under Jal Jeevan Mission under NMD-II, PHE Dte.APD |  |  | ORD/000885/2023-2024 | 2426/NMD-II | 10/08/2023 | 09/09/2023 | QUAZI NOZRUL ISLAM | 34.2 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Providing FHTC and Laying of Pipe line at GHOSKADANGA PWSS under JAL JEEVAN MISSION (PART -Y) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000775/2022-2023 | 1662/CD | 10/02/2023 | 11/04/2023 | SWAPAN SAHA | 30.71 | 0.3 | 0.96 | 48
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Providing FHTC and Laying of Pipe line at GHOSKADANGA PWSS under JAL JEEVAN MISSION (PART ¿X) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000351/2022-2023 | 3004/CD | 29/09/2022 | 29/10/2022 | MODERN UN-EMP CO-OPT LABOUR CONT & CONSTN SOCIETY LIMITED | 30.7 | 14 | 45.6 | 48
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Execution of different works related to GHOSKADANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000780/2022-2023 | 1696/CD | 13/02/2023 | 05/03/2023 | GOUTAM KUMAR DAS | 7.64 | 7.64 | 100 | 100
8 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GHOKSADANGA PWSS ZONE-I TW I |  |  | BILL/02761/2023-2024 | BP-2023-24-632 | 22/02/2024 |  | WBSEDCL | 3.66 | 0 | 0 | null
9 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GHOKSADANGA PWSS ZONE-I TW I |  |  | BILL/02761/2023-2024 | BP-2023-24-632 | 22/02/2024 |  | WBSEDCL | 3.66 | 0 | 0 | null
10 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GHOKSADANGA PWSS ZONE-II TW I |  |  | BILL/02762/2023-2024 | BP-2023-24-631 | 22/02/2024 |  | WBSEDCL | 7.85 | 0 | 0 | null
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Providing FHTC and laying of pipe line at GHOKSADANGA PWSS under Jal Jeevan Mission (Part-Z) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000889/2022-2023 | 1001/CD | 29/09/2022 | 29/10/2022 | PATLAKHOWA UN EMP CO OP LAB CONT AND CONST SOC LTD | 30.71 | 14.6 | 47.53 | 48
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Execution of different works related to GHOSKADANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000368/2023-2024 | 1391/CD | 05/12/2023 | 03/02/2024 | MODERN UN-EMP CO-OPT LABOUR CONT & CONSTN SOCIETY LIMITED | 31.96 | 16.04 | 50.18 | 50
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Execution of different works related to GHOKSADANGA ZONE - I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1210/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000537/2022-2023 | 1780/CD | 02/03/2023 | 30/07/2023 | Z STAR COMMOTRADE PVT LTD | 779.99 | 458.52 | 58.79 | 56
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Execution of different works related to GHOKSADANGA ZONE - II PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1243/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000557/2022-2023 | 1782/CD | 02/03/2023 | 30/07/2023 | Z STAR COMMOTRADE PVT LTD | 638.51 | 311.93 | 48.85 | 50
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Sinking of Big Dia Tubewell at GHOSKADANGA PWSS under JAL JEEVAN MISSION (Z-I: 3rd Site Z-II: HWS & 2nd Site) | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000389/2022-2023 | 1034/CD | 29/09/2022 | 28/11/2022 | LONGLAST PIPES (INDIA) PVT. LTD. | 35.04 | 0 | 0 | 30
16 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GHOKSADANGA TW II ZONE-II. |  |  | BILL/00754/2024-2025 | BP-216/24-25 | 15/07/2024 |  | WBSEDCL | 5.49 | 0 | 0 | null
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GHOKSADANGA PIPED WATER SUPPLY SCHEME | SM/11977 | Augmentation | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part G | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000584/2023-2024 | 600/CD | 11/03/2024 | 10/05/2024 | LIMRA SOCIAL WELFARE SOCIETY | 54.64 | 0 | 0 | 100
Total | [13 empty] | 21537.81 | 832.78 | 3.87